**Strategic Map Update 2017**



**Implementation Planning Worksheet**

**Central Challenge**

**Improve Population Health in Connecticut through Engagement, Innovation, Expertise Leadership, and Action**

# Strategic Priority or Goal: [Strengthen Approaches and Capacity to Improve Population Health]

# Track of Work/Objectives: [Maintain PHAB Accreditation and Prepare for Reaccreditation]

|  |  |  |  |
| --- | --- | --- | --- |
| **Result** | **Deadline** | **Accountability** | **Status/Comment** |
| 1) For the SHIP, provide references to the evidence base for the specific strategies chosen for implementation (i.e., SHIP Action Agendas) [5.2.2]  | December 31, 2017 | PHSI | Completed |
| 2) Establish formal agreements with universities to conduct research involving human subjects and establish a policy to describe how the CTDPH will work with such institutions [10.2.1] | December 31, 2017 | Health Statistics and Surveillance | Completed |
| 3) Review actions taken/issues discussed by governing entity to determine patterns, trends, issues, successes, and areas where increased communication is needed [12.3.2] | December 31, 2017 | Government Relations, Commissioner’s Office | Completed – developed new tracking tool |
| 4) Increase % of DPH programs with PMs and targets in the dashboard to 70% | December 31, 2017 | All, PHSI | ~60% |
| 5) Identify telecommunication services and process to access for visually or hearing impaired. | July 31, 2017 | Communications, OHE, AAO, HR | Completed – Information to be updated on website |
| 6) Complete one Low Priority and one Medium Priority Opportunity for Improvement | November 30, 2017 | All | On Track – one Low Priority Completed, several Medium Priorities in progress |

**Track of Work:** an objective or set of related objectives on the strategic map

**Result:** “what”—a specific outcome to be achieved in support of the track of work/objectives

**Deadline:** “when”—the date by which the result will be achieved

**Accountability:** “who”—the person or group responsible for achieving the result

**Status/Comment: -** the status in reaching the result. Note if: on track, off track, completed (with date), comments as needed.