## PROCEDURE & INSTRUCTIONS
3080 Liquidated Damages Calculator Instructions
Liquidated Damages:
Liquidated damages are a specific sum (or a sum readily determinable) of money, stipulated by the contracting parties, as the amount to be recovered for each day of delay in delivery of the product. Typically, the actual damage amount is unknown or difficult to estimate and is liquidated by the mutual agreement to the rate. Liquidated damages must be based on a reference to a definite standard, such as market value, established experience, or direct inference from known circumstances. Liquidated damages can not be speculative or a penalty.
Rate Determination:
The amount of liquidated damages must be reasonable to ensure that the damages will not be held to be unenforceable. Therefore, the rate of liquidated damages, also, must be reasonable and is figured on a project-by-project basis. On the other hand, you do not want to set the liquidated damages at too low an amount. Once liquidated damages are included in a contract, you will be unable to recover actual damages in excess of the specified amount.
Two per diem rates will be determined using the Liquidated Damages Calculator (Form 3080)
Liquidated Damages per Calendar Day beyond Substantial Completion
The first rate will apply to each calendar day of non-concurrent contractor delay in reaching substantial completion as stated in the contract.
Liquidated Damages per Calendar Day beyond 90 days after Substantial Completion
The second rate will apply to each calendar day in excess of 90 days beyond substantial completion of which final completion has not been achieved.
Elements of Rate determination:
(All rates to be based on daily costs)
Design Consultant Fees – calculated as the construction administration portion of the consultant fee divided by the project duration it is based on increase by 3% per year based on duration. If not known, use estimate.
Construction Administrator Fees - calculated as the construction administration portion of the construction administration fee divided by the project duration it is based on increase by 3% per year based on duration. If not known, use estimate
Liquidated Damages Calculator Instructions - Continued
State Funded Field Costs – this should include items such as trailers, phone service, copiers/fax machines, etc.
Temporary Heat/Cooling/Electric, Owner provided – calculated at $ 0.012 per S.F. of project area/day
Temporary Storage of Owner provided FFE – Costs for storage of Furniture, Fixtures, and Equipment, or other storage of products or materials caused by the delayed turn over of the facility. (20ft storage trailer - $2.33/day; 40ft storage trailer - $2.67/day)
Rental/Lease of Facilities for Students, Staff, and/or Clients – calculated in coordination with the agency representative based upon specific needs and available alternatives
(60ft x 24ft office trailer - $36.67/day)
New Staff Wages – wages for new employees intended to serve completed project for which no alternative work or benefit may be achieved prior to completed project
Project Manager/Assistant Project Manager Time – calculated at $ 620 per day per position (based on an average wage of $82.68 per hour multiplied by 7.5 hours per day)
Agency Administrative Costs – based upon daily rate for agency personnel assigned to work on project or agency personnel required to spend a portion of their time should be included at that percentage of the daily rate. If daily rate is unknown or unavailable, use $600/day.
DCS Project Overhead - based upon daily rate for DCS administrative overhead costs not recovered in PM billing rate. Calculated at $35.76/ day.

## FORM 3080
3080
Liquidated Damages Calculator
Enter Design Consultant's total CA fee (during construction) |  |  | 0
Enter Design Consultant's duration (days) of CA fee |  |  | 0
Enter Construction Administrator's total CA Fee |  |  | 0
Enter Construction Administrator's duration (days) of CA Fee |  |  | 0
Enter Total Project Enclosed Square Footage |  |  | 0
Enter Total Daily DCS PM/APM Full time Equivalents |  |  | 0
Design Consultant Fees |  |  | #DIV/0! | /day
Construction Administrator Fees |  |  | #DIV/0! | /day
State Funded Field Costs * |  |  | 0 | /day
Temporary Heat/Cooling/Electric |  |  | 0 | /day
Temporary Storage of Owner Provided FFE * |  |  | 0 | /day
Rental/Lease of Facilites for Students, Staff, and/or Clients* |  |  | 0 | /day
New Staff Wages * |  |  | 0 | /day
Project Manager/Assistant Project Manager |  |  | 0 | /day
Agency Administrative Costs * |  |  | 0 | /day
DCS Project Overhead |  |  | 35.76 | /day
Lost revenues* |  |  | 0 | /day
Security * |  |  | 0 | /day
Other * |  |  | 0 | /day
Liquidated Damages per Calendar Day
beyond Substantial Completion |  |  | #DIV/0! | /day
For DCS Project #:
Design Consultant Fees |  |  | #DIV/0! | /day
Construction Administrator Fees |  |  | #DIV/0! | /day
State Funded Field Costs * |  |  | 0 | /day
Project Manager/Assistant Project Manager |  |  | 0 | /day
DCS Project Overhead |  |  | 35.76 | /day
Security* |  |  | 0 | /day
Other * |  |  | 0 | /day
Liquidated Damages per Calendar Day
beyond ninety (90) days after Substantial Completion |  |  | #DIV/0! | /day
* basis for costs must be included on/or attached to this form
Agency Review
By:
Typed or Printed Name |  | Signature | Date