SCHOOL CONSTRUCTION GRANTS

What You Need to Know Before Applying for a Grant:

School Buildings & Duties of the Board of Education
Local Needs Assessment
School Construction Reimbursement Percentages
Current Policy of SDE Regarding Code Compliance
Progress Payments General Discussion
Summary of Key Grantee Responsibilities
Grant Procedures:

Part One: 
Applying for a Grant
Part Two:
Local Authorization of Project Funding
Part Three:
Request State Share of Design Costs
Part Four:
Site and/or Purchased Building—SDE Inspection & Approval for Use

Request State Share of Acquisition Costs
Part Five:
Architectural Plan Approval
Part Six:
Bid SDE-Approved Plans

Issue Contracts and Notify SDE of Start of Construction

Request State Share of Eligible Construction Costs
Part Seven:
The Progress Payment Cycle
Part Eight:
Project Completion and Audit
Appendices:
State Project Number Abbreviations

Changes in Project Cost and/or Scope

Project Disapproval and Nullification of Eligibility

General Contractor vs. Construction Manager (Bidding Requirements)

SDE Policy on Allowances

Change Orders and Addenda
INDEX
SCHOOL BUILDINGS & DUTIES OF THE BOARD OF EDUCATION 


Section 10-220(a) of the Connecticut General Statutes addresses duties of the local Board of Education.  This law cites multiple responsibilities including but not limited to the following for school buildings:

· Each local or regional board of education shall provide an appropriate learning environment for its students which includes:  adequate instructional books, supplies, materials, equipment, staffing, facilities and technology; equitable allocation of resources among its schools; and a safe school setting.

· Each local or regional board of education shall have charge of the schools of its respective school district.

· Each local or regional board of education shall make a continuing study of the need for school facilities and of a long-term school building program and from time to time make recommendations based on such study to the town.

· Each local or regional board of education shall have the care, maintenance and operation of buildings, lands, apparatus and other property used for school purposes.

· Each local or regional board of education shall at all times insure all such buildings and all capital equipment contained therein against loss in an amount not less than eighty percent of the replacement cost. 

LOCAL NEEDS ASSESSMENT


· The Board of Education must make a continuing study of the need for school facilities.  

· Continuous assessment of local situations is necessary for proper planning and early recognition of school construction needs in advance of crisis situations.

· Research is required to fully define a construction project and establish a clear course of action.  The extent of research is driven by the nature of construction (i.e., building of a new school warrants more analysis and evaluation than a roof replacement). 

· In performing research, contact neighboring districts to explore common goals, economize state and local funding resources, and learn from others’ construction experiences—both good and bad.

· Failure to perform adequate research may result in development of incomplete Educational Specifications, pursuit of a school construction project which does not address all of your needs, costly change orders during the course of construction, or insufficient local support for the project and defeat at referendum.   

SCHOOL CONSTRUCTION REIMBURSEMENT PERCENTAGES


The state school construction grants pay upon a 20% to 80% sliding scale, a percent of eligible expenditures in accordance with a relative wealth rank.  Percentages are assigned to a project based upon date of grant commitment.  (See Reimbursement Rate Exceptions and Bonuses.)

Reimbursement rates for projects are determined based upon the date that funding is locally authorized in an amount sufficient to at least cover the local share of the project.  Local share is defined as total project costs less the state school construction grant.  School construction projects are typically authorized for the full amount of project costs but financed for only the local share.

See
Determination of School Construction Reimbursement Percentages
DETERMINATION OF

SCHOOL CONSTRUCTION REIMBURSEMENT  PERCENTAGES

The state school construction grants pay, upon a 20% to 80% sliding scale, a percent of eligible expenditures in accordance with a relative wealth rank.  Poorer towns receive higher percentages of state support because of their lesser ability to support these costs with local tax dollars. The Adjusted Equalized Net Grand List per Capita (AENGLC) pursuant to C.G.S. 10-261(a)(5) is the measure of wealth.

AENGLC is defined as a combination of property tax base per person and income per person.  Property tax base is used because it is the form of wealth taxed by Connecticut’s towns.  Per Capita Income (PCI) is used because the income from which taxes are paid has an important effect on town taxing capacity.  ENGL is the Equalized Net Grand List which represents the value of taxable real and personal property at 100% of fair market value.  The determination of AENGLC is computed as follows:



       ENGL

X
          PCI


Population
Highest PCI

For 1999-2000 the following data was used:


1995 ENGL


1996 Population


1989 PCI

Since the data used to derive AENGLC is town-based, for regional school districts, regional education service centers (RESCs), the endowed academies and approved interdistrict cooperative schools, statute provides for member population-weighted wealth ranks to be used to derive their percentages.

REIMBURSEMENT RATE EXCEPTIONS AND BONUSES


· Approved regional special education facilities, vocational agriculture centers and interdistrict magnet schools are eligible for 95% state funding. 

· Projects for central administration are eligible for half the state reimbursement percentage.  The exceptions are projects for roof replacement or correction of code violations which are eligible for the full rate.

· Secondary and K-12 regional districts receive additional 5 and 10 percentage points respectively, not to exceed 85%.

· The expansion, alteration or renovation of an existing public school for conversion to an approved lighthouse school pursuant to C.G.S. 10-266cc is eligible for an additional 10 percentage points.

· Construction projects for public schools may be increased up to an additional 10 percentage points based on the number of out-of-district (CHOICE) spaces for participation in programs pursuant to C.G.S. 10-266aa as amended by Public Act 99-289(13).

· New construction or expansion of an elementary school for approved school readiness programs pursuant to C.G.S. 10-16p is eligible for an additional 5 percentage points, not to exceed 95%, for that portion of the building used primarily for such school readiness program.

· Subject to C.G.S. 10-285a(h) and 10-285d, projects for construction at an elementary school building in a priority school district or for a priority school, if necessary to offer an approved full-day kindergarten program pursuant to C.G.S. 10-265f, are eligible for an additional 10 percentage points for the portion of the building used primarily for such full-day kindergarten program. 

· Subject to C.G.S. 10-285a(h) and 10-285d, projects for construction at an elementary school building in a priority school district or for a priority school, if approved as necessary to reduce class size pursuant to C.G.S. 10-265f, are eligible for an additional 10 percentage points for the portion of the building used primarily for such reduced class sizes.

CURRENT POLICY OF SDE REGARDING CODE COMPLIANCE


· All current project work must comply with applicable codes including any existing systems that interface with current project work.  Any other code violations (not part of the project being reviewed) that are evident from the drawings provided shall be documented and the applicant and appropriate code officials shall be notified of SDE findings.

· In the event of substantial alteration or extension of a building, SDE will review the entire facility to the extent appropriate to determine building conformance with Section 504 and ADA accessibility regulations for persons with disabilities.

· Local education agencies will not be required to provide SDE with any written plan or specific time frame within which they will address code/ADA violations noted during the review but determined to be beyond the scope of the project under review.  Notice of the violations and the language from the various codes regarding remediation will be provided to the local education agencies for information purposes.

There is no SDE regulation that prohibits a district from adding a wing to an existing building without updating the entire facility for code compliance.  Similarly, a project for alterations on a portion of a building would carry no obligation to address the entire building for code compliance.  Lastly, a project undertaken to correct certain specific code issues is allowable even though other code issues in the building are not being acted upon at that time.

Enforcement of codes is under the jurisdiction of other State and Federal agencies.  Please call the Plan Review Staff with any questions.

PROGRESS PAYMENTS GENERAL DISCUSSION


· Section 10-287i of the Connecticut General Statutes requires grants for all school construction projects authorized by the General Assembly during the 1997 session and beyond and grants for all code projects approved on or after July 1, 1997, to be paid on a current basis during the course of construction.  SDE refers to this payment process as PROGRESS PAYMENTS.

· Progress Payments are wired into a Reich & Tang tax-exempt mutual fund.  Unlike non-Progress Payment projects, the State retains all interest accrued on unused balances.  Therefore, a separate sub-account must be established with Reich and Tang before any Progress Payments can be made.  Contact Annette McCall at (860) 713-6466 with any questions related to setting up this account.

· Progress Payments require two months of SDE processing time.  Therefore, cash needs must be projected at least 60 days in advance by the district.  Payment requests may be submitted no sooner than every other month.  Payment requests received within a month of the previous request will not be processed.  See Sample Progress Payment Timelines.

· Progress Payments may be released for Architectural Design, Site Acquisition, or Construction needs.  Payment is contingent upon districts meeting specific requirements.  See table titled Progress Payment Requirements Prior to Reimbursement.

· The State withholds five percent of the grant pending completion of an audit.  (This five percent is withheld from each Progress Payment made.)  This means that at the conclusion of the project, it will be necessary for the district to temporarily cover the full costs of the remaining five percent of project costs.  See Project Completion and Audit.

PROGRESS PAYMENT REQUIREMENTS PRIOR TO REIMBURSEMENT

	Type of  Expenditure
	State Grant Authorization
	SDE Site Inspection & Approval
	Two Independent Appraisals
	Purchase Price Document
	SDE Architectural Plan Approval

	Architectural Design and Professional Fees
	X
	
	
	
	

	Site Acquisition
	X
	X
	X
	X
	

	All Other Costs

(Construction and

FF&E)
	X
	
	
	
	X


See also
Sample Progress Payment Timelines

Request State Share of Design Costs

Request State Share of Site Acquisition Costs

Request State Share of Eligible Construction Costs
SAMPLE PROGRESS PAYMENT TIMELINES

	Two-Month Period Covering Planned Expenditures
	Date By Which SFU Must Receive Form ED046 
	SDE Review & Processing
	Date By Which Payment will be Made to Reich & Tang Sub-Account

	
	
	
	

	Dec / Jan
	November 1
	Month of November
	December 15

	Jan / Feb
	December 1
	Month of December
	January 15

	Feb / Mar
	January 1
	Month of January
	February 15

	Mar / Apr
	February 1
	Month of February
	March 15

	Apr / May
	March 1
	Month of March
	April 15

	May / Jun
	April 1
	Month of April
	May 15

	Jun / Jul
	May 1
	Month of May
	June 15

	Jul / Aug
	June 1
	Month of June
	July 15

	Aug / Sept
	July 1
	Month of July
	August 15

	Sept / Oct
	August 1
	Month of August
	September 15

	Oct / Nov
	September 1
	Month of September
	October 15

	Nov / Dec
	October 1
	Month of October
	November 15


SUMMARY OF KEY GRANTEE RESPONSIBILITIES


The following are highlights only; this is not intended to be an all-inclusive list.  

· Records must be maintained for a period of three years following final audited payment of a School Construction grant.  Records must include documentation which discloses all project and site acquisition costs and the amount, sources and disposition of all funds received for a project.

· For purposes of audit, all books, documents, papers and records of the applicant that are pertinent to the grant shall be submitted for state review upon SDE request.

· All proceeds of a school building project grant must be promptly applied to meet project costs or site acquisition costs, if applicable.

· No school building project for which state assistance is sought shall be undertaken at an expense exceeding the sum which the town or regional district may approve for the project.

· If a grant overpayment is made to an applicant, the amount of such overpayment shall be repaid upon SDE request.

· No project or phase thereof, for which state assistance is sought, may go out for bidding purposes without prior written approval of the plan and site by SDE.

· The grantee shall promptly notify the commissioner of the Start of Construction Date.

· All legislative and regulatory requirements are to be met in the awarding of contracts.  Bidding requirements must comply with the provisions of C.G.S. Section 10-287(b), and the SDE Policy on Allowances.

· The applicant shall notify SDE promptly, and submit copies for approval, of any final plan changes, Change Orders and Addenda.

· Final application for a school building project grant is to be made within 1 year of completion and acceptance of the project by the local board of education.  Failure to submit the final application within one year may result in the withholding of ten per cent of the state grant for a project.

PART ONE:  APPLYING FOR A GRANT

Application Submission Deadlines

Priority List Projects

· June 30 is the filing deadline for Priority List projects to be submitted to the Governor and the General Assembly for consideration during the subsequent regularly scheduled session.

· Grant commitments will not become effective until such projects have been approved by the General Assembly and the bill has been signed by the governor.

Non-Priority List Projects

· Projects to remedy damage from fire and catastrophe, to correct safety, health and other code violations, to replace roofs, to purchase relocatable classrooms, or to remedy an indoor air quality emergency may be submitted continuously throughout the fiscal year. 

See also 
Types of Priority List Projects

Types of Non-Priority List Projects
PART ONE:  APPLYING FOR A GRANT

Types of Priority List Projects

Of the projects eligible for school construction grants, Priority List projects include all types of construction except projects to replace roofs, remedy damage from fire and catastrophe, to correct safety, health and other code violations, to purchase relocatable classrooms, or to remedy a certified indoor air quality emergency.  (See Non-Priority List Projects.)  Priority List projects include the following:

Alteration
Facility Purchase
Energy Conservation
Renovation
Extension 
Educational Technology Infrastructure

New Schools 
Vocational Agriculture Equipment
Priority List projects must be submitted to the General Assembly with a request for authorization to enter into grant commitments.

Grant commitments for Priority List projects become effective only after such projects have been approved by the General Assembly and the bill has been signed by the governor.

Priority List projects are subject to a Start of Construction Deadline.

See also
Priority List Projects—Priority Category Placement

Key Dates for Priority List Projects
PART ONE:  APPLYING FOR A GRANT

Priority List Projects—Priority Category Placement

In accordance with C.G.S. 10-283(a)(2), Priority List projects are assigned to one of three categories based upon the described need for the project.  For category definitions and examples, see:


Priority Category A

Priority Category B

Priority Category C
By October 1, SDE will notify applicants of the assigned category for Priority List projects which were submitted prior to the preceding June 30.  Note that if additional information is received for a project after initial category placement, a re-evaluation may occur and a revised category placement may be issued, if warranted.

PRIORITY CATEGORY A


Per the law, Priority Category A projects create new facilities or alter existing facilities to provide for mandatory instructional programs pursuant to this chapter, for physical education facilities in compliance with Title IX of the Elementary and Secondary Education Act of 1972 where such programs or such compliance cannot be provided within existing facilities or for the correction of code violations which cannot be reasonably addressed within existing program space.

Typical examples of Category A projects:

· Addition of 1,000 square feet of space to an existing women’s locker room at a high school to achieve compliance with Title IX

· Building a new middle school to alleviate extreme overcrowding within a district

PRIORITY CATEGORY B


Per the law, Priority Category B projects create new facilities or alter existing facilities to enhance mandatory instructional programs pursuant to this chapter or provide comparable facilities among schools to all students at the same grade level or levels within the school district unless such project is otherwise explicitly included in another category pursuant to this section 

Typical examples of Category B projects:

· Projects for LANs and other educational technology infrastructure improvements when done as alterations to existing buildings 

· Expansion of the existing media center at a middle school to make it comparable to the facilities at a second middle school within a district

· Projects for purchase of Vocational Agriculture Equipment needed to enhance programs at a regional vocational agriculture center

· A project for construction of a new elementary school to replace one that is in a state of disrepair and can no longer be feasibly maintained

PRIORITY CATEGORY C


Per the law, Priority Category C projects create new facilities or alter existing facilities to provide supportive services, provided in no event shall such supportive services include swimming pools, auditoriums, outdoor athletic facilities, tennis courts, elementary school playgrounds, site improvement or garages or storage, parking or general recreation areas.

Typical examples of Category C projects:

· Projects for window replacements for energy conservation reasons at existing facilities

· All projects at Board of Education Central Administration offices (except projects solely for the correction of code violations which are deemed Non-Priority List Projects).  See also Types of Non-Priority List Projects. 

PART ONE:  APPLYING FOR A GRANT

Typical

 Dates for Priority List Projects

June 30, 2008
Deadline for Priority List projects to be submitted to Governor and General Assembly for consideration during the subsequent regularly scheduled session

Oct. 1, 2008
SDE notifies applicants of assigned Priority Category for Priority List projects

Dec. 15, 2008
SDE submits Priority List to Governor and Education Committee 

Feb. 1, 2009 
Education Committee submits approved or modified Priority List to Governor and General Assembly  

Spring/Summer 2009 
General Assembly authorizes Commissioner of Education to enter into grant commitments on behalf of the state, AND

SDE notifies applicants of grant commitments for projects on Priority List

Summer 2009
After applicants receive grant commitments, construction processes begin

Spring/Summer 2011
Start of Construction Deadline 

PART ONE:  APPLYING FOR A GRANT

Types of Non-Priority List Projects

Projects to remedy damage from fire and catastrophe, to correct safety, health and other code violations, to replace roofs, to purchase relocatable classrooms, or to remedy a certified indoor air quality emergency do not require submission to the Governor and the General Assembly.  The commissioner has the authority to issue grant commitments for these types of projects.
Grant commitments for such Non-Priority List projects are issued after a complete grant application is received by SDE and approved by the commissioner.  

Non-Priority List projects are subject to a Start of Construction Deadline.

See also 
Code Updates.


Roof Replacements

Relocatables

Certified Indoor Air Quality Emergency
PART ONE:  APPLYING FOR A GRANT

Complete Application Package

The application for a school construction grant must include all of the following:

Form ED049
Certified Copies of the Three Local Legislative Authorizations
Educational Specifications for the Project
Board of Education’s Written Approval of Educational Specifications
Enrollment Projections
Programmatic Approval (interdistrict magnets, vocational agriculture, regional special ed)
Vo-Ag Equipment List, if Applicable
Cost Estimating Worksheet (Part B)
Local Funding Authorization
Grant Application Submission Check-List
Form ED049 is required to be electronically submitted via the School Construction Grant Management System (SCGMS).  All other supporting documentation may be compiled and delivered to:


State Department of Education



Bureau of School Facilities – Room 258



165 Capitol Avenue


Hartford, CT  06106


Or mailed to:



State Department of Education




Bureau of School Facilities – Room 258



P. O. Box 2219



Hartford, CT  06145

PART ONE:  APPLYING FOR A GRANT

Form ED049

Grant Application and Executive Summary of Educational Specifications for a

School Building Project

The ED049 form is the multiple page grant application for a school construction project.  It collects a variety of data about a proposed project including but not limited to:  reason(s) for project, cost information, financing information, nature of work to be undertaken, square footage details, projected enrollment, and grade range.  Click here to access the ED049 form and its instructions.

See also application hints in the following areas:
Square Footage

Grade Range

Highest 8-Year Projected Enrollment
SQUARE FOOTAGE


For projects subject to Space Standards, existing square footage will be pre-filled on the School Construction Grant Management System (SCGMS) electronic Form ED049 with the amount of square footage as last reported by the district on Form ED050, School Facilities Survey.
After plan review has taken place, square footage will be revised to be consistent with the architectural plans submitted for the project.

Building Area Definition

For grant purposes square footage is Building Area as defined in the State Building Code.  It is the area included within surrounding exterior walls (or exterior walls and fire walls) exclusive of vent shafts and courts.  Areas of the building not provided with surrounding walls shall be included in the building area if such areas are included within the horizontal projection of the roof or floor above.

GRADE RANGE


For projects subject to Space Standards, grade range reported on Form ED049 must be consistent with the grade range listed in the Connecticut Education Directory.

If the grade range does not match that in the Connecticut Education Directory, the Educational Specifications for the project must contain an acceptable explanation (e.g., redistricting of students or reconfiguration of grades within a district’s schools).

HIGHEST 8-YEAR PROJECTED ENROLLMENT


For projects subject to Space Standards, the enrollment projection:

· must be taken from an 8-year window period which begins with projected enrollment for the October following your application.

· may be revised only until the date of plan submission, however, the window period cannot be changed

· must be a bonafide projection specific to the school facility for which a grant application is submitted

· may be documented by projections created by SDE (if adjusted to the specific facility) or by the New England School Development Council (NESDC)

· may be created internally by the district if a reasonable methodology is used and documentation supports the data

NEW
Enrollment projections are required to be submitted as part of the grant application effective for applications submitted July 1, 2007 and later.  For grant applications submitted prior to July 1, 2007, enrollment projections may be requested during the course or construction and, if not provided sooner, will be requested at the time of audit.

See Highest Eight-Year Projected Enrollment Example
EXAMPLE OF EIGHT-YEAR PROJECTED ENROLLMENT


For an application received by SDE on June 30, 2008, the 8-year window period would begin with October 2008 and would end with October 2015.  In this example, the highest 8-year projected enrollment would be 575.

	Time Period


	Oct

2008
	Oct

2009
	Oct

2010
	Oct

2011
	Oct

2012
	Oct

2013
	Oct

2014
	Oct

2015

	Projected Enrollment
	500
	515
	525
	529
	548
	561
	575
	560


BE REMINDED THAT BUILDING CAPACITY IS NOT THE SAME THING AS PROJECTED ENROLLMENT.  CAPACITY CANNOT BE SUBSTITUTED FOR PROJECTED ENROLLMENT.

PART ONE:  APPLYING FOR A GRANT



	Certified Copies Of The 

	Three Local Legislative Authorizations

	

	

	As required by statute, application for a school construction grant must include a certified copy of three authorizations adopted by the Local Legislative Body.

	

	The three authorizations may be done as one or as several resolutions.  They must cover the following:

	

	1)  the board of education must be authorized to apply to the Commissioner of Education

     and to accept or reject such grant 

	

	2)  a building committee must be established for the project 

	

	3)  authorization must be given for at least the preparation of schematic drawings and 

     outline specifications for the proposed project

	

	See Appointment of a Building Committee
       Samples of Three Local Authorizations

	


PART ONE:  APPLYING FOR A GRANT

Appointment of a Building Committee

For each construction project, a building committee must be officially appointed.  The building committee interacts with design professionals, board of education members, parents, teachers, other local committees, and the State Department of Education.  In effect, they are in the driver’s seat of the project and are responsible for implementing the educational specifications approved by the Board of Education.

Specific duties, responsibilities, and authority of the building committee are not defined in statute or regulation.  When appointed, the building committee should have a specific charge and a clearly defined place in the district’s hierarchy.  Outlining these things up front will prevent questions of authority and responsibility as the project progresses.

· Exercise caution when appointing committee members giving heed to potential conflicts of interest.

· Be mindful of the duration of school construction projects when appointing members to a building committee.  New schools can take four or more years to complete.

See also:
Standing Building Committees

Building Committee Size

Building Committee Constitution
STANDING BUILDING COMMITTEES


· Projects are sometimes referred to public building commissions or permanent school building committees. 

· For projects referred to a standing building committee, the application for grant must still include a certified copy of a local legislative authorization for a building committee.  

· The language for the resolution should include a project-specific reference and a referral to the standing committee. 

BUILDING COMMITTEE SIZE


Committee size should be determined by the nature of construction.  For smaller code update projects or roof replacements, a committee may consist of one or a handful of members.  For construction of a new school, a larger committee should be appointed to include members having expertise in a variety of areas.

· Exercise caution when appointing committee members giving heed to potential conflicts of interest.

· Be mindful of the duration of school construction projects when appointing members to a building committee.  New schools can take four or more years to complete.

BUILDING COMMITTEE CONSTITUTION


A committee should include members selected for professional expertise they bring to a project (e.g., architects, engineers, financial advisors, and contractors).  Members who represent the field of education and the community at large should also be given consideration.

· Exercise caution when appointing committee members giving heed to potential conflicts of interest.

· Be mindful of the duration of school construction projects when appointing members to a building committee.  New schools can take four or more years to complete.

	SAMPLES OF THREE LOCAL AUTHORIZATIONS

	

	

	Replace the underscored/italicized phrases as appropriate.

	

	

	RESOLVED, that the legislative body authorizes the town/district/RESC/academy Board of Education to apply to the Commissioner of Education and to accept or reject a grant for the proposed project at the school name.

	

	RESOLVED, that the building committee is hereby established as the building committee with regard to the proposed project at the school name.

	

	RESOLVED, that the legislative body hereby authorizes at least the preparation of schematic drawings and outline specifications for the proposed project at the school name.

	


	LOCAL LEGISLATIVE BODY

	

	As defined in the Section 10-287c-1(9) of the Connecticut General Statutes, the legislative body is:

	

	

	Grant Applicant
	Legislative Body

	Regional School District
	Board of Education

	Regional Education Service Center
	Governing Board

	Municipality
	Governing Body (e.g., Representative

Town Meeting, Board of Selectman)

	Incorporated or Endowed High School or Academy

Eligible for School Construction Pursuant to 

C.G.S. 10-285b
	Governing Board


EDUCATIONAL SPECIFICATIONS


Definition



 HYPERLINK "http://www.ct.gov/dcs/lib/dcs/bsf/grantprocess/edspec.doc" 

Development Suggestions



 HYPERLINK "http://www.ct.gov/dcs/lib/dcs/bsf/grantprocess/edspec.doc" 

Components



 HYPERLINK "http://www.ct.gov/dcs/lib/dcs/bsf/grantprocess/edspec.doc" 

State Requirements



 HYPERLINK "http://www.ct.gov/dcs/lib/dcs/bsf/grantprocess/edspec.doc" 

Sample Project Extracts from Full Educational Specifications



BOARD OF EDUCATION APPROVAL

OF EDUCATIONAL SPECIFICATIONS

C.G.S. Section 10-287c-11 requires an application for a school construction grant include one copy of the educational specifications for the project as approved by the local or regional board of education or governing body of such other eligible grant recipient.

Therefore, a copy of the resolution approving the educational specifications must be submitted as part of the grant application for the proposed school construction project.

PROGRAMMATIC APPROVAL

Formal approval by the appropriate SDE programmatic office for specific types of school construction projects is required in order to secure a 95 percent reimbursement rate for the project.  Formal programmatic approval is also needed to complete the school construction grant application for these projects as follows:
Program Type




SDE Program Office
Interdistrict Magnet Schools:
Sheff Magnet



SDE Sheff Office
Jack.Hasegawa@ct.gov
Other Magnets



Bureau of Choice Programs

Mark.Linabury@ct.gov
Vocational Agriculture



Bureau of Curriculum and Instruction







Gregory.Kane@ct.gov
Regional Special Education Center

Bureau of Special Education








AnneLouise.Thompson@ct.gov
VOCATIONAL AGRICULTURE EQUIPMENT LIST


Vocational Agriculture Equipment must be approved by the SDE Bureau of Curriculum and Instruction within the Division of Teaching, Learning and Instructional Leadership before it can be eligible for 95 percent payment as a school construction grant.

A copy of the signed approval letter must be submitted with the ED049 application package.

Contact Greg Kane of the Bureau of Curriculum and Instruction at (860) 713-6756 for information regarding this approval.

See also 
Vocational Agriculture Equipment

Projects Designated as Regional Vo-Ag or Regional Special Education Centers
COST ESTIMATING WORKSHEET

Worksheet Part A

This worksheet is designed to aid districts in preparing and evaluating anticipated project costs.  It includes a list of possible project components for which a district must calculate the cost per square foot.  Also, a calculation is required to determine soft costs as a percentage of construction costs.  

Cost Estimating Worksheet A is incorporated into the school construction grant application (Form ED049) which is required to be electronically submitted via the School Construction Grant Management System (SCGMS).

In the event that the calculated amounts fall outside of the normal range of costs per square foot, a written explanation may be requested of the district as part of the application review.

Costs reported on Part A of the Cost Estimating Worksheet must agree with costs reported on Part B of the Cost Estimating Worksheet.

See also the document
Cost Estimating Worksheet

Cost Estimating Worksheet Part B
COST ESTIMATING WORKSHEET

Worksheet Part B

This worksheet is designed to aid districts in more accurately projecting costs for proposed  projects.  It includes a detailed list of construction costs, by division, which mirrors the industry standard (Construction Specifications Institute).

It is strongly recommended that the Cost Estimating Worksheet Part B be completed by a professional cost estimator.  However, districts may avail themselves of the services of suitably qualified technical staff on the town or district payroll. 

Costs reported on Part B of the Cost Estimating Worksheet must agree with costs reported on Part A of the Cost Estimating Worksheet.

This worksheet is required for each project with estimated costs exceeding $2 million.  It must be received by the Bureau of School Facilities no later than the September 30th following grant application.  For projects costing $2 million or less, submission of the worksheet is not required as part of the application; maintain it at the local level with other project documentation.

See also the document
Cost Estimating Worksheet

Cost Estimating Worksheet Part A
SPACE STANDARDS WORKSHEET


This worksheet will assist districts in computing the maximum allowable square footage that the State Department of Education will support with a state grant for this project.  Space standards are calculated automatically when a grant application (Form ED049) is submitted electronically via the School Construction Grant Management System (SCGMS).
See also the document 
Space Standards Worksheet

Space Standards (Discussion of)


Sample Space Standards Calculations
GRANT APPLICATION SUBMISSION CHECK-LIST


This checklist was developed to insure the completeness of grant applications submitted to the State Department of Education. 

All components of the grant package are listed on this checklist, and a signature to attest to completeness of the application is required.

Click here for a copy of the actual Grant Application Submission Check-List.

REIMBURSEMENT RATE BONUSES

Program Approvals

To qualify for a reimbursement percentage bonus under any of the programs listed below, the program must be certified by the appropriate programmatic division of SDE.  Click on the program of interest.


Interdistrict Magnet

Regional Vocational Agriculture Equipment

Regional Vocational Agriculture Center

Regional Special Education Center

School Readiness Program (Form ED049 Schedule 9)


Lighthouse Schools (Form ED049 Schedule 9)


Out-of-District Students (CHOICE) (Form ED049 Schedule 9)


Full-day Kindergarten (Form ED049 Schedule 9)


Reduced Class Size (Form ED049 Schedule 9)

Projects Designated as

INTERDISTRICT MAGNET SCHOOL

For construction projects at SDE-approved Interdistrict Magnet Schools, special endorsement of the proposed operating plan is required in order to receive a grant for 95 percent of eligible construction costs.  Formal programmatic approval is required to complete the grant application (Form ED049) for Interdistrict Magnet School construction projects.

Copies of the formal operating plan approval by the Commissioner must be included with the school construction project grant application package submitted for the June 30 deadline.  Failure to receive the necessary program approval may result in the proposed project not being submitted to the legislature for a grant commitment.

Progress payments for a magnet school cannot be made without the approval of the plan of operations by the commissioner.

For non-construction questions regarding interdistrict magnet schools and for guidance regarding the plan of operations, contact Mark Linabury, Chief, Bureau of Choice Programs at (860) 807-2119.

Questions regarding interdistrict magnet schools approved pursuant to the Sheff v. O’Neill settlement, including guidance for their plan of operations, contact Jack Hasegawa , Sheff Office at (860) 713-6544.

For construction questions and to request a waiver of the Space Standards, contact the Bureau of School Facilities.
Projects Designated as

REGIONAL VO-AG OR REGIONAL SPECIAL EDUCATION CENTERS

For projects at State Board of Education approved Regional Vocational Agriculture Centers or Regional Special Education Centers, special approval of the proposed project is required in order to receive a grant for 95 percent of eligible construction costs.

· Copies of the program approval must be included with the application for grant.

· Failure to receive the necessary endorsements may result in less than 95 percent reimbursement for a project.

Regional Vo-Ag Center projects
To obtain written approval for the project and for non-construction questions regarding Regional Vocational Agriculture Centers, contact Greg Kane of the Bureau of Curriculum and Instruction at (860) 713-6756.

Regional Special Education Center projects
Circular Letter C-6 issued August 19, 2003 by the Commissioner notified districts that the Department would not be able to accept, review and recommend to the State Board of Education the approval of Section 10-76e school construction grants other than code compliance projects.  This decision was the result of the settlement agreement arising from the disposition of P.J., et al v. State of Connecticut, Board of Education et al.  Generally, the Department supports the belief that goals for students with disabilities are best achieved in the child’s local school and in a least restrictive environment consistent with the intent, spirit and language of the Individuals with Disabilities Education Act (IDEA). 
To obtain more information regarding program approval for regional special education centers, contact Anne Louise Thompson, Chief, Bureau of Special Education.
For construction questions and to request a waiver of the Space Standards, contact the Bureau of School Facilities
See also Vocational Agriculture Equipment List.

SCHOOL READINESS

· The project must be for a new elementary school building or the expansion of an existing elementary school building.

· The project must include space for a school readiness program.

· If approved, the reimbursement percentage shall be increased by five percentage points, but shall not exceed one hundred percent, for the portion of the building used primarily for school readiness.

· The total square footage of the project area, and that portion of such square footage that is to be used primarily for the school readiness program, are required in order to calculate the bonus.  (See ED049 Schedule 9.)

For programmatic questions related to School Readiness, contact Harriet Feldlaufer, Chief, Bureau of Early Childhood Education, at (860) 713-6528.

For construction questions, contact the Bureau of School Facilities.

LIGHTHOUSE SCHOOLS


· This project must be located in an existing public school building and must be for the expansion, alteration or renovation necessary to convert the building for use as a lighthouse school.

· If approved, the reimbursement percentage shall be increased by ten percentage points.

For programmatic questions related to Lighthouse Schools, contact attorney Karen Flanagan, Director, Division of Legal and Governmental Affairs, at (860) 713-6517.

For construction questions, contact the Bureau of School Facilities.

OUT-OF-DISTRICT STUDENTS (CHOICE)


· Spaces must be made available for out-of-district students participating in the program established pursuant to section 10-266aa.

· If approved, the reimbursement percentage shall be increased by the number of CHOICE spaces made available, expressed as a percentage of the total projected enrollment of the school, provided that such percentage increase shall not exceed ten percent.

· The number of spaces that will be made available to such out-of-district students is required in order to calculate the bonus.  Note that the number of CHOICE spaces made available must be included in the total enrollment projection figure.  (See ED049 Schedule 9 and Schedule 6, Item f.)

For programmatic questions related to CHOICE, contact Mark Linabury, Chief, Bureau of Choice Programs, at (860) 807-2119.

For construction questions, contact the Bureau of School Facilities.
FULL-DAY KINDERGARTEN


· The project must be located in either an elementary school building within a priority school district or an elementary priority school building that is in a non-priority school district. 

· The project must also be necessary in order to offer a full-day kindergarten program funded pursuant to an Early Reading Success grant program (C.G.S. 10-265f). 

· If approved, the reimbursement percentage shall be increased by ten percentage points for the portion of the building used primarily for such full-day kindergarten program. 

· The total square footage of the project area, and the portion of such square footage that is to be used primarily for such full-day kindergarten program are required in order to calculate the bonus.  (See ED049 Schedule 9.)

For programmatic questions related to Full-Day Kindergarten, contact Harriet Feldlaufer, Chief, Bureau of Early Childhood Education at (860) 713-6528.

For construction questions, contact the Bureau of School Facilities.

REDUCED CLASS SIZE


· The project must be located in either an elementary school building within a priority school district or an elementary priority school building that is in a non-priority school district.

· The project must also be necessary for a reduced-sized class in grades kindergarten to three, inclusive, funded pursuant to an approved Early Reading Success grant program (C.G.S. 10-265f).

· If approved, the reimbursement percentage shall be increased by ten percentage points for the portion of the building used primarily for such reduced size classes.

· The total square footage of the project area, and the portion of such square footage that is to be used primarily for such reduced size classes are required in order to calculate the bonus.  (See ED049 Schedule 9.)

For programmatic questions related to Reduced Class Size, contact Harriet Feldlaufer, Chief, Bureau of Early Childhood Education, at (860) 713-6528.

For construction questions, contact the Bureau of School Facilities.

PART TWO:  LOCAL AUTHORIZATION OF PROJECT FUNDING


Local funding authorization must cover all project costs including any site acquisition costs.  Section 7-345 of the Connecticut General Statutes requires local authorization of 100 percent of the project costs even if the local authority will actually be funding only its share.

For each school construction project, a district must receive a local authorization to

· expend 100 percent of project revenues and

· finance the Local Share of project costs. 

Specific mechanism of approval is dictated by local charter and the general statutes.

· For minor codes, approval is often tied to funding of a line item in the BOE budget.

· For construction of a new school, funding is often done through a referendum. 

A COPY OF THE LOCAL FUNDING AUTHORIZATION MUST BE SUBMITTED TO THE BUREAU OF SCHOOL FACILITIES IN ORDER TO COMPLETE THE GRANT APPLICATION PROCESS.
See  also
Notifying SDE of Local Funding Authorization.


Local Share

Other Sources of Funding
LOCAL SHARE


Local share is most simply defined as project costs less the state school construction grant.

Local share includes all Ineligible Costs, any costs for building construction in excess of Space Standards, local share of any Limited Eligible Costs, costs paid in excess of appraised values, and adjustment for Other Sources of Funding.
SDE has designed two worksheets for use in determining local share:

Calculation Type 1 is for projects with the following components only:  Code or Health Violation, Roof Replacement, Central Administration (any type of project), Vocational Agriculture Construction or Equipment, or Building Purchase with No Alteration Component.

Calculation Type 2 is for all projects not eligible for Calculation Type 1.

CAUTION:  SIMPLY APPLYING THE DISTRICT’S REIMBURSEMENT RATE TO TOTAL PROJECT COSTS MAY UNDERSTATE THE LOCAL SHARE.

OTHER SOURCES OF FUNDING


Funding which is not directly from the town or the local board of education must be reported separately.  This funding is classified as “Other,” and in the calculation of a school construction grant, these amounts effectively reduce the State Share.

Examples of Other Sources of Funding include, but are not limited to:

Insurance Proceeds

Federal Grants (e.g., Universal Service Fund)

Rebates (e.g., Northeast Utilities)

Other State Grants (e.g., Technology Infrastructure; Connecticut Clean Energy Fund)

See Calculation Type 1 and Calculation Type 2 for details on the impact of Other Funding.

PART TWO:  LOCAL AUTHORIZATION OF PROJECT FUNDING

Notifying SDE of Local Funding Authorization
A copy of the local funding authorization must be submitted to SDE for all school construction projects.  It should be submitted to the Bureau of School Facilities in order to complete the grant application (Form ED049) requirements.  There is no state form for this notification.  Instead, provide the following:

· For projects funded through a referendum, send the language of the referendum question as well as evidence of the voting outcome.

· For projects funded through line item(s) in a budget, send a copy of the budget and evidence of budget approval.

· For projects funded through a vote of the Representative Town Meeting, send a copy of the resolution as voted upon as well as evidence of the voting outcome.

If funding language does not specifically address a project and its corresponding dollar amount, you must also submit a cover letter which identifies projects by name and state project number and which includes individual project allocations.

NO GRANT APPLICATIONS WILL BE CONSIDERED COMPLETE AND NO GRANT COMMITMENTS CAN BE MADE UNTIL A COPY OF THE LOCAL FUNDING AUTHORIZATION HAS BEEN RECEIVED BY THE BUREAU OF SCHOOL FACILITIES.

PART THREE:  REQUEST STATE SHARE OF DESIGN COSTS

The first grant payments for which a district may be eligible is the State Share of Design Costs.  (In the event that the initial payment request includes both Design Costs and Site Costs, see additional requirements under Request State Share of Acquisition Costs.)

Prior to submitting the initial progress payment request, the following criteria must be in place:

Complete Application Package
Grant Commitment
The mechanism by which districts request the State Share is Form ED046, Request for School Construction Progress Payments.  

Note:
Five percent of all grant payments for a project will be withheld until 

· the project is accepted as complete by the district,

· final costs and all other final documentation is submitted to SDE, 

· the audit is completed, and

· the final audited grant amount determined.

See also
Form ED046
GRANT COMMITMENT


Grant commitments for Priority List Projects become effective only after such projects have been approved by the General Assembly and the bill signed by the governor.

Grant commitments for Non-Priority List Projects are issued after a complete grant application is received by SDE and approved by the commissioner.

When a grant commitment is issued, the Bureau of School Facilities will send out a formal letter of notification (“Grant Commitment Notification”) which includes specific language regarding the state’s commitment to a project.

FORM ED046

Request for School Construction Progress Payments

ALL ED046 PAYMENT REQUESTS NEED TO BE
ELECTRONICALLY SUBMITTED VIA THE
SCHOOL CONSTRUCTION GRANT MANAGEMENT SYSTEM (SCGMS)
Form ED046 is due on or before the first of the month.  Because the ED046 payment cycle is a bimonthly one, forecast cash needs at least 60 days in advance.

Payment requests may be submitted no sooner than every other month.  Payment requests received within a month of the previous request will not be processed.

After receipt of Form ED046, SDE performs a project file review.  Issues are identified by SDE and communicated in writing or email to the local BOE.  It is anticipated that a district will work to resolve identified issues by the time of the next payment request submission.  The complete SDE review and payment cycle is about 45 days, but a district’s failure to satisfactorily address outstanding issues will result in a delay of payment. 

Payment is made via wire transfer to the appropriate Reich and Tang subaccount on or about the 15th of the month following ED046 submission.  (e.g., Payment requests submitted on or before November 1 will receive a progress payment on or about December 15.)

See also



ED046 Form and Instructions

Sample Progress Payment Timelines

Ineligible and Limited Eligible Costs

Changes in Project Cost and/or Scope
PART FOUR:  SITE ACQUISITION and/or PURCHASED BUILDING

SDE Inspection and Approval for Use 
Districts must contact SDE to request an inspection and approval of:

· site acquired for a school construction project

· building purchased for use as a school or Board of Education Central Administration

A Site Analysis Form (ED053) must be submitted for all projects which include the acquisition of land.

For reimbursement purposes, no distinction is made between developable and undevelopable land.  If a site includes areas classified as inland wetlands upon which you may not develop, such wetlands and any other unusable portions of a site will be included as part of the total site in determining the acreage for calculation purposes.

See additional requirements and limitations under
Purchase Projects



Purchase Projects—Limits 



Site Acquisition


Site Acquisition—Limits 



Site Acquisition Standards
PART FOUR:  SITE ACQUISITION and/or PURCHASED BUILDING

Request State Share of Acquisition Costs

Prior to submitting a progress payment request for site acquisition costs, the following criteria must be in place:

	Form ED053
	SDE Inspection and Approval for Use

	Complete Application Package
	Two Independent Appraisals

	Grant Commitment
	Actual Site or Facility Purchase Costs


The mechanism by which districts request the State Share is Form ED046 Request for School Construction Progress Payments.  

Purchase costs for a building subject to interior alterations or for relocatable units are not eligible for state share until applicable architectural plan approval is granted by SDE.

Note:
Five percent of all grant payments for a project will be withheld until 

· the project is accepted as complete by the district,

· final costs and all other final documentation is submitted to SDE, 

· the audit is completed, and

· the final audited grant amount determined.  

See also
Form ED046
PART FIVE:  ARCHITECTURAL PLAN APPROVAL


CAUTION:  NO PHASE OF A SCHOOL CONSTRUCTION PROJECT MAY BE LET OUT FOR BID WITHOUT HAVING PRIOR WRITTEN ARCHITECTURAL PLAN APPROVAL FROM THE STATE DEPARTMENT OF EDUCATION.

Projects may be performed in phases; however, each separate and distinct phase of a project must receive SDE architectural plan approval.  Consult Construction Document Guidelines for School Districts and Design Professionals for plan review requirements related to phased projects.

NEW

A Flood Management Certification must be submitted for:  construction at any facility located within a floodplain, construction which will affect a floodplain, and construction which will affect a natural or man-made storm drainage facility.  An application for this certification along with supporting documentation must be submitted to the State Department of Environmental Protection (DEP).  DEP approval shall be forwarded to the School Facilities Unit for review prior to SDE issuance of written plan approval.  Please contact Arthur P. Christian of DEP at (860) 424-3706 with questions about the certification application process.  Please contact Craig Smith of the Bureau of School Facilities at (860) 713-6486 with questions about the role of floodplain certification in the school construction plan approval process.

Local Plan Review Option
Bureau of School Facilities Pre-Review Evaluation Process (PREP) Meeting
Preparation of Final Plans and Specifications
Bureau of School Facilities Plan Completion Test (PCT) Meeting
Bureau of School Facilities Plan Review and Approval Process
Sample Plan Approval Letter
Construction Document Guidelines for School Districts and Design Professionals



PART FIVE:  ARCHITECTURAL PLAN APPROVAL

Local Plan Review Option
The Local Plan Review Option is limited to the following types of projects:

· Oil Tank Replacement (all, regardless of cost)

· Roof Replacement (all, regardless of cost)

· Asbestos Abatement (costs cannot exceed $1 million)

· Code Violation Correction (costs cannot exceed $1 million)

· Certified Indoor Air Quality Emergency

· Energy Conservation (costs cannot exceed $1 million)

· Projects Not Funded by Chapter 173 Grant (all, regardless of cost)

If a construction project includes only the types of work listed above, alone or in combination, the Local Plan Review Option may be selected.  For all other types of construction, plans must be submitted to the SDE for review and approval.

Local Plan Review Option—Description 
Local Plan Review Option—Requirements 

PART FIVE:  ARCHITECTURAL PLAN APPROVAL
Local Plan Review Option—Description

· In lieu of plan review by the Bureau of School Facilities, districts may have local code officials review the architectural plans for compliance with all state and federal codes.  (Be aware that local code officials are not required by law to conduct a review for the State Department of Education.)

· This option is available for limited projects:  oil tank replacements (all); roof replacements (all); projects not funded by Chapter 173 grant (all); and asbestos abatement, code violation correction, certified indoor air quality emergency, and energy conservation (provided costs do not exceed $1 million).

· This option is available only for single phase projects—phase 1 of 1.  Projects with multiple phases should be reviewed by the Bureau of School Facilities.

· Local Review requires certifications by Local Building Official, Local Fire Marshall, Local Health Official, and Local Federal 504 Official.  If any of these required certifications cannot be obtained locally, plan review and approval must be completed by the Bureau of School Facilities for such projects.  Partial local review is not an option.  

· Option is available to supplant review of plans only.  SDE written plan approval is still required prior to letting a project out for bid.

See also
Local Plan Review Option—Requirements

Bureau of School Facilities Plan Review and Approval Process

Sample Plan Approval Letter

Construction Document Guidelines for School Districts and Design Professionals
PART FIVE:  ARCHITECTURAL PLAN APPROVAL
Local Plan Review Option—Requirements

· Completed Form ED042 Request for Review of Final Plans (form side 1) and Request for State Acceptance of Local Plan Review and Approval (form side 2) must be submitted to SDE.

· Professional cost estimate must be submitted to SDE with Form ED042.

· Ineligible and Limited Eligible Costs Worksheet must be submitted to SDE with Form ED042.

· Copy of the reviewed plans and project manual must be kept on file at the local board of education until final grant payment has been made on this project.  Do not submit plans and specifications to SDE with Form ED042.

Once SDE has determined that Form ED042 and required attachments are complete and accurate, a written plan approval letter will be issued.  A PROJECT CANNOT BE LET OUT FOR BID UNTIL A PLAN APPROVAL LETTER HAS BEEN ISSUED.

SDE plan review of future projects at a facility may reveal errors, omissions, or oversights in prior reviews conducted by local officials.  In such cases, code compliance will be required for areas impacted by construction.  Call the Bureau of School Facilities with questions.

See also
Local Plan Review Option—Description

Bureau of School Facilities Plan Review and Approval Process

Sample Plan Approval Letter

Change Orders and Addenda

Construction Document Guidelines for School Districts and Design Professionals
PART FIVE:  ARCHITECTURAL PLAN APPROVAL
Bureau of School Facilities Pre-Review Evaluation Process (PREP) Meeting

· A PREP meeting is required for all projects which will undergo plan review by the Bureau of School Facilities in lieu of the Local Plan Review Option.  

· A PREP meeting should be held just prior to the start of the plan development process. PREP meetings should be scheduled as soon as the design team has been hired.  When planning, keep in mind that meetings are limited to Mondays and Tuesdays and are scheduled on a first-come, first served basis.  

· Participants at the meeting should include the chairperson of the school building committee, the chairperson of the Board of Education, the Superintendent of Schools, and a senior partner, job captain, drafter, and engineers for the architects designing the project.  Other interested parties, including local officials, are invited to attend.  (Historically, districts who attend PREP meetings without appropriate representation undergo delays in overall project deadlines and completion.)

· At the PREP meeting, a member of the Bureau of School Facilities plan review staff will review the code conformity process to be conducted by the architect and will also review the plan submission/review process to be conducted by the Bureau of School Facilities.

· The review conducted at the PREP meeting is intended to reduce to an absolute minimum any delays in the approval process and for all parties to commit to a set of submission standards.

See also Construction Document Guidelines for School Districts and Design Professionals for information about phasing and other aspects of building design. 
PART FIVE:  ARCHITECTURAL PLAN APPROVAL
Preparation of Final Plans and Specifications

· Final plans and specifications (a.k.a. contract documents) must be prepared, stamped, and signed by a registered architect or registered engineer.

· These are the actual documents that will go to bid following written plan approval by SDE.

· Change orders and addenda must also be submitted to SDE for review.  See Change Orders and Addenda.

· 
Establishing and adhering to timelines is crucial to all portions of a project.  Relative to design, it is necessary to remain on schedule in order to meet the Start of Construction Deadline for all projects.
PART FIVE:  ARCHITECTURAL PLAN APPROVAL
Bureau of School Facilities Project Completion Test (PCT) Meeting

· A PCT meeting is required for all projects which will undergo plan review by the Bureau of School Facilities (BSF) in lieu of the Local Plan Review Option.  

· A PCT meeting is held when all stages of the plan development process have been completed for a given design phase (including the code conformity and final coordination stage).

· PCT meetings should be scheduled well in advance to insure that districts get their preferred date.  Keep in mind that meetings are limited to Mondays and Tuesdays and are scheduled on a first-come, first served basis.

· Participants at the meeting should include the Superintendent of Schools or a designee (someone who attended the PREP meeting) and the architects and consultants who attended the PREP meeting. 

· Required documentation at the PCT meeting includes:  final contract documents; completed Form ED042 (Request for Review of Final Plans); completed Bureau of School Facilities Plan Review Checklists (See Construction Document Guidelines for School Districts and Design Professionals); Ineligible and Limited Eligible Costs Worksheet with column two completed; professional cost estimate; all code modifications; and approvals from other State Agencies, as applicable, including life cycle cost analysis (DPW), septic system (DEP), State Traffic Commission, and wheel chair lifts (DPS).

· It is the design professional’s responsibility to ensure that the documents submitted indicate compliance to all codes, are the final contract documents, and are prepared in accordance with the BSF Guidelines and Standards.

· At the PCT meeting, a statistical sampling is made to ensure that the Master Checklist system (given to the design professionals during the PREP meeting) has been used completely.  If it becomes evident that the design guidelines have not been followed, the plan review process will be terminated and the plans returned to the superintendent unapproved.  If the documents pass this test, they are considered complete and will be accepted for SDE review.

· Once accepted as complete, plans will be placed in a review queue, and you will be informed of the target date for SFU to complete its review.  If the Bureau of School Facilities determines that it cannot complete its review within 30 days, local review becomes an option under the 30-Day Exception. 

· A project cannot be let out for bid until SDE has issued a letter of plan approval which clearly states that the plans are approved and the project (or phase thereof) may be let out for bid.  See Sample Plan Approval Letter.

See also Construction Document Guidelines for School Districts and Design Professionals
PART FIVE:  ARCHITECTURAL PLAN APPROVAL
30-Day Exception

· Under this plan review option, districts may have local code officials review the architectural plans for compliance with all state and federal codes.  (Be aware that local code officials are not required by law to conduct a review for the State Department of Education.) 

· Local review requires certifications by Local Building Official, Local Fire Marshall, Local Health Official, and Local Federal 504 Official.

· If any of the required certifications cannot be obtained locally, plans must be submitted to SDE for review by the Bureau of School Facilities (BSF).  The project will be placed in the SDE review queue, and you will be informed of the estimated date upon which the School Facilities Unit will complete its review.

· If the 30-Day Exception applies to a project and the district prefers to have the BSF review the plans, the project is placed in the SDE review queue, and you will be informed of the estimated date upon which BSF will compete its review. 

· 30-Day Exception Option is available to supplant review of plans only.  SDE written plan approval is still required prior to letting a project out for bid.

Once SDE has determined that the requirements for local review have been satisfied and that the local officials’ documentation is complete and accurate, a written plan approval letter will be issued.  A PROJECT CANNOT BE LET OUT FOR BID UNTIL A PLAN APPROVAL LETTER HAS BEEN ISSUED.  See Sample Plan Approval Letter.
SDE plan review of future projects at a facility may reveal errors, omissions, or oversights in prior reviews conducted by local officials.  In such cases, code compliance will be required for areas impacted by construction.  Call the Bureau of School Facilities with questions.

See also 
Bureau of School Facilities Project Completion Test (PCT) Meeting

Construction Document Guidelines for School Districts and Design Professionals
PART FIVE:  ARCHITECTURAL PLAN APPROVAL
Bureau of School Facilities Plan Review and Approval Process
· The Bureau of School Facilities (BSF) review (mandated by general statute) requires that the BSF verify that the school construction documents comply with all state and federal codes and laws and report to the Commissioner of Education.  As well, the BSF reviews all construction documents for items which are not eligible for reimbursement.

· If the BSF review uncovers code citations or comments are warranted, these items are documented in a “Plan Review Record” (PRR).  All items documented in the PRR must be satisfactorily addressed using one of three options.  See PRR Issue Resolution for the options.

· Corrections and responses to the PRR must be made to the final contract documents which will be bid.  Therefore, the original drawings must be retrieved from the BSF by the design professional in order to complete the review and to obtain plan approval.

· ONCE PRR ISSUES HAVE BEEN SATISFACTORILY RESOLVED, A WRITTEN PLAN APPROVAL LETTER WILL BE ISSUED.  A PROJECT CANNOT BE LET OUT FOR BID UNTIL A PLAN APPROVAL LETTER HAS BEEN ISSUED.  See Sample Plan Approval Letter.

NOTE:  The Bureau of School Facilities review is separate from that which is required of the local officials prior to them issuing a building permit.

See also Construction Document Guidelines for School Districts and Design Professionals
PART FIVE:  ARCHITECTURAL PLAN APPROVAL
Plan Review Record (PRR) Issue Resolution
If a project review results in code citations or comments are warranted, the items can be resolved by your local code officials or by the Bureau of School Facilities (BSF) using one of the following three options:

Option One:
The local code official or the BSF possess revised construction documents from the design professional(s) which implement the corrective action exactly as described in the citation/comment as listed in the PRR, or
Option Two:
The local code official or the BSF have received a signed and approved modification from the appropriate state authority having jurisdiction.  If additional work is required for the modification, the local code official or the BSF have reviewed and approved all revisions, or
Option Three:
Other.  Before taking this option, the local code official must call the reviewer to thoroughly explain why this option will be chosen.  It is important to resolve the code issue and avoid potential delays in project approval.  If Option Three is chosen and a code interpretation is needed, the appropriate state authority having jurisdiction shall be contacted.

PART FIVE:  ARCHITECTURAL PLAN APPROVAL
Sample Plan Approval Letter







Month Day, Year

Dr. Richard Jones

Superintendent of Schools

Smithetown Public Schools

55 Fifth Street

Smithetown, XX 53684

Subject:  State Project No. XXX-XXX, Smithetown Elementary School, Phase 1 of 2

Dear Dr. Jones:

This is to inform you that we have received and reviewed all necessary materials and approve the final plans submitted on this phase of the above-mentioned project(s) as required by Section 10-292 of the Connecticut General Statutes.  Be aware that the review conducted by the State Department of Education is separate from that required by the local safety and health officials for permit.  Also, please be reminded that all addenda and change orders must be submitted to the School Facilities Unit for review and approval.

NOTE:  THIS PHASE OF THE PROJECT MAY BE LET OUT FOR BID, IN ACCORDANCE WITH THE PROVISIONS OF SECTION 10-291 AS AMENDED.

Please refer to Appendix B of the School Construction Grants Manual for a list of items for which the state does not provide reimbursement.  You are required to identify all of these items occurring within your project(s), when reporting final costs to the State Department of Education.  Your final grant amounts will be calculated in accordance with the final eligible expenditures made in connection with these projects after they are accepted as complete by your local Board of Education and all necessary submissions have been approved by the State Department of Education.

If you are in need of any assistance, please call the Bureau of School Facilities plan review staff at (860) 713-6490.






Sincerely,






David R. Wedge, Chief





Bureau of School Facilities
PART SIX:  BID SDE-APPROVED PLANS


· All contracts over $10,000 must be awarded to the lowest responsible qualified bidder after a public invitation to bid.  (Exception:  Bidding may be waived for contracts of an emergency nature only if pre-approved by the Commissioner of Education.  In such cases, the contractor or vendor may be selected by negotiation, provided no local fiscal regulations, ordinances or charter provisions conflict.)
· Effective July 1, 2007, architectural and construction management services are also required to be publicly bid and awarded to the lowest responsible qualified bidder.

· Invitation to bid must be advertised in a newspaper having circulation in the town in which construction is to take place. 

· A project cannot be let out for bid until SDE has issued a letter of plan approval which clearly states that the plans are approved and the project (or phase thereof) may be let out for bid. 

· Any and all bids may be rejected for not meeting all conditions of the specifications.  In such cases, the contractor or vendor may be selected by negotiation, provided no local fiscal regulations, ordinances or charter provisions conflict.

· The low bidder does not have to be awarded the contract if the district can document and justify that the low bidder is either not responsible or not qualified.

· Failure to publicly bid work results in grant ineligibility.

· In no case shall a specific vendor be identified or required in a bid specification.  However, bid specifications may include requirements of performance standards, product equivalency, or compatibility with existing systems or designs.

At the completion of the project, the town or board attorney will be required to certify that bidding and posting of proper bonds was done in conformance with C.G.S. 10-287(b) and C.G.S. 49-41.  Please call the Bureau of School Facilities with any questions related to bidding.

See 
SDE Policy on Allowances

Use of State Contracts by Local Districts

Architect and Construction Management Services Bidding
USE OF STATE CONTRACTS BY LOCAL DISTRICTS


Section 10-292(a), (c), and (d) of the Connecticut General Statutes permit the use of state contracts by school districts in lieu of bidding out the work or commodity separately.

Only after SDE plan approval, districts may access the state contracts for purposes of going forward with their project.

TO ACCESS THE STATE CONTRACTS:

A. Use the Internet and go to http://www.das.state.ct.us.

B. Click on “Procurement”
C. Click “State Contracting Portal”

D. Select the Commodity category desired from the drop-down menu. (Commodity categories are established by DAS.)

E. Click the Contract Number.

F. Print the first page or two of the contract which provides the vendor name, effective term of the contract, and state contract award number.

For School Construction record retention, keep the printouts obtained using Step F.
PART SIX:  ISSUE CONTRACTS AND

NOTIFY SDE OF START OF CONSTRUCTION
· Districts are required to report the “date of beginning of construction” for each project.  For grant purposes, this date is more commonly referred to as the Start of Construction Date.

· This date is defined in the law as “the date on which the general construction contract or the first phase thereof, purchase agreement or leasing agreement is signed by the authorized agent of the town or regional school district.”

· For Priority List Projects, construction must begin within two years of state legislative authorization.  This is known as the Start of Construction Deadline.

· Non-Priority List Projects are also required to begin construction within two fiscal years after the year of grant commitment.
· The Start of Construction Date needs to be electronically submitted via the School Construction Grant Management System (SCGMS).  A “Start of Construction Date” button can be accessed on the Project Menu of SCGMS.
THERE CAN BE NO GRANT PAYMENTS FOR CONSTRUCTION EXPENDITURES UNTIL THIS DATE HAS BEEN REPORTED TO THE BUREAU OF SCHOOL FACILITIES.

PART SIX:  ISSUE CONTRACTS AND

NOTIFY SDE OF START OF CONSTRUCTION
Start Of Construction Deadline

For Priority List Projects, the general construction contract (or first phase thereof) must be signed within two years after the effective date of the act of the General Assembly authorizing the Commissioner to enter into a grant commitment.  (This date is identified in the grant commitment letter for each Priority List Project.)  Failure to meet this deadline will result in a lapse of grant authorization for the project. 

Since June 2004, the Department’s policy is to not permit extensions to the start of construction deadline except for extraordinary circumstances.
For Non-Priority List Projects, the general construction contract (or first phase thereof) must be signed with two fiscal years after the fiscal year of the grant commitment.

PART SIX:  REQUEST STATE SHARE OF 

ELIGIBLE CONSTRUCTION COSTS
Prior to submitting a progress payment request for eligible construction costs, the following criteria must be in place:

	FOR ALL PROJECTS:
	ONLY IF APPLICABLE:

	Completed Application Package
	Form ED053

	Grant Commitment
	SDE Site Inspection and Approval

	SDE Architectural Plan Approval
	Two Independent Appraisals

	Start of Construction Date
	Actual Purchase Documentation

	
	


The mechanism by which districts request the State Share is Form ED046 Request for School Construction Progress Payments. 

REIMBURSEMENT IS LIMITED TO CONSTRUCTION COSTS ASSOCIATED WITH THE PHASE OR PHASES FOR WHICH SDE ARCHITECTURAL PLAN APPROVAL HAS BEEN GRANTED.

Note:
Five percent of all grant payments for a project will be withheld until 

· the project is accepted as complete by the district,

· final costs and all other final documentation is submitted to SDE, 

· the audit is completed, and

· the final audited grant amount determined.  

See also
Form ED046

The Progress Payment Cycle
PART SEVEN:  THE PROGRESS PAYMENT CYCLE


· Project costs should be reviewed with each Progress Payment request and updated or revised as appropriate by the district.

· Projected expenditures should be updated for each payment request.  (This includes revised data for Ineligible and Limited Eligible Costs.)  

· Forecast cash needs at least 60 days in advance when requesting Progress Payments.

· Payment requests may be submitted no sooner than every other month. 

· Timing of payment requests is dependent upon local cash needs for a 60-day period of time.  Districts may elect to wait on design fees and combine this request with the first request for construction money (after plan approval).

· For projects costing less than $5 million, once actual construction is underway and prior to finalization, districts must submit to SDE a copy of the Contractor’s Application and Certificate for Payment (AIA Doc. G702).  Districts must also provide the Continuation Sheets which provide cost detail for the project.  If the Contractor’s Application and Certificate for Payment was not used, submit a copy of the job estimates/invoices.  (For projects costing $5 million or more, this information must be maintained at the local level and made available to SDE at the time of on-site audit for the project.)  See Audit of School Construction Projects.

· 
Five percent of the State Share will be withheld from each payment request until the project audit is complete. 

· Change orders and addenda must be submitted to SDE as they occur.  Do not compile large amounts of change orders and submit them together at the end of the project.

See 
Form ED046

Change Orders and Addenda
PART EIGHT:  PROJECT COMPLETION AND AUDIT

Required Final Submissions

· When all construction is completed (including punch list items), and all bills and contractors have been paid, the project must be accepted as complete by the local Board of Education.

· Once the project has been accepted as complete, districts are required to submit:

· Form ED046 - Districts need to submit a “final” payment request reflecting cumulative expenditures equal to final project costs.  This final payment request may or may not result in an actual grant payment because SDE will release only 95% of the state school construction grant prior to audit. 

· ED049F Final Grant Application for a School Building Project

· 
Ineligible and Limited Eligible Costs Worksheet with Final Column Completed
IF A DISTRICT FAILS TO SUBMIT FORM ED049F WITHIN ONE YEAR FROM THE DATE THE LOCAL BOARD OF EDUCATION ACCEPTS THE PROJECT AS COMPLETE, THE COMMISSIONER MAY WITHHOLD TEN PERCENT OF THE STATE REIMBURSEMENT FOR THE PROJECT.

PART EIGHT:  PROJECT COMPLETION AND AUDIT

The Final Calculation Process

· After receipt of final project documentation, SDE performs a final project file review prior to releasing the project for final grant calculation and payment computation. 

· After final grant calculation, projects are forwarded to the State Department of Education Office of Internal Audit for review.  See Audit of School Construction Projects.

· If the audit results in no adjustments to the project, the final 5 percent is released.

· If the audit results in adjustments, a recalculation is performed.  Adjusted payment is made OR a refund is requested in accordance with the grant recalculation.

Except for projects solely for the correction of code violations or for certified indoor air quality emergency projects, audited grant calculation for all Progress Payment projects will include computation of an amortization schedule for the State Share.  The district will be subject to grant repayment provisions if they abandon, sell, lease, demolish or otherwise redirect the use of the school building project to a nonpublic school use during the amortization period.

See 
Form ED046

Amortization Schedule and Grant Repayment
PART EIGHT:  PROJECT COMPLETION AND AUDIT

Amortization Schedule and Grant Repayment

· Except for projects solely for the correction of code violations, audited grant calculation for all Progress Payment projects will include computation of an amortization schedule for the State Share.

· For projects with costs equal to or greater than $2 million, the state grant for the school building project will be amortized on a straight-line basis over a 20-year period.

· For projects with costs less than $2 million, the state grant for the school building project will be amortized on a straight-line basis over a 10-year period.

· Any town or regional school district which abandons, sells, leases, demolishes or otherwise redirects the use of such a school building project to a non-public use during the amortization period shall refund to the state the unamortized balance of the state grant remaining s of the date the abandonment, sale, lease, demolition, or redirection occurs.

· The amortization period shall begin on the date the project was accepted as complete by the local Board of Education.

· A request for forgiveness of such refund may be submitted if the building is redirected for public use.  Requests of this nature will be included as an addendum to the annual school construction Priority List and must be approved by the General Assembly.

PART EIGHT:  PROJECT COMPLETION AND AUDIT

Audit of School Construction Projects

SDE has six months from receipt of final acceptable project documentation to complete its audit of a Progress Payment project.  If the audit cannot be performed within this period, the applicant may have an independent audit performed and include the cost of such audit in the eligible project costs.

For on-site audits, the Office of Internal Audit will contact a district to coordinate and schedule the review.  The documentation listed below must be readily available for SDE examination.  (It is not necessary to make copies of this information.)

· Project ledger, general ledger, cash disbursements journal, or other schedule of project expenditures 

· All contracts including, but not limited to, construction, architect, engineering, furniture, equipment, etc.

· All project change orders

· Competitive bid summaries for all contracts in excess of $10,000

· All original paid invoices including, but not limited to, contractors’ applications for payment (i.e., contractors’ final invoices) and any other payment requests

· Schedule or summary of ineligible and/or limited eligible items and associated costs

· Documentation (e.g., architectural plans or assessor’s card) for the building square footage
· Documentation for the highest eight-year projected enrollment for projects other than roof replacements, code violations and Board of Education facility projects

· Audited financial statements of the town for the fiscal years in which project expenditures were incurred

· Project Manual/Bid Specifications 

· Additional information as requested at the time of audit

STATE PROJECT NUMBER ABBREVIATIONS

 

Sample of a State Project Number

	Town Code No.
	Project Number
	Project Type Abbreviation

	064
	102
	EA/RR

	
	
	

	Hartford
	102nd Project Undertaken
	Extension, Alteration, & Roof Replacement


Project Type Abbreviations

Abbreviation
Type of Project

A
Alteration

A/TCH
Technology Infrastructure

CV
Code Violation

E
Extension

EA
Extension and Alteration

EC
Energy Conservation

HV
Health Violation (Asbestos Abatement)

IAQ
Certified Indoor Air Quality Emergency
N
New School

OT
Oil Tank

PF
Purchase of a Building 

PS
Site Acquisition
RE
Relocatable Classrooms (Portables, Modulars)

RNV
SDE-Approved Renovation

RR
Roof Replacement

VE
Vocational Agriculture Equipment

Facility Type Designations

For facilities which are designated other than regular education, the project type abbreviation will be preceded by a designation for the type of facility.  Facility types include the following.

Designation
Type of Facility

BE
Board of Education Central Administration

IC
Interdistrict Cooperative School

MAG
Approved Interdistrict Magnet School

SP
Approved Regional Special Education Facility

VA
Approved Regional Vocational Agriculture Center

For questions regarding state project numbers, please contact the Bureau of School Facilities.
CHANGES IN PROJECT COST and/or SCOPE


Section 10-283(a)(2) of the Connecticut General Statutes states, in part, that the SDE shall submit to the General Assembly “a schedule of authorized projects which have changed in scope or cost to a degree determined by the commissioner.”  Changes which would require reauthorization are listed below.

· Significant change to the educational specifications as defined in Section 10-287c-1(5) of the Regulations of Connecticut State Agencies including:

· change in the project type (e.g. from extension to new construction or from energy conservation to roof replacement), 

· change to the programmatic component of the project which alters the learning activities to be conducted in the project, and

· addition of a type of construction that would itself require authorization of the General Assembly (e.g. adding a roof replacement to an interior alteration project).

· Change to the category placement of the project pursuant to Section 10-283 of the Connecticut General Statutes (e.g. changing the proposed use of a building addition from classrooms to central administration offices).

· Change in the location where the project was to be undertaken (i.e. a project authorized at one school cannot be transferred to another school.  This does not include construction of a new facility for which the actual site location may change prior to construction).

· Significant change to the grade range of the project (e.g. changing a project authorized as a K-6 facility to a facility for grades 9-12.  Changing a new facility from K-4 to K-6 would not be considered significant for purposes of this policy.)

· In projects where a cost increase occurs, SDE will evaluate the following in determining the need for reauthorization:

· expansion in scope of the original project and the reasons therefore.

· unexpected changes to data used in the original determination of project cost.

· general cost increases prevalent in the building industry during the project period.

· accuracy of original versus current cost estimates for the same work.

· For projects eligible for 100% state funding, incidental cost increases not to exceed 2.5 percent of the authorized project costs will not require supplemental authorization by the Governor and legislature.

In general, projects that have changed in character must be resubmitted for reauthorization.  Projects that are essentially the same but have increased in cost due to minor changes in scope, unanticipated code implications or general industry cost increases may not require reauthorization.

TO REPORT CHANGES TO A PROJECT, USE FORM ED049R AND PROVIDE A WRITTEN EXPLANATION FOR ALL REVISIONS.

Districts must notify SDE of changes to a project which may require reauthorization.  This must be as soon as possible, and NO LATER THAN NOVEMBER 1st if the project is to be included on the Priority List for submission to the General Assembly by December 15.  

PROJECT DISAPPROVAL AND NULLIFICATION OF ELIGIBILITY


A project will be disapproved and deemed ineligible for reimbursement if any of the following apply:

· It does not comply with the requirements of the state fire marshal or the department of public health and addiction services

· A life-cycle cost analysis approved by the commissioner of public works pursuant to C.G.S. Section 16a-38 is not provided at or prior to final plan review (for projects that require such an analysis)

· It does not comply with the provisions of C.G.S. Sections 10-290d and 10-291.

· It does not meet the standards or school building priorities established by the state board of education

· For all projects , the applicant fails to meet its Start of Construction Deadline
GENERAL CONTRACTOR VS. CONSTRUCTION MANAGER

COMPETITIVE BIDDING REQUIREMENTS

With regard to general contractors and construction managers, SDE has been advised of the following:

General Contractor

A general contractor contracts with an owner for a certain price to build a school building project.  He is responsible for completion of the project in accordance with the plans and specifications.  The general contractor directly contracts with subcontractors and material men in his own name, coordinates their services, and pays them directly.  

If a general contractor is used, only the contract between the general contractor and the town must be publicly bid in accordance with C.G.S. 10-287(b) because all subcontracts are with the general contractor, who, in turn, must furnish a bond under Section 49-41 of the General Statutes.

Construction Manager

A construction manager provides professional services to a project owner including scheduling and coordinating the work and assisting the owner in arranging for the contractors and architects who will actually do the work.  He coordinates the efforts of others from the start of the project to the final delivery of the completed facility.  The construction manager may be hired through competitive bidding or otherwise.  He falls within the concept of “consultant” as defined by Section 4b-55(b) and is thereby expressly exempt from the bond requirements of Section 49-41.  When a construction manager is used, the various construction contracts run between the project owner, i.e., the school district, and the individual contractors, who would ordinarily be subcontractors if a general contractor had been engaged.  The construction manager performs only the management and coordination functions of a general contractor. 

If a construction manager is used, all contracts are directly with the town, and each contract must be bid in accordance with C.G.S. 10-287(b).  In such a case, each contractor must furnish a bond if his contract falls within the monetary limits of Section 49-41 of the General Statutes.

Questions regarding whether a firm is classified as a general contractor or a construction manager should be directed to your legal counsel.  Because Section 10-287c-19(b) of the Regulations requires grant applicants to certify that they have met all legislative and regulatory requirements in the award of contracts, an attorney should be consulted to insure compliance with applicable bond and bid laws. 

See also Bid SDE-Approved Plans
SDE POLICY ON ALLOWANCES


· Although bid allowances may be used as a tool for budgeting and planning, they are not to be included in bid specifications or contract awards.

· Any item(s) for which an allowance has been budgeted must be separately bid and awarded a separate contract at the time the specific items and quantities are known.

CHANGE ORDERS AND ADDENDA

· Change Orders and Addenda provide an orderly procedure to amend construction contracts but should be used only for unforeseen or emergency conditions and should not total more than ten percent of the original contract sum.

· Overhead and profit percentages for both general contractor and subcontractor shall be identified at the bidding stage in the Proposal Form or in the Contract under Special Provisions.

· The total mark-up on subcontractors should be limited by contractual language.

· Form ED042CO Notice of Change Order, with original signatures, must be submitted for all change orders.  Sufficient backup documentation is required for SDE to determine code compliance as well as grant eligibility.  (Include contract documents, such as SK’s, where applicable.)

· For state submission, change orders and addenda must be numbered sequentially for each project.  (For local purposes, numbering systems are discretionary.)

· Submit change orders as they occur.  Do not compile large amounts of change orders and submit them together at the end of the project.

· Effective June 6, 1995, there is no requirement for Change Orders to be publicly bid.
· Unapproved, unreviewed change orders are ineligible for grant payments.
NEW

For projects authorized by the General Assembly after July 1, 2006 with project costs greater than $10,000,000, grant reimbursement for change orders may be limited.  Eligible costs from change orders exceeding 5 percent of authorized costs will only be reimbursed at one-half the project reimbursement rate.
ARCHITECT AND CONSTRUCTION MANAGEMENT SERVICES

COMPETITIVE BIDDING REQUIREMENTS

NEW
· Effective July 1, 2007, architectural and construction management services are required to be publicly bid and awarded to the lowest responsible qualified bidder.

· Exceptions to the publicly bid requirement are:

· Where the town or regional school district is using a state contract

· Where the contract is less than $10,000

Circular Letter C-6 Issued October 1, 2007 by the Commissioner provides guidance regarding these new bidding requirements and includes Frequently Asked Questions.
Dave Wedge, Chief, Bureau of School Facilities may be contacted at (860) 713-6467 for additional questions.
See Circular Letter C-6 (October 1, 2007)
INDEX

Allowances—SDE Policy
Amortization Schedule and Grant Repayment

Application Submission Deadlines

Appointment of a Building Committee

Architectural Plan Approval

Architect and Construction Management Services Bidding

Audit

Bid SDE-Approved Plans

Building and/or Site Acquisition Costs—Request State Share

Change Orders and Addenda

Changes in Project Cost and/or Scope

Code Compliance—SDE Policy

Complete Application Package

Construction Manager

Cost Estimating Worksheet—Discussion

Design Costs—Request State Share

Educational Specifications

Eligible Construction Costs—Request State Share

Final Calculation Process

Form ED046 Request for Progress Payments—Discussion
Form ED049 Grant Application—Discussion

Full-Day Kindergarten

General Contractor

Grade Range

Grant Application Submission Check-List—Discussion

Grant Commitment

Highest 8-Year Projected Enrollment

Interdistrict Magnets

Key Grantee Responsibilities (Summary)

Lighthouse Schools

Local Authorization of Project Funding—Discussion

Local Authorization of Project Funding—Notifying SDE

Local Board of Education Approval of Educational Specifications

Local Funding Authorization Deadline

Local Legislative Authorizations

Local Legislative Body

Local Needs Assessment

Local Plan Review Option—Description

Local Plan Review Option—Eligible Projects Identified

Local Plan Review Option—Requirements

Local Share

Local Use of State Contracts

Other Sources of Funding

Out-of-District Students (CHOICE)

Plan Review Record (PRR) Issue Resolution

Preparation of Final Plans and Specifications

Pre-Review Evaluation Process (PREP) Meeting

Priority Category Placement

Progress Payment Cycle

Progress Payment Requirements Prior to Reimbursement

Progress Payment Sample Timelines

Progress Payments—General Discussion

Project Completion Test (PCT) Meeting

Project Disapproval and Nullification of Eligibility

Purchased Building Inspection and Approval for Use

Reduced-Class Size

Regional Special Education Center

Regional Vocational Agriculture Center

Regional Vocational Agriculture Equipment

Required Final Grant Submissions

Sample Plan Approval Letter

School Buildings & Duties of the Board of Education

School Construction Reimbursement Percentages

School Readiness

SFU Plan Review and Approval Process

Site Inspection and Approval for Use

Space Standards Worksheet—Discussion

Special Program Approvals for Reimbursement Rate Bonuses

Square Footage

Start of Construction Deadline

Start of Construction—Notifying SDE

State Project Number Abbreviations

30-Day Exception

Types of Non-Priority List Projects

Types of Priority List Projects

Typical Dates for Priority List Projects

Vocational Agriculture Equipment List

� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�





� HYPERLINK  \l "top" ��Main Directory�








