## Air
Predictable Regulation (Goal 15) Project Tracking
Division | Bureau of Air Management
Beyond Public Notice
Anticipated Regulatory Adoption/Amendment |  | Point of Contact | LRRC Hearing Date | Status
Definition of emergency/emergency engine |  | Merrily Gere | 2019-09-24 | Approved with technical corrections. Effective 10/08/2019.
Adopt a Permit by Rule to replace the General Permit to Limit Potential to Emit Permits (new RCSA sections 22a-174-33a and -33b) |  | Raquel Herrera | 7/28/2020; 09/22/2020 | Approved with technical corrections. Effective 09/24/2020.
|  |  | 7/28/2020; 09/22/2020 | Approved with technical corrections
New Source Review permitting Program, amends 22a-174-1-3 |  | Paula Gomez | 08/25/2020; 10/27/2020 | Approved with technical corrections. Effective 11/18/2020.
Exemptions from New Source Review permitting for certain small incinerators |  | Raquel Herrera | 1/26/2021; 02/23/2021 | Approved with technical corrections. Effective 03/05/2021.
Pre-Public Notice
Regulatory Concepts under Consideration |  | Point of Contact | Goal for Public Notice | Status
Update of source monitoring requirements |  | Paula Gomez | Summer 2021 | Preparing submission to OPM and Governor's Office
Modernization of radiation regulations |  | Raquel Herrera | Fall 2021 | Internal agency review of drafts ongoing
Revision of definition of "severe nonattainment area for ozone" |  | Merrily Gere | Fall 2021 | Internal agency review of impacts ongoing

## WPLR
Predictable Regulation (Goal 15) Project Tracking
Division | Bureau of Water Protection & Land Reuse
Beyond Public Notice
Anticipated Regulatory Adoption/Amendment |  | Point of Contact | LRRCHearing Date | Status
Remediation Standard Regulations 22a-133k1-3 |  | Kevin Neary | Winter 2020 | Adopted Effective 02/16/21
Environmental Use Regulations |  | Jade Barber | Winter 2020 | Adopted Effective 02/16/21
Pre-Public Notice
Regulatory Concepts under Consideration |  | Point of Contact | Goal for Public Notice | Status
Water Quality Regs: 22a-426-1 through -9 |  | Water Planning & Management Division | Winter 2021 | Internal agency review ongoing
Release-based Regs: Public Act No. 20-9 Sept. Special Session, Section 19 |  | Remediation Division | Summer 2022 | Stakeholder process to set vision for regulations beginning

## BETP
Predictable Regulation (Goal 15) Project Tracking
Division | Bureau of Energy & Technology Policy
Beyond Public Notice
Anticipated Regulatory Adoption/Amendment |  | Point of Contact | LRRC Hearing Date | Status
Pre-Public Notice
Regulatory Concepts under Consideration |  | Point of Contact | Goal for Public Notice | Status
New HFC Regulations |  | Bureau of Energy & Technology Policy | Summer 2020 | Informal review OTG & OPM
Pursuant to PA 19-35 -Update to the High Performance Building Regulations (CGS §16a-38k) |  | Office of Demand | Spring 2020 | Internal agency review ongoing

## Natural Resources
Predictable Regulation (Goal 15) Project Tracking
Division | Bureau of Natural Resources
Beyond Public Notice
Anticipated Regulatory Adoption/Amendment |  | Point of Contact | LRRC Hearing Date | Status
State-controlled Wildlife Management Areas 23-5c-1 et seq. and New 26-55-7. |  | Wildlife Division, Robin Blum | 2020-01-28 | Approved by LRRC; filed with the SOS; Effective 02/04/20
Update bow & arrow fishing regs and makes clarifying change to creel limit definition Section 26-112-43. |  | Fisheries Division, Pete Aarrestad | 2021-06-22 | Submitted to LRRC for review (6/22 meeting)
Remove Black Pond (Woodstock) and Mohawk Pond from the list of lakes & ponds with a closed season from the last day of February to Opening Day. To conform with other proposed changes (see section 26-112-46(d.) |  | Fisheries Division, Pete Aarrestad | 2021-06-22 | Submitted to LRRC for review (6/22 meeting)
Revision to: 1) Carp regs as per legislative intent (to provide additional opportunities for bow fishers).Section 26-112-45 2) add Tiger Muskie with Northern Pike for methods and limits (creel, length), 3) add Crescent Lake to the list of lakes & ponds with a 3 catfish per day creel limit. |  | Fisheries Division, Pete Aarrestad | 2021-06-22 | Submitted to LRRC for review (6/22 meeting)
Update and make clarfications to Special Management Areas Section 26-112-46 . 1) Add Black Pond (Woodstock) and Mohawk Pond to the list of Trout Management Lakes, 2) establishes “thermal” refuges on highland Lake, 3) Under subsection (h). Amends designation from Atlantic Salmon Broodstock Areas to “Atlantic Salmon Management Areas” better reflect current management goals, 4) revises subsection to provide additional opportunities for bow fishers, 5) provides exception to allow temporary retention of carp for measuring. |  | Fisheries Division, Pete Aarrestad | 2021-06-22 | Submitted to LRRC for review (6/22 meeting)
Repeal Sections 26-112-24 (Closed seasons) and 26-112-47 (State-controlled fishing areas). Sec. 26-112-24: Eliminates outdated provisions concerning a statewide closed season. Sec. 26-112-47: Eliminates outdated provisions concerning the now defunct Quinebaug Valley Trout Hatchery Public fishing Ponds. |  | Fisheries Division, Pete Aarrestad | 2021-06-22 | Submitted to LRRC for review (6/22 meeting)
Pre-Public Notice
Regulatory Concepts under Consideration |  | Point of Contact | Goal for Public Notice | Status
Work cooperatively with NY to adopt regulations for the whelk fishery in Long Island Sound. |  | Fisheries Division, Justin Davis | Third Quarter 2021 | Internal agency review ongoing
Per direction from Atlantic States Marine Fisheries Commission, adopt new regulations for horseshoe crab fishery to reduce harvest. |  | Fisheries Division, Justin Davis | Third Quarter 2021 | Internal agency review ongoing
New regulations establishing a fee to reinstate an expired forest practitioner certification (23-65h-1), and require use of BMPs to protect water quality during timber harvests 23-65j-1. |  | Forestry Division, Chris Martin | Summer 2021 | Requires adoption of proposed amendments to the Forest Practices Act
Endangered species list- revise list of endangered and threatened species, and species of special concern. |  | Wildlife Division, Robin Blum | Fall 2021 | Internal agency review ongoing
Update regulations concerning mooring of boats at state boat access areas Section 26-112-39 |  | Fisheries Division, Pete Aarrestad | First Quarter 2022 | Development, iInternal review ongoing | Updates Fisheries reg to conform with Boating regs.
Pursuant to P.A. 19-28, amend cooperative multi-state possession/landing program for the Winter 1 commercial summer flounder fishery 26-159a-29 to include black sea bass. |  | Fisheries Division, Justin Davis | Fourth Quarter 2021 | Internal agency review ongoing

## BMMCA
Predictable Regulation (Goal 15) Project Tracking
Division | Bureau of Materials Management & Compliance Assurance
Beyond Public Notice
Anticipated Regulatory Adoption/Amendment |  | Point of Contact | LRRC Hearing Date | Status
Pre-Public Notice
Regulatory Concepts under Consideration |  | Point of Contact | Goal for Public Notice | Status
Underground Storage Tanks Regulation update - minor revisions to the UST regs for consistency with the 215 federal regulations |  | Emergency Response and Spill Prevention Division | Winter 2021 | need EPA review; internal agency review ongoing
Hazardous Waste regulation update - update CT haz waste regulations |  | Engineering & Enforcement Division | Fall 2021 | Need EPA review; internal agency review ongoing
Release Reporting Regulations |  | Emergency Response and Spill Prevention Division | late Fall 2020 | Open for public comments. Public comment ends May 10, 2021. Public hearing via Zoom link scheduled for April 27, 2021 at 1:30.