## Instructions
INSTRUCTIONS FOR CALENDAR DAY CHART
1) | Start with Key Dates Tab
- Enter information into blue highlighted cells
- Enter operations, quantity and rates
-The number of weeks required to perform each operation is calculated from the quantity and production rates
2) | 1 yr Calendar , 2yr Calendar or 3 yr Calendar Tab
- Round up the number of construction seasons to determine which calendar tab to use (i.e. for 1.5 construction season project, choose 2 yr calendar)
- FDP, DCD, ADV, Permit Restriction dates, Operations, Number of Weeks required for each operation are referenced from the Key Dates tab to the calendar chart.
- Refer to the "pop-up comments" for guidance to enter dates
- Enter date for Start of Construction at the top
- Enter X for each week there will be Utility Work performed by the utility companies.
- Enter X for each week it takes for a given operation. If the number X's entered doesn't match the Number of Weeks (Column C), the row will be highlighted in red
- Weeks in winter shutdown are in orange (December 1 to March 31). Do not enter X's for these weeks if there no work during winter shutdown
- At the bottom of the page, calendar days are automatically filled in based on the entered dates for the start and end of construction
If using 1yr tab, enter End of Construction date to calculate the calendar days
If using 2yr or 3yr tabs, enter Start and End dates for each season to calculate the calendar days.
- The calendar days shouldn't exceed the number of days between April 1 and November 30 (244 days) per season if there is no work occuring during winter shutdown.
For questions, please contact:
| Ahsan Saghir |  | ahsan.saghir@ct.gov | Tel.# 860-594-2076
| Meredith Andrews |  | meredith.andrews@ct.gov | Tel.# 860-594-3224
Last Revised:
1. Added New Tabs For Work During Winter Shut Down - 2/10/2017
2. Added extra day in end date equation in 2 yr calendar & 3 yr calendar equations - 01/04/2018
3. Revised Milestone dates - 05/24/2018
4. Work Classfication - 03/18/2019

## key dates
PROJECT NO. | 000-000
FED AID PROJ. NO. | 000-000
PROJECT TITLE | Intersection Improvements
CITY/TOWN | City/Town
PROJECT ENGINEER'S NAME (Designer) | Name
FINAL DESIGN PLANS (FDP) | 2016-09-07 | No. of Days | No. of Weeks
DESIGN COMPLETION DATE (DCD) | 2016-10-19 | 42 | 6
DATE OF ADVERTISEMENT (ADV) | 2016-11-16 | 28 | 4
DATE OF LETTING | 2016-12-14 | 28 | 4
DATE OF AWARD(Fri.) | 2017-02-10 | 58 | 8.2857
NOTICE TO PROCEED (Mon.) | 2017-03-27 | 45 | 6.4286
PERMIT TIME RESTRICTIONS | N/A | N/A | #VALUE!
UTILITY WORK YES / NO | YES |  | 10
OPERATION | QUANTITY | RATE OF PRODUCTION (Amount per week) | No. of Weeks
MOBILIZATION |  | 1 | 1
CLEAR AND GRUB |  | 1 | 1
EARTH EXCAVATION | 2535 | 600 | 5
DRAINAGE STRUCTURES | 19 | 10 | 2
STORM PIPE | 1040 | 400 | 3
WATERMAIN |  | 500 | 0
FORMATION OF SUBGRADE | 1670 | 5000 | 2
SUBBASE/PROCESSED AGGREGATE BASE | 557 | 1000 | 2
MILLING | 7641 | 7750 | 1
HMA S1 | 288 | 1450 | 2
HMA S0.5 | 1263 | 1800 | 2
SIDEWALK |  | 1000 | 0
TRAFFIC SIGNAL |  | 0.5 | 0
TEMP PAVE MARK FOR WINTER |  | 1 | 0
TRAFFIC SIGNS/PAVE MARKINGS | 2 | 1 | 2
TOP SOIL/TURF ESTABLISHMENT | 3535 | 5000 | 1
PLANTINGS |  | 1 | 0
UTILITY RELOCATIONS |  | 1 | 0
MATERIAL PROCUREMENT/FABRICATION |  | 1 | 0
HANDLING OF CONTAMINATED MATERIAL |  | 1 | 0
BORROW |  | 1 | 0
ROCK EX | 4 | 1 | 4
TPCBC | 1 | 1 | 1
FILL |  | 1 | 0
MEMBRANE |  | 1 | 0
CURBING | 2 | 1 | 2
GUIDERAIL |  | 1 | 0
RIP-RAP |  | 1 | 0
TEMPORARY SHEETING |  | 1 | 0
COFFERDAM AND DEWATERING |  | 1 | 0
STRUCTURE EXCAVATION |  | 1 | 0
PILES/TEST PILES |  | 1 | 0
TEMPORARY STRUCTURES |  | 1 | 0
REMOVAL OF SUPERSTRUCTURE |  | 1 | 0
SUBSTRUCTURE |  | 1 | 0
SUPERSTRUCTURE |  | 1 | 0
RETAINING WALLS |  | 1 | 0
BEARING PADS |  | 1 | 0
STRUCTURAL STEEL FABRICATION |  | 1 | 0
STRUCTURAL STEEL DELIVERY |  | 1 | 0
PAINTING |  | 1 | 0
ILLUMINATION - BY LOCATION |  | 1 | 0
SIGNALIZATION - BY INTERSECTION |  | 1 | 0
TURF ESTABLISHMENT |  | 1 | 0
FACILITY - DIVISION 2 - EXISTING CONDITIONS |  | 1 | 0
FACILITY - DIVISION 3 - CONCRETE |  | 1 | 0
FACILITY - DIVISION 4 - MASONRY |  | 1 | 0
FACILITY - DIVISION 5 - METALS |  | 1 | 0
FACILITY - DIVISION 6 - WOOD, PLASTIC, AND COMPOSITES |  | 1 | 0
FACILITY - DIVISION 7 - THERMAL AND MOISTURE PROTECTION |  | 1 | 0
FACILITY - DIVISION 8 - OPENINGS |  | 1 | 0
FACILITY - DIVISION 9 - FINISHES |  | 1 | 0
FACILITY - DIVISION 10 - SPECIALTIES |  | 1 | 0
FACILITY - DIVISION 11 - EQUIPMENT |  | 1 | 0
FACILITY - DIVISION 12 - FURNISHINGS |  | 1 | 0
FACILITY - DIVISION 13 - SPECIAL CONSTRUCTION |  | 1 | 0
FACILITY - DIVISION 14 - CONVEYING EQUIPMENT |  | 1 | 0
FACILITY - DIVISION 21 - FIRE SUPPRESSION |  | 1 | 0
FACILITY - DIVISION 22 - PLUMBING |  | 1 | 0
FACILITY - DIVISION 23 - HEATING, VENTILATING, AND AIR CONDITIONING |  | 1 | 0
FACILITY - DIVISION 26 - ELECTRICAL |  | 1 | 0
FACILITY - DIVISION 27 - COMMUNICATIONS |  | 1 | 0
FACILITY - DIVISION 28 - ELECTRONIC SAFETY AND SECURITY |  | 1 | 0
FACILITY - DIVISION 31 - EARTHWORK |  | 1 | 0
PROJECT CLOSEOUT | 1 | 1 | 1
Note on B12: Please indicate the starting date of the restriction If none, say "N/A"
Note on C12: Please indicate the end date of the restriction If none, say "N/A"
Note on D13: Based on Utility Work Schedules (UWS) from the utility companies
Note on C16: The rates of production shown are for example only. Use the following link for updated rates: pw:\\ctdot.projectwiseonline.com:CTDOT\Documents\04.00 - Engineering Libraries\Construction\Production Rates\
Note on D16: The number of weeks required for each operation is calculated from the quantity and rate of production entered.

## 1 yr calendar
CALENDAR DAY CHART FOR DETERMINING NUMBER OF CONTRACT DAYS
State Project No. 000-000 / FAP No. 000-000
Intersection Improvements
City / Town
WORK CLASSIFICATION:
| Prepared By (Designer): | Name | [15 empty] | Date: | [11 empty] | Concurred By: | [18 empty] | Date:
|  | Project Engineer | [28 empty] | (District Construction Supervising Engineer)
| Construction Season |  | 2017-03-27 | [39 empty] | 2018-01-01
WORK BEGINNING DATE (STARTING MONDAYS) | [55 empty] | WEEKS ENTERED | time axis 2017-03-27 to 2018-03-26
OPERATION | NUMBER OF WEEKS |  | 2017-03-27: NOTICE TO PROCEED
FDP | 2016-09-07
DCD | 2016-10-19
DATE OF ADV (Wed) | 2016-11-16
DATE OF LETTING (Wed) | 2016-12-14
DATE OF AWARD (Fri) | 2017-02-10
NOTICE TO PROCEED (Mon.) | 2017-03-27
START OF CONSTRUCTION | 2017-04-03
PERMIT RESTRICTIONS |  | N/A to N/A | [53 empty] | 0
UTILITY WORK |  | 10 | [53 empty] | 10 | bar: 2017-05-08 to 2017-07-10
MOBILIZATION |  | 1 | [53 empty] | 1 | bar: 2017-04-17
CLEAR AND GRUB |  | 1 | [53 empty] | 1 | bar: 2017-04-24
EARTH EXCAVATION |  | 5 | [53 empty] | 5 | bar: 2017-05-01; 2017-07-10 to 2017-07-17; 2017-09-18 to 2017-09-25
DRAINAGE STRUCTURES |  | 2 | [53 empty] | 2 | bar: 2017-08-07; 2017-10-16
STORM PIPE |  | 3 | [53 empty] | 3 | bar: 2017-08-07; 2017-10-16 to 2017-10-23
WATERMAIN |  | 0 | [53 empty] | 0
FORMATION OF SUBGRADE |  | 2 | [53 empty] | 2 | bar: 2017-08-14; 2017-10-30
SUBBASE/PROCESSED AGGREGATE BASE |  | 2 | [53 empty] | 2 | bar: 2017-08-14; 2017-10-30
MILLING |  | 1 | [53 empty] | 1 | bar: 2017-08-21
HMA S1 |  | 2 | [53 empty] | 2 | bar: 2017-08-28; 2017-11-13
HMA S0.5 |  | 2 | [53 empty] | 2 | bar: 2017-08-28; 2017-11-13
SIDEWALK |  | 0 | [53 empty] | 0
TRAFFIC SIGNAL |  | 0 | [53 empty] | 0
TEMP PAVE MARK FOR WINTER |  | 0 | [53 empty] | 0
TRAFFIC SIGNS/PAVE MARKINGS |  | 2 | [53 empty] | 2 | bar: 2017-09-04; 2017-11-20
TOP SOIL/TURF ESTABLISHMENT |  | 1 | [53 empty] | 1 | bar: 2017-11-13
PLANTINGS |  | 0 | [53 empty] | 0
UTILITY RELOCATIONS |  | 0 | [53 empty] | 0
MATERIAL PROCUREMENT/FABRICATION |  | 0 | [53 empty] | 0
HANDLING OF CONTAMINATED MATERIAL |  | 0 | [53 empty] | 0
BORROW |  | 0 | [53 empty] | 0
ROCK EX |  | 4 | [53 empty] | 4 | bar: 2017-07-24 to 2017-07-31; 2017-10-02 to 2017-10-09
TPCBC |  | 1 | [53 empty] | 1 | bar: 2017-06-19
FILL |  | 0 | [53 empty] | 0
MEMBRANE |  | 0 | [53 empty] | 0
CURBING |  | 2 | [53 empty] | 2 | bar: 2017-09-11; 2017-11-27
GUIDERAIL |  | 0 | [53 empty] | 0
RIP-RAP |  | 0 | [53 empty] | 0
TEMPORARY SHEETING |  | 0 | [53 empty] | 0
COFFERDAM AND DEWATERING |  | 0 | [53 empty] | 0
STRUCTURE EXCAVATION |  | 0 | [53 empty] | 0
PILES/TEST PILES |  | 0 | [53 empty] | 0
TEMPORARY STRUCTURES |  | 0 | [53 empty] | 0
REMOVAL OF SUPERSTRUCTURE |  | 0 | [53 empty] | 0
SUBSTRUCTURE |  | 0 | [53 empty] | 0
SUPERSTRUCTURE |  | 0 | [53 empty] | 0
RETAINING WALLS |  | 0 | [53 empty] | 0
BEARING PADS |  | 0 | [53 empty] | 0
STRUCTURAL STEEL FABRICATION |  | 0 | [53 empty] | 0
STRUCTURAL STEEL DELIVERY |  | 0 | [53 empty] | 0
PAINTING |  | 0 | [53 empty] | 0
ILLUMINATION - BY LOCATION |  | 0 | [53 empty] | 0
SIGNALIZATION - BY INTERSECTION |  | 0 | [53 empty] | 0
TURF ESTABLISHMENT |  | 0 | [53 empty] | 0
FACILITY - DIVISION 2 - EXISTING CONDITIONS |  | 0 | [53 empty] | 0
FACILITY - DIVISION 3 - CONCRETE |  | 0 | [53 empty] | 0
FACILITY - DIVISION 4 - MASONRY |  | 0 | [53 empty] | 0
FACILITY - DIVISION 5 - METALS |  | 0 | [53 empty] | 0
FACILITY - DIVISION 6 - WOOD, PLASTIC, AND COMPOSITES |  | 0 | [53 empty] | 0
FACILITY - DIVISION 7 - THERMAL AND MOISTURE PROTECTION |  | 0 | [53 empty] | 0
FACILITY - DIVISION 8 - OPENINGS |  | 0 | [53 empty] | 0
FACILITY - DIVISION 9 - FINISHES |  | 0 | [53 empty] | 0
FACILITY - DIVISION 10 - SPECIALTIES |  | 0 | [53 empty] | 0
FACILITY - DIVISION 11 - EQUIPMENT |  | 0 | [53 empty] | 0
FACILITY - DIVISION 12 - FURNISHINGS |  | 0 | [53 empty] | 0
FACILITY - DIVISION 13 - SPECIAL CONSTRUCTION |  | 0 | [53 empty] | 0
FACILITY - DIVISION 14 - CONVEYING EQUIPMENT |  | 0 | [53 empty] | 0
FACILITY - DIVISION 21 - FIRE SUPPRESSION |  | 0 | [53 empty] | 0
FACILITY - DIVISION 22 - PLUMBING |  | 0 | [53 empty] | 0
FACILITY - DIVISION 23 - HEATING, VENTILATING, AND AIR CONDITIONING |  | 0 | [53 empty] | 0
FACILITY - DIVISION 26 - ELECTRICAL |  | 0 | [53 empty] | 0
FACILITY - DIVISION 27 - COMMUNICATIONS |  | 0 | [53 empty] | 0
FACILITY - DIVISION 28 - ELECTRONIC SAFETY AND SECURITY |  | 0 | [53 empty] | 0
FACILITY - DIVISION 31 - EARTHWORK |  | 0 | [53 empty] | 0
PROJECT CLOSEOUT |  | 1 | [53 empty] | 1 | bar: 2017-12-11
WORK BEGINNING DATE (STARTING MONDAYS) | time axis 2017-03-27 to 2018-03-26
Printed on: | 2019-03-18 16:04 |  | 2017-05-01: Start of Construction; 2017-06-26: 2017-04-03; 2017-12-18: CALENDAR WEEKS
[8 empty] | End of Construction | [7 empty] | 2017-11-30
[8 empty] | CALENDAR DAYS | [7 empty] | 242 | [24 empty] | WINTER SHUTDOWN (DEC. 1 to Mar. 31)
OPERATIONS DURING WEEK: |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 0 | 3 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C6: Select Appropriate "Work Classification" Description (change zoom level of worksheet for larger drop-down text)
Note on B19: The Notice to Proceed and Start of Construction typically match. If the Notice to Proceed falls within winter shutdown, the Start of Construction should be in April if there will be no work allowed during winter shutdown.
Note on B20: Enter the Start of Construction (typically a weekday) based on the Contractor's start of the work entered below.
Note on C22: This should match the Utility Work Schedules (UWS) from the utility companies
Note on Q91: Enter the End of Construction based on the last week of operations (typically a weekday).
Note on Q92: Number of days between the start and end of construction. The calendar days shouldn't exceed 244 (maximum between April 1 and November 30) if there is no work during winter shutdown and one construction season is anticipated.

## 2 yr calendar
CALENDAR DAY CHART FOR DETERMINING NUMBER OF CONTRACT DAYS
Project 000-000
FAP 000-000
Intersection Improvements
City/Town
WORK CLASSIFICATION:
|  | Prepared By (Designer): | Name | [17 empty] | Date: | [14 empty] | Concurred By: | [18 empty] | Date:
|  |  | Project Engineer | [33 empty] | (District Construction Supervising Engineer)
| Construction Season |  | 2017-03-27 | [39 empty] | 2018-01-01 | [52 empty] | 2019-01-07
WORK BEGINNING DATE (STARTING MONDAYS) | [101 empty] | WEEKS ENTERED | time axis 2017-03-27 to 2019-02-11
OPERATION | NUMBER OF WEEKS |  | 2017-03-27: NOTICE TO PROCEED
FDP | 2016-09-07
DCD | 2016-10-19
DATE OF ADV (Wed) | 2016-11-16
DATE OF LETTING (Wed) | 2016-12-14
DATE OF AWARD (Fri) | 2017-02-10
NOTICE TO PROCEED (Mon.) | 2017-03-27
START OF CONSTRUCTION | 2017-04-03
PERMIT RESTRICTIONS |  | N/A to N/A | [99 empty] | 0
UTILITY WORK |  | 10 | [99 empty] | 10 | bar: 2017-05-08 to 2017-07-10
MOBILIZATION |  | 1 | [99 empty] | 1 | bar: 2017-04-17
CLEAR AND GRUB |  | 1 | [99 empty] | 1 | bar: 2017-04-24
EARTH EXCAVATION |  | 5 | [99 empty] | 5 | bar: 2017-05-01; 2017-07-10 to 2017-07-17; 2017-09-18 to 2017-09-25
DRAINAGE STRUCTURES |  | 2 | [99 empty] | 2 | bar: 2017-08-07; 2017-10-16
STORM PIPE |  | 3 | [99 empty] | 3 | bar: 2017-08-07; 2017-10-16 to 2017-10-23
WATERMAIN |  | 0 | [99 empty] | 0
FORMATION OF SUBGRADE |  | 2 | [99 empty] | 2 | bar: 2017-08-14; 2017-10-30
SUBBASE/PROCESSED AGGREGATE BASE |  | 2 | [99 empty] | 2 | bar: 2017-08-14; 2017-10-30
MILLING |  | 1 | [99 empty] | 1 | bar: 2017-08-21
HMA S1 |  | 2 | [99 empty] | 2 | bar: 2017-08-28; 2017-11-13
HMA S0.5 |  | 2 | [99 empty] | 2 | bar: 2017-08-28; 2017-11-13
SIDEWALK |  | 0 | [99 empty] | 0
TRAFFIC SIGNAL |  | 0 | [99 empty] | 0
TEMP PAVE MARK FOR WINTER |  | 0 | [99 empty] | 0
TRAFFIC SIGNS/PAVE MARKINGS |  | 2 | [99 empty] | 2 | bar: 2017-09-04; 2017-11-20
TOP SOIL/TURF ESTABLISHMENT |  | 1 | [99 empty] | 1 | bar: 2017-11-13
PLANTINGS |  | 0 | [99 empty] | 0
UTILITY RELOCATIONS |  | 0 | [99 empty] | 0
MATERIAL PROCUREMENT/FABRICATION |  | 0 | [99 empty] | 0
HANDLING OF CONTAMINATED MATERIAL |  | 0 | [99 empty] | 0
BORROW |  | 0 | [99 empty] | 0
ROCK EX |  | 4 | [99 empty] | 4 | bar: 2017-10-02 to 2017-10-09; 2018-04-16 to 2018-04-23
TPCBC |  | 1 | [99 empty] | 1 | bar: 2018-04-30
FILL |  | 0 | [99 empty] | 0
MEMBRANE |  | 0 | [99 empty] | 0
CURBING |  | 2 | [99 empty] | 2 | bar: 2017-09-11; 2017-11-27
GUIDERAIL |  | 0 | [99 empty] | 0
RIP-RAP |  | 0 | [99 empty] | 0
TEMPORARY SHEETING |  | 0 | [99 empty] | 0
COFFERDAM AND DEWATERING |  | 0 | [99 empty] | 0
STRUCTURE EXCAVATION |  | 0 | [99 empty] | 0
PILES/TEST PILES |  | 0 | [99 empty] | 0
TEMPORARY STRUCTURES |  | 0 | [99 empty] | 0
REMOVAL OF SUPERSTRUCTURE |  | 0 | [99 empty] | 0
SUBSTRUCTURE |  | 0 | [99 empty] | 0
SUPERSTRUCTURE |  | 0 | [99 empty] | 0
RETAINING WALLS |  | 0 | [99 empty] | 0
BEARING PADS |  | 0 | [99 empty] | 0
STRUCTURAL STEEL FABRICATION |  | 0 | [99 empty] | 0
STRUCTURAL STEEL DELIVERY |  | 0 | [99 empty] | 0
PAINTING |  | 0 | [99 empty] | 0
ILLUMINATION - BY LOCATION |  | 0 | [99 empty] | 0
SIGNALIZATION - BY INTERSECTION |  | 0 | [99 empty] | 0
TURF ESTABLISHMENT |  | 0 | [99 empty] | 0
FACILITY - DIVISION 2 - EXISTING CONDITIONS |  | 0 | [99 empty] | 0
FACILITY - DIVISION 3 - CONCRETE |  | 0 | [99 empty] | 0
FACILITY - DIVISION 4 - MASONRY |  | 0 | [99 empty] | 0
FACILITY - DIVISION 5 - METALS |  | 0 | [99 empty] | 0
FACILITY - DIVISION 6 - WOOD, PLASTIC, AND COMPOSITES |  | 0 | [99 empty] | 0
FACILITY - DIVISION 7 - THERMAL AND MOISTURE PROTECTION |  | 0 | [99 empty] | 0
FACILITY - DIVISION 8 - OPENINGS |  | 0 | [99 empty] | 0
FACILITY - DIVISION 9 - FINISHES |  | 0 | [99 empty] | 0
FACILITY - DIVISION 10 - SPECIALTIES |  | 0 | [99 empty] | 0
FACILITY - DIVISION 11 - EQUIPMENT |  | 0 | [99 empty] | 0
FACILITY - DIVISION 12 - FURNISHINGS |  | 0 | [99 empty] | 0
FACILITY - DIVISION 13 - SPECIAL CONSTRUCTION |  | 0 | [99 empty] | 0
FACILITY - DIVISION 14 - CONVEYING EQUIPMENT |  | 0 | [99 empty] | 0
FACILITY - DIVISION 21 - FIRE SUPPRESSION |  | 0 | [99 empty] | 0
FACILITY - DIVISION 22 - PLUMBING |  | 0 | [99 empty] | 0
FACILITY - DIVISION 23 - HEATING, VENTILATING, AND AIR CONDITIONING |  | 0 | [99 empty] | 0
FACILITY - DIVISION 26 - ELECTRICAL |  | 0 | [99 empty] | 0
FACILITY - DIVISION 27 - COMMUNICATIONS |  | 0 | [99 empty] | 0
FACILITY - DIVISION 28 - ELECTRONIC SAFETY AND SECURITY |  | 0 | [99 empty] | 0
FACILITY - DIVISION 31 - EARTHWORK |  | 0 | [99 empty] | 0
PROJECT CLOSEOUT |  | 1 | [99 empty] | 1 | bar: 2018-05-21
WORK BEGINNING DATE (STARTING MONDAYS) | time axis 2017-03-27 to 2019-02-11
[31 empty] | Season 1 | [5 empty] | Season 2
Printed on: | 2019-03-18 16:04 |  | 2017-05-01: Start of Construction; 2017-06-26: 2017-04-03; 2017-09-18: Start; 2017-10-09: 2017-04-03; 2017-11-20: 2018-04-01; 2018-08-13: CALENDAR WEEKS
[8 empty] | End of Construction | [7 empty] | 2018-05-11 | [11 empty] | End |  |  | 2017-11-30 | [5 empty] | 2018-05-11
[8 empty] | CALENDAR DAYS | [7 empty] | 283 | [58 empty] | WINTER SHUTDOWN (DEC. 1 to Mar. 31)
|  |  | WORK CLASSIFICATION | [12 empty] | Group XX
OPERATIONS DURING WEEK: |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 0 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D7: Select Appropriate "Work Classification" Description (change zoom level of worksheet for larger drop-down text)
Note on B20: The Notice to Proceed and Start of Construction typically match. If the Notice to Proceed falls within winter shutdown, the Start of Construction should be in April if there will be no work allowed during winter shutdown.
Note on B21: Enter the Start of Construction (typically a weekday) based on the Contractor's start of the work entered below.
Note on C23: This should match the Utility Work Schedules (UWS) from the utility companies
Note on AL92: Designer should enter the Start for Season 2. If there is no work during winter shutdown, enter April 1. If work is allowed during the winter shutdown, enter January 1.
Note on AF93: Designer should enter the End of Season 1. If there is no work during winter shutdown, enter November 30. If work is allowed during the winter shutdown, enter December 31.
Note on AL93: Designer should enter the End of Construction based on the last week of work (typically a weekday).
Note on Q94: Number of days between the start and end of construction. This is based on the season 1 and 2 start/end dates on the right. The maximum number of days between April 1 and November 30 is 244. The calendar days shouldn't exceed 488 if there is no work during winter shutdown and two seasons are anticipated.

## 3 yr calendar
CALENDAR DAY CHART FOR DETERMINING NUMBER OF CONTRACT DAYS
Project 000-000
FAP 000-000
Intersection Improvements
City/Town
WORK CLASSIFICATION:
|  | Prepared By (Designer): | Name | [17 empty] | Date: | [14 empty] | Concurred By: | [18 empty] | Date:
|  |  | Project Engineer | [33 empty] | (District Construction Supervising Engineer)
| Construction Season |  | 2017-03-27 | [39 empty] | 2018-01-01 | [52 empty] | 2019-01-07 | [51 empty] | 2020-01-06
WORK BEGINNING DATE (STARTING MONDAYS) | [157 empty] | WEEKS ENTERED | time axis 2017-03-27 to 2020-03-09
OPERATION | NUMBER OF WEEKS |  | 2017-03-27: NOTICE TO PROCEED
FDP | 2016-09-07
DCD | 2016-10-19
DATE OF ADV (Wed) | 2016-11-16
DATE OF LETTING (Wed) | 2016-12-14
DATE OF AWARD (Fri) | 2017-02-10
NOTICE TO PROCEED (Mon.) | 2017-03-27
START OF CONSTRUCTION | 2017-04-03
PERMIT RESTRICTIONS |  | N/A to N/A | [155 empty] | 0
UTILITY WORK |  | 10 | [155 empty] | 10 | bar: 2017-05-08 to 2017-07-10
MOBILIZATION |  | 1 | [155 empty] | 1 | bar: 2017-04-17
CLEAR AND GRUB |  | 1 | [155 empty] | 1 | bar: 2017-04-24
EARTH EXCAVATION |  | 5 | [155 empty] | 5 | bar: 2017-05-01; 2017-07-10 to 2017-07-17; 2018-04-16 to 2018-04-23
DRAINAGE STRUCTURES |  | 2 | [155 empty] | 2 | bar: 2017-08-07; 2018-05-14
STORM PIPE |  | 3 | [155 empty] | 3 | bar: 2017-08-07; 2018-05-14 to 2018-05-21
WATERMAIN |  | 0 | [155 empty] | 0
FORMATION OF SUBGRADE |  | 2 | [155 empty] | 2 | bar: 2017-08-14; 2018-05-28
SUBBASE/PROCESSED AGGREGATE BASE |  | 2 | [155 empty] | 2 | bar: 2017-08-14; 2018-05-28
MILLING |  | 1 | [155 empty] | 1 | bar: 2017-08-21
HMA S1 |  | 2 | [155 empty] | 2 | bar: 2017-08-28; 2018-06-11
HMA S0.5 |  | 2 | [155 empty] | 2 | bar: 2017-08-28; 2018-06-11
SIDEWALK |  | 0 | [155 empty] | 0
TRAFFIC SIGNAL |  | 0 | [155 empty] | 0
TEMP PAVE MARK FOR WINTER |  | 0 | [155 empty] | 0
TRAFFIC SIGNS/PAVE MARKINGS |  | 2 | [155 empty] | 2 | bar: 2017-09-04; 2018-06-18
TOP SOIL/TURF ESTABLISHMENT |  | 1 | [155 empty] | 1 | bar: 2018-06-11
PLANTINGS |  | 0 | [155 empty] | 0
UTILITY RELOCATIONS |  | 0 | [155 empty] | 0
MATERIAL PROCUREMENT/FABRICATION |  | 0 | [155 empty] | 0
HANDLING OF CONTAMINATED MATERIAL |  | 0 | [155 empty] | 0
BORROW |  | 0 | [155 empty] | 0
ROCK EX |  | 4 | [155 empty] | 4 | bar: 2017-10-02 to 2017-10-09; 2018-11-19 to 2018-11-26
TPCBC |  | 1 | [155 empty] | 1 | bar: 2018-12-03
FILL |  | 0 | [155 empty] | 0
MEMBRANE |  | 0 | [155 empty] | 0
CURBING |  | 2 | [155 empty] | 2 | bar: 2017-09-11; 2017-11-27
GUIDERAIL |  | 0 | [155 empty] | 0
RIP-RAP |  | 0 | [155 empty] | 0
TEMPORARY SHEETING |  | 0 | [155 empty] | 0
COFFERDAM AND DEWATERING |  | 0 | [155 empty] | 0
STRUCTURE EXCAVATION |  | 0 | [155 empty] | 0
PILES/TEST PILES |  | 0 | [155 empty] | 0
TEMPORARY STRUCTURES |  | 0 | [155 empty] | 0
REMOVAL OF SUPERSTRUCTURE |  | 0 | [155 empty] | 0
SUBSTRUCTURE |  | 0 | [155 empty] | 0
SUPERSTRUCTURE |  | 0 | [155 empty] | 0
RETAINING WALLS |  | 0 | [155 empty] | 0
BEARING PADS |  | 0 | [155 empty] | 0
STRUCTURAL STEEL FABRICATION |  | 0 | [155 empty] | 0
STRUCTURAL STEEL DELIVERY |  | 0 | [155 empty] | 0
PAINTING |  | 0 | [155 empty] | 0
ILLUMINATION - BY LOCATION |  | 0 | [155 empty] | 0
SIGNALIZATION - BY INTERSECTION |  | 0 | [155 empty] | 0
TURF ESTABLISHMENT |  | 0 | [155 empty] | 0
FACILITY - DIVISION 2 - EXISTING CONDITIONS |  | 0 | [155 empty] | 0
FACILITY - DIVISION 3 - CONCRETE |  | 0 | [155 empty] | 0
FACILITY - DIVISION 4 - MASONRY |  | 0 | [155 empty] | 0
FACILITY - DIVISION 5 - METALS |  | 0 | [155 empty] | 0
FACILITY - DIVISION 6 - WOOD, PLASTIC, AND COMPOSITES |  | 0 | [155 empty] | 0
FACILITY - DIVISION 7 - THERMAL AND MOISTURE PROTECTION |  | 0 | [155 empty] | 0
FACILITY - DIVISION 8 - OPENINGS |  | 0 | [155 empty] | 0
FACILITY - DIVISION 9 - FINISHES |  | 0 | [155 empty] | 0
FACILITY - DIVISION 10 - SPECIALTIES |  | 0 | [155 empty] | 0
FACILITY - DIVISION 11 - EQUIPMENT |  | 0 | [155 empty] | 0
FACILITY - DIVISION 12 - FURNISHINGS |  | 0 | [155 empty] | 0
FACILITY - DIVISION 13 - SPECIAL CONSTRUCTION |  | 0 | [155 empty] | 0
FACILITY - DIVISION 14 - CONVEYING EQUIPMENT |  | 0 | [155 empty] | 0
FACILITY - DIVISION 21 - FIRE SUPPRESSION |  | 0 | [155 empty] | 0
FACILITY - DIVISION 22 - PLUMBING |  | 0 | [155 empty] | 0
FACILITY - DIVISION 23 - HEATING, VENTILATING, AND AIR CONDITIONING |  | 0 | [155 empty] | 0
FACILITY - DIVISION 26 - ELECTRICAL |  | 0 | [155 empty] | 0
FACILITY - DIVISION 27 - COMMUNICATIONS |  | 0 | [155 empty] | 0
FACILITY - DIVISION 28 - ELECTRONIC SAFETY AND SECURITY |  | 0 | [155 empty] | 0
FACILITY - DIVISION 31 - EARTHWORK |  | 0 | [155 empty] | 0
PROJECT CLOSEOUT |  | 1 | [155 empty] | 1 | bar: 2019-05-13
WORK BEGINNING DATE (STARTING MONDAYS) | time axis 2017-03-27 to 2020-03-09
[31 empty] | Season 1 | [5 empty] | Season 2 | [5 empty] | Season 3
Printed on: | 2019-03-18 16:04 |  | 2017-05-01: Start of Construction; 2017-06-26: 2017-04-03; 2017-09-18: Start; 2017-10-09: 2017-04-03; 2017-11-20: 2018-04-01; 2018-01-01: 2019-04-01; 2018-08-06: CALENDAR WEEKS
[8 empty] | End of Construction | [7 empty] | 2019-05-03 | [11 empty] | End |  |  | 2017-11-30 | [5 empty] | 2018-11-30 | [5 empty] | 2019-05-03
[8 empty] | CALENDAR DAYS | [7 empty] | 519 | [57 empty] | WINTER SHUTDOWN (DEC. 1 to Mar. 31)
|  |  | WORK CLASSIFICATION | [12 empty] | Group XX
OPERATIONS DURING WEEK: |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 1 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D7: Select Appropriate "Work Classification" Description (change zoom level of worksheet for larger drop-down text)
Note on B20: The Notice to Proceed and Start of Construction typically match. If the Notice to Proceed falls within winter shutdown, the Start of Construction should be in April if there will be no work allowed during winter shutdown.
Note on B21: Enter the Start of Construction (typically a weekday) based on the Contractor's start of the work entered below.
Note on C23: This should match the Utility Work Schedules (UWS) from the utility companies
Note on AL92: Designer should enter the Start for Season 2. If there is no work during winter shutdown, enter April 1. If work is allowed during the winter shutdown, enter January 1.
Note on AR92: Designer should enter the Start for Season 3. If there is no work during winter shutdown, enter April 1. If work is allowed during the winter shutdown, enter January 1.
Note on AF93: Designer should enter the End of Season 1. If there is no work during winter shutdown, enter November 30. If work is allowed during the winter shutdown, enter December 31.
Note on AL93: Designer should enter the End of Season 2. If there is no work during winter shutdown, enter November 30. If work is allowed during the winter shutdown, enter December 31.
Note on AR93: Designer should enter the End of Construction based on the last week of work (typically a weekday).
Note on Q94: Number of days between the start and end of construction. This is based on the season 1,2,3 start/end dates on the right. The maximum number of days between April 1 and November 30 is 244. The calendar days shouldn't exceed 732 if there is no work during winter shutdown and two seasons are anticipated.

## 1 yr Without Winter Shutdown
CALENDAR DAY CHART FOR DETERMINING NUMBER OF CONTRACT DAYS
Project 000-000
FAP 000-000
Intersection Improvements
City/Town
WORK CLASSIFICATION:
| Prepared By (Designer): | Name | [15 empty] | Date: | [11 empty] | Concurred By: | [18 empty] | Date:
|  | Project Engineer | [28 empty] | (District Construction Supervising Engineer)
| Construction Season |  | 2017-03-27 | [39 empty] | 2018-01-01
WORK BEGINNING DATE (STARTING MONDAYS) | [55 empty] | WEEKS ENTERED | time axis 2017-03-27 to 2018-03-26
OPERATION | NUMBER OF WEEKS |  | 2017-03-27: NOTICE TO PROCEED
FDP | 2016-09-07
DCD | 2016-10-19
DATE OF ADV (Wed) | 2016-11-16
DATE OF LETTING (Wed) | 2016-12-14
DATE OF AWARD (Fri) | 2017-02-10
NOTICE TO PROCEED (Mon.) | 2017-03-27
START OF CONSTRUCTION | 2017-04-03
PERMIT RESTRICTIONS |  | N/A to N/A | [53 empty] | 0
UTILITY WORK |  | 10 | [53 empty] | 10 | bar: 2017-05-08 to 2017-07-10
MOBILIZATION |  | 1 | [53 empty] | 1 | bar: 2017-04-17
CLEAR AND GRUB |  | 1 | [53 empty] | 1 | bar: 2017-04-24
EARTH EXCAVATION |  | 5 | [53 empty] | 5 | bar: 2017-05-01; 2017-07-10 to 2017-07-17; 2017-09-18 to 2017-09-25
DRAINAGE STRUCTURES |  | 2 | [53 empty] | 2 | bar: 2017-08-07; 2017-10-16
STORM PIPE |  | 3 | [53 empty] | 3 | bar: 2017-08-07; 2017-10-16 to 2017-10-23
WATERMAIN |  | 0 | [53 empty] | 0
FORMATION OF SUBGRADE |  | 2 | [53 empty] | 2 | bar: 2017-08-14; 2017-10-30
SUBBASE/PROCESSED AGGREGATE BASE |  | 2 | [53 empty] | 2 | bar: 2017-08-14; 2017-10-30
MILLING |  | 1 | [53 empty] | 1 | bar: 2017-08-21
HMA S1 |  | 2 | [53 empty] | 2 | bar: 2017-08-28; 2017-11-13
HMA S0.5 |  | 2 | [53 empty] | 2 | bar: 2017-08-28; 2018-02-26
SIDEWALK |  | 0 | [53 empty] | 0
TRAFFIC SIGNAL |  | 0 | [53 empty] | 0
TEMP PAVE MARK FOR WINTER |  | 0 | [53 empty] | 0
TRAFFIC SIGNS/PAVE MARKINGS |  | 2 | [53 empty] | 2 | bar: 2017-09-04; 2017-11-20
TOP SOIL/TURF ESTABLISHMENT |  | 1 | [53 empty] | 1 | bar: 2017-11-13
PLANTINGS |  | 0 | [53 empty] | 0
UTILITY RELOCATIONS |  | 0 | [53 empty] | 0
MATERIAL PROCUREMENT/FABRICATION |  | 0 | [53 empty] | 0
HANDLING OF CONTAMINATED MATERIAL |  | 0 | [53 empty] | 0
BORROW |  | 0 | [53 empty] | 0
ROCK EX |  | 4 | [53 empty] | 4 | bar: 2017-07-24 to 2017-07-31; 2017-10-02 to 2017-10-09
TPCBC |  | 1 | [53 empty] | 1 | bar: 2017-06-19
FILL |  | 0 | [53 empty] | 0
MEMBRANE |  | 0 | [53 empty] | 0
CURBING |  | 2 | [53 empty] | 2 | bar: 2017-09-11; 2017-11-27
GUIDERAIL |  | 0 | [53 empty] | 0
RIP-RAP |  | 0 | [53 empty] | 0
TEMPORARY SHEETING |  | 0 | [53 empty] | 0
COFFERDAM AND DEWATERING |  | 0 | [53 empty] | 0
STRUCTURE EXCAVATION |  | 0 | [53 empty] | 0
PILES/TEST PILES |  | 0 | [53 empty] | 0
TEMPORARY STRUCTURES |  | 0 | [53 empty] | 0
REMOVAL OF SUPERSTRUCTURE |  | 0 | [53 empty] | 0
SUBSTRUCTURE |  | 0 | [53 empty] | 0
SUPERSTRUCTURE |  | 0 | [53 empty] | 0
RETAINING WALLS |  | 0 | [53 empty] | 0
BEARING PADS |  | 0 | [53 empty] | 0
STRUCTURAL STEEL FABRICATION |  | 0 | [53 empty] | 0
STRUCTURAL STEEL DELIVERY |  | 0 | [53 empty] | 0
PAINTING |  | 0 | [53 empty] | 0
ILLUMINATION - BY LOCATION |  | 0 | [53 empty] | 0
SIGNALIZATION - BY INTERSECTION |  | 0 | [53 empty] | 0
TURF ESTABLISHMENT |  | 0 | [53 empty] | 0
FACILITY - DIVISION 2 - EXISTING CONDITIONS |  | 0 | [53 empty] | 0
FACILITY - DIVISION 3 - CONCRETE |  | 0 | [53 empty] | 0
FACILITY - DIVISION 4 - MASONRY |  | 0 | [53 empty] | 0
FACILITY - DIVISION 5 - METALS |  | 0 | [53 empty] | 0
FACILITY - DIVISION 6 - WOOD, PLASTIC, AND COMPOSITES |  | 0 | [53 empty] | 0
FACILITY - DIVISION 7 - THERMAL AND MOISTURE PROTECTION |  | 0 | [53 empty] | 0
FACILITY - DIVISION 8 - OPENINGS |  | 0 | [53 empty] | 0
FACILITY - DIVISION 9 - FINISHES |  | 0 | [53 empty] | 0
FACILITY - DIVISION 10 - SPECIALTIES |  | 0 | [53 empty] | 0
FACILITY - DIVISION 11 - EQUIPMENT |  | 0 | [53 empty] | 0
FACILITY - DIVISION 12 - FURNISHINGS |  | 0 | [53 empty] | 0
FACILITY - DIVISION 13 - SPECIAL CONSTRUCTION |  | 0 | [53 empty] | 0
FACILITY - DIVISION 14 - CONVEYING EQUIPMENT |  | 0 | [53 empty] | 0
FACILITY - DIVISION 21 - FIRE SUPPRESSION |  | 0 | [53 empty] | 0
FACILITY - DIVISION 22 - PLUMBING |  | 0 | [53 empty] | 0
FACILITY - DIVISION 23 - HEATING, VENTILATING, AND AIR CONDITIONING |  | 0 | [53 empty] | 0
FACILITY - DIVISION 26 - ELECTRICAL |  | 0 | [53 empty] | 0
FACILITY - DIVISION 27 - COMMUNICATIONS |  | 0 | [53 empty] | 0
FACILITY - DIVISION 28 - ELECTRONIC SAFETY AND SECURITY |  | 0 | [53 empty] | 0
FACILITY - DIVISION 31 - EARTHWORK |  | 0 | [53 empty] | 0
PROJECT CLOSEOUT |  | 1 | [53 empty] | 1 | bar: 2017-12-11
WORK BEGINNING DATE (STARTING MONDAYS) | time axis 2017-03-27 to 2018-03-26
Printed on: | 2019-03-18 16:04 |  | 2017-05-01: Start of Construction; 2017-06-26: 2017-04-03; 2017-12-18: CALENDAR WEEKS
[8 empty] | End of Construction | [7 empty] | 2018-02-08
[8 empty] | CALENDAR DAYS | [7 empty] | 312
|  |  | WORK CLASSIFICATION | [12 empty] | Group XX
OPERATIONS DURING WEEK: |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 0 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Note on C7: Select Appropriate "Work Classification" Description (change zoom level of worksheet for larger drop-down text)
Note on B20: The Notice to Proceed and Start of Construction typically match.
Note on B21: Enter the Start of Construction (typically a weekday) based on the Contractor's start of the work entered below.
Note on C23: This should match the Utility Work Schedules (UWS) from the utility companies
Note on Q92: Enter the End of Construction based on the last week of operations (typically a weekday).
Note on Q93: Number of days between the start and end of construction.

## 2 yr Without Winter Shutdown
CALENDAR DAY CHART FOR DETERMINING NUMBER OF CONTRACT DAYS
Project 000-000
FAP 000-000
Intersection Improvements
City/Town
WORK CLASSIFICATION:
|  | Prepared By (Designer): | Name | [17 empty] | Date: | [14 empty] | Concurred By: | [18 empty] | Date:
|  |  | Project Engineer | [33 empty] | (District Construction Supervising Engineer)
| Construction Season |  | 2017-03-27 | [39 empty] | 2018-01-01 | [52 empty] | 2019-01-07
WORK BEGINNING DATE (STARTING MONDAYS) | [101 empty] | WEEKS ENTERED | time axis 2017-03-27 to 2019-02-11
OPERATION | NUMBER OF WEEKS |  | 2017-03-27: NOTICE TO PROCEED
FDP | 2016-09-07
DCD | 2016-10-19
DATE OF ADV (Wed) | 2016-11-16
DATE OF LETTING (Wed) | 2016-12-14
DATE OF AWARD (Fri) | 2017-02-10
NOTICE TO PROCEED (Mon.) | 2017-03-27
START OF CONSTRUCTION | 2017-04-03
PERMIT RESTRICTIONS |  | N/A to N/A | [99 empty] | 0
UTILITY WORK |  | 10 | [99 empty] | 10 | bar: 2017-05-08 to 2017-07-10
MOBILIZATION |  | 1 | [99 empty] | 1 | bar: 2017-04-17
CLEAR AND GRUB |  | 1 | [99 empty] | 1 | bar: 2017-04-24
EARTH EXCAVATION |  | 5 | [99 empty] | 5 | bar: 2017-05-01; 2017-07-10 to 2017-07-17; 2017-09-18 to 2017-09-25
DRAINAGE STRUCTURES |  | 2 | [99 empty] | 2 | bar: 2017-08-07; 2017-10-16
STORM PIPE |  | 3 | [99 empty] | 3 | bar: 2017-08-07; 2017-10-16 to 2017-10-23
WATERMAIN |  | 0 | [99 empty] | 0
FORMATION OF SUBGRADE |  | 2 | [99 empty] | 2 | bar: 2017-08-14; 2018-02-05
SUBBASE/PROCESSED AGGREGATE BASE |  | 2 | [99 empty] | 2 | bar: 2017-08-14; 2017-10-30
MILLING |  | 1 | [99 empty] | 1 | bar: 2017-08-21
HMA S1 |  | 2 | [99 empty] | 2 | bar: 2017-08-28; 2017-11-13
HMA S0.5 |  | 2 | [99 empty] | 2 | bar: 2017-08-28; 2017-11-13
SIDEWALK |  | 0 | [99 empty] | 0
TRAFFIC SIGNAL |  | 0 | [99 empty] | 0
TEMP PAVE MARK FOR WINTER |  | 0 | [99 empty] | 0
TRAFFIC SIGNS/PAVE MARKINGS |  | 2 | [99 empty] | 2 | bar: 2017-09-04; 2018-02-26
TOP SOIL/TURF ESTABLISHMENT |  | 1 | [99 empty] | 1 | bar: 2017-11-13
PLANTINGS |  | 0 | [99 empty] | 0
UTILITY RELOCATIONS |  | 0 | [99 empty] | 0
MATERIAL PROCUREMENT/FABRICATION |  | 0 | [99 empty] | 0
HANDLING OF CONTAMINATED MATERIAL |  | 0 | [99 empty] | 0
BORROW |  | 0 | [99 empty] | 0
ROCK EX |  | 4 | [99 empty] | 4 | bar: 2017-10-02 to 2017-10-09; 2018-04-16 to 2018-04-23
TPCBC |  | 1 | [99 empty] | 1 | bar: 2018-04-30
FILL |  | 0 | [99 empty] | 0
MEMBRANE |  | 0 | [99 empty] | 0
CURBING |  | 2 | [99 empty] | 2 | bar: 2017-09-11; 2017-11-27
GUIDERAIL |  | 0 | [99 empty] | 0
RIP-RAP |  | 0 | [99 empty] | 0
TEMPORARY SHEETING |  | 0 | [99 empty] | 0
COFFERDAM AND DEWATERING |  | 0 | [99 empty] | 0
STRUCTURE EXCAVATION |  | 0 | [99 empty] | 0
PILES/TEST PILES |  | 0 | [99 empty] | 0
TEMPORARY STRUCTURES |  | 0 | [99 empty] | 0
REMOVAL OF SUPERSTRUCTURE |  | 0 | [99 empty] | 0
SUBSTRUCTURE |  | 0 | [99 empty] | 0
SUPERSTRUCTURE |  | 0 | [99 empty] | 0
RETAINING WALLS |  | 0 | [99 empty] | 0
BEARING PADS |  | 0 | [99 empty] | 0
STRUCTURAL STEEL FABRICATION |  | 0 | [99 empty] | 0
STRUCTURAL STEEL DELIVERY |  | 0 | [99 empty] | 0
PAINTING |  | 0 | [99 empty] | 0
ILLUMINATION - BY LOCATION |  | 0 | [99 empty] | 0
SIGNALIZATION - BY INTERSECTION |  | 0 | [99 empty] | 0
TURF ESTABLISHMENT |  | 0 | [99 empty] | 0
FACILITY - DIVISION 2 - EXISTING CONDITIONS |  | 0 | [99 empty] | 0
FACILITY - DIVISION 3 - CONCRETE |  | 0 | [99 empty] | 0
FACILITY - DIVISION 4 - MASONRY |  | 0 | [99 empty] | 0
FACILITY - DIVISION 5 - METALS |  | 0 | [99 empty] | 0
FACILITY - DIVISION 6 - WOOD, PLASTIC, AND COMPOSITES |  | 0 | [99 empty] | 0
FACILITY - DIVISION 7 - THERMAL AND MOISTURE PROTECTION |  | 0 | [99 empty] | 0
FACILITY - DIVISION 8 - OPENINGS |  | 0 | [99 empty] | 0
FACILITY - DIVISION 9 - FINISHES |  | 0 | [99 empty] | 0
FACILITY - DIVISION 10 - SPECIALTIES |  | 0 | [99 empty] | 0
FACILITY - DIVISION 11 - EQUIPMENT |  | 0 | [99 empty] | 0
FACILITY - DIVISION 12 - FURNISHINGS |  | 0 | [99 empty] | 0
FACILITY - DIVISION 13 - SPECIAL CONSTRUCTION |  | 0 | [99 empty] | 0
FACILITY - DIVISION 14 - CONVEYING EQUIPMENT |  | 0 | [99 empty] | 0
FACILITY - DIVISION 21 - FIRE SUPPRESSION |  | 0 | [99 empty] | 0
FACILITY - DIVISION 22 - PLUMBING |  | 0 | [99 empty] | 0
FACILITY - DIVISION 23 - HEATING, VENTILATING, AND AIR CONDITIONING |  | 0 | [99 empty] | 0
FACILITY - DIVISION 26 - ELECTRICAL |  | 0 | [99 empty] | 0
FACILITY - DIVISION 27 - COMMUNICATIONS |  | 0 | [99 empty] | 0
FACILITY - DIVISION 28 - ELECTRONIC SAFETY AND SECURITY |  | 0 | [99 empty] | 0
FACILITY - DIVISION 31 - EARTHWORK |  | 0 | [99 empty] | 0
PROJECT CLOSEOUT |  | 1 | [99 empty] | 1 | bar: 2018-05-21
WORK BEGINNING DATE (STARTING MONDAYS) | time axis 2017-03-27 to 2019-02-11
Printed on: | 2019-03-18 16:04 |  | 2017-05-01: Start of Construction; 2017-06-26: 2017-04-03; 2018-08-13: CALENDAR WEEKS
[8 empty] | End of Construction | [7 empty] | 2018-05-11
[8 empty] | CALENDAR DAYS | [7 empty] | 404
|  |  | WORK CLASSIFICATION | [12 empty] | Group XX
OPERATIONS DURING WEEK: |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D7: Select Appropriate "Work Classification" Description (change zoom level of worksheet for larger drop-down text)
Note on B20: The Notice to Proceed and Start of Construction typically match.
Note on B21: Enter the Start of Construction (typically a weekday) based on the Contractor's start of the work entered below.
Note on C23: This should match the Utility Work Schedules (UWS) from the utility companies
Note on Q93: Designer should enter the End of Construction based on the last week of work (typically a weekday).
Note on Q94: Number of days between the start and end of construction.

## Drop Down Lists
Workspace Classification Descriptions
Group No. 01 - Earthwork: Site Work
Group No. 02 - Earthwork: Utility Work
Group No. 03 - Concrete Restoration
Group No. 04 - Specialized Concrete Repair
Group No. 05 - Paving and Associated Construction
Group No. 06 - Road Construction and Rehabilitation: Local Roads & Streets and Non-Freeways
Group No. 07 - Road Construction and Rehabilitation: Limited Access Highways, Freeways, and Major Reconstruction of Non-Freeway State Routes
Group No. 08 - Minor Bridges
Group No. 09 - Intermediate Bridges
Group No. 10 - Major Bridges
Group No. 11 - Bridge Painting
Group No. 12 - Marine Repairs, Construction or Salvaging
Group No. 13 - Traffic Control & Illumination/Electrical
Group No. 14 - Signing Delineation
Group No. 15 - Intelligent Transportation Systems (ITS)
Group No. 16 - Pavement Markings
Group No. 17 - Incidental Construction: Fencing
Group No. 18 - Incidental Construction: Guide Rail
Group No. 19 - Incidental Construction: Bridge Joints and Membranes
Group No. 20 - Incidental Construction: Temporary Traffic Control
Group No. 21 - Railroad Construction
Group No. 22 - Railroad Construction: Electrical
Group No. 23 - Landscaping/Environmental Improvements
Group No. 24 - Environmental
Group No. 25A - Vertical Construction
Group No. 25B - Vertical Construction
Group No. 25C - Vertical Construction