## Checklist Name
| Revision Date: |  |  | 2015-06-01 | Author: | Delois Barnes | Phone No.: | (860) 594-3307
Project Number:
Prepared by:
Landscape Unit Contact:
Comments / Completion Date
Coordination with Project Contract
Review contract plans for all planting locations, noting any conflicts with utilities or staging.
Invite Landscape Design to Pre-Construction Meeting, determine who is reponsible for topsoil and sub-surface preparation.
Invite Landscape Design to tree-removal meeting, note trees outside project limits impacted by work.
Develop a tracking system for planting installation inspection, warranty kick off dates.
Review contract for Control and Removal of Invasive Vegetation, Tree Protection, Root Pruning, or other items.
Ensure that spring dug material is procured in advance of Fall Installations by contractor.
Throughout construction - Note conflicts from Change Orders, or areas of poor drainage, compaction from anti-tracking, etc.
Coordination Early in Planting Season
Notification
Contact Landscape Design to review field conditions and determine corrective measures.
Review specifications, coordinate seeding and soil preparation with General Contractor.
Direct contractor to send a transmittal with attached Source of Supply and Request for Plant Inspection to the Landscape Design Unit.
Inspections and Submittals
Upon reciept of the approved transmittal back from Landscape Design, forward to Contractor, noting unapproved species, etc.
Coordinate any substitution requests through RFC.
Submit submittals for seeding to Landscape Design for approval.
Coordinate source visits, material certifications, samples and quantity tracking and mixing of organic material into topsoil.
Layout
Schedule the plant layout with the contractor and Landscape Design, providing 1 week notice.
Review specifications, details, installation and staging of plantings with Landscape Design. Questions ?
Delivery, Handling & Storage
Check all root balls and containers to ensure they are moist upon arrival on site.
Check trunks and rootballs for damage, ensure they do not shift during handling .
Verify that the plantings are stored in a shady area and covered with mulch during staging.
Confirm that the plants are being watered to maintain optimum health in stockpile area.
Installation
Planting Pits
Confirm the contractor is measuring the depth of pit against the hieght of the root ball during excavation.
Review planting depth if the root flare is not visible due to excess soil over ball from B&B operations.
Confirm that the planting pit is twice the diameter of the root ball, with scarified sides to permit roots to move into the native soil.
Check plant pits for obstructions, asphalt, or standing water. Hold off on planting, alert Landscape design.
Verify that the soil below the required excavation depth remains undisturbed. If not, direct the contractor to add soil & tamp.
Re-measure plant pit to ensure it is 2" less than the hieght of the root ball before moving tree!
Setting Plants
Review soil to ensure it was mixed, and that organic material was incorporated as per specification.
If synthetic rope or other non-biodegradable material is present, it must be removed.
Observe that has the pit is half filled with planting mix and then well tamped around the ball to remove air pockets, which would cause shifting or settling.
Observe the pit being filled with water and allowed to drain.
Observe removal of rope, top of burlap, and excess soil so root flare is above finished grade.
Direct the contractor to bend down the top 1/3 of the wire basket, cut around the next tier of wire, and to remove the burlap from 1/3-1/2 of the ball, so roots can grow into surrounding soil.
Verify that the tree is straight and the pit filled with planting soil then tamped to remove air pockets.
Ensure that a 6" tall saucer is constructed around each tree trunk, capable of holding soaking water.
Mulching
Verify that the woodchip mulch been placed per contract details.
Ensure the mulch is left 2" away from tree trunk so no rotting occurs.
Ensure the base of all shrub stems are exposed to air so no rotting occurs.
Watering
Has water been applied at a controlled rate so that it percolates to the root zone of the tree?
Water injection or bags may be substituted at the discretion of the Engineer. This must be formally submitted and accepted.
Review the contractors schedule for watering, and determine how it will be tracked.
Staking and Guying
Stake and guy all trees per the standard details on sheet No. 949 or M949-1&2.
Other methods must be formally submitted and accepted prior to installation.
Semi-Final Inspection
Verify that all plants in the contract are installed.
Verify that any areas damaged by contractor are restored.
Transmit a copy of the this completed checklist to LDU.
Establishment Period and Punch List
Notify LDU 1 year after all plant material has been installed to schedule a final inventory.
Review the inventory of dead, dying and otherwise unacceptable plant material, and promptly notify the contractor to schedule replacement work and corrective measures.
Verify that all planting areas are free of weeds and all stakes and wires have been removed.
Notify the LDU that the project is ready for the final walk-thru.
Verify that all contract items are installed and living per the Contract.