## Sheet1
Date: |  |  | Project Plan
| TASK | [11 empty] | EXPECTED
TASK/ACTIVITY | OWNER(S) | PARTICIPANTS | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | RESULTS
|  | Color Code Key | Oct: ON Target; Nov: Struggling; Dec: NO Action; Jan: Future; Feb: Complete

## Sheet2
PLIS LEAN Project Plan October 2, 2013
| TASK | [7 empty] | A |  |  |  | EXPECTED
TASK/ACTIVITY | OWNER(S) | PARTICIPANTS | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | RESULTS
Great
Web Portal | Jolanta | IT, Marcus,Jen, Wendy | A Jul: Next year | Decrease number of steps and standardize content of complaint
E- licensing | Jolanta | IT, Steve Carragher | A Jul: Next year | Improve response time to petitioner
IT encryption of softward and policy on size of file | Marcus | IT, Jolanta, Jen | A Jul: Next year | Decrease investigation time and costs
Increase CMEB involvement earlier in process | Diane | CMEB, AG, Jeff, Jen | [10 empty] | Decrease time to complete an investigation from intake and referral to legal | bar: Mar to A Jun
Scanning resources secured | Marcus | Jen, Wendy | A Jul: Next year | Decrease cost and time of investigations
New contracting process with consultants | Rose Marie | Pam, Kathy, Jen | [10 empty] | Increased pool of consultants from 0 to xx | bar: Nov to Feb
Stardardize and implement record release to respondent as a precursor to standardizing scheduling respondent conference with ORLC | Linda | AG, Matt | [10 empty] | Decrease time to complete an investigation from intake and referral to legal | bar: Jan to A Apr
Clarification of FOIA, HIPAA, CGS section19a-14, allows release of case file to respondent during investigation | Diane | AG, Matt, Kathy | [10 empty] | Decrease time to complete an investigation from intake and referral to legal | bar: Jan to A Apr
*Proposal for statutory change to enable corrective action plan for MDs | David | Matt, Wendy, Jill | [10 empty] | Decrease the number of investigation files returned to PLIS from OLRC for dismissal | bar: A May to A Jul
Case management team of OLRC and PLIS to reduce layer or approval | David | Matt, Wendy, Jen | [10 empty] | Reduction in number of approvals from 3 to 2 and increase the quality of the final investigation product. | bar: Jan to A Jun
As part of credentialing process, physician on call to DPH to serve as consultant for x amount of time | [12 empty] | 1) Increase pool of consultants from 0 to 30 per year by July 2014. | bar: A May to A Jul
Explore opportunities to recoup expenses from disciplined physicians to go to a dedicated fund for PLIS | [12 empty] | Increase resources for purchase of consultant services | bar: A May to A Jul
|  | Color Code Key | Dec: ON Target; Jan: Struggling; Feb: NO Action; Mar: Future; A Apr: Complete