CT Commission on Nonprofit Health and Human Services

Process Outline – Working Draft

September 21, 2010

| Timeframe: |
| --- |
| Phase 1: Learn about/Gather Data - Establish Work Groups to Review Data - Achieving Administrative Efficiencies - Cost Comparisons – Private and State Services - Private Provider Costs Increases & Fiscal Fitness - Potential Cost Savings of Community-Based Care - Projected Costs of Service Delivery & Sources of Revenue - Develop Guiding Principles for Funding and Delivering State Supported Health & Human Services | Sept – Dec. |
| Phase 2: Analyze Data - Work Groups Present Findings to Commission - Commission Analyzes Data | Oct. – Dec. |
| Phase 3: Recommend - Explore new/improved Models/Approaches to Service: - Procurement - Monitoring - Delivery - Preliminary Report (Due Jan 1): - Summarize Commission’s Work-to-Date - Guiding Principles for Service Delivery - Recommend Ways to Achieve Administrative Efficiencies - Final Report (Due April 1): - Procurement Models - Summarize Commission’s Work - What’s working, - What’s not working - Recommendations for improvements - Recommended Next Steps | Dec. – March |