## Sheet1
Active DEEP Projects Requiring IT Funding
Project Title | Budget | FY 14 IT Investment Funding | LEAN/Business Requirements Complete | Scope Complete | Projected Contract Award | Notes
PURA e-Filing | 2800000 | 2300000 | Yes | Yes | Immediate | Vendor selected-Awaiting funds
Site CMS (Remediation) | 2500000 | 1900000 | Yes | Yes | 2013-11-01
EC Tournament Permits | 500000 | 400000 | Yes | Yes | 2013-09-15
Radiation DTX & RMI | 500000 | 400000 | Yes | Yes | 2013-10-01
Records Mgmt Admin | 500000 | 500000 | Yes | No | 2013-12-01
BEES | 800000 | 400000 | Yes | Yes | 2013-10-01
VOIP | 1000000 | 300000 | Yes | Yes | Immediate | Vendor selected-Awaiting funds
| 8600000 | 6200000
In order to execute contracts and issue purchase orders the Department will need $ 6.2M of State bond funding in FY 14. The above list projects cash flow requirements for the next three months. The Department prefers to maintain an aggressive schedule as phased funding will interrupt project development and may result in additional costs to the state. The Department appreciates the Committee's consideration and will realign the project schedules to preserve CY 13 bonding with hope of receiving the remaining FY 14 balance early in CY 14.