
Permit/Approval Status for the Use of Three TM2500s

Permit/ 

Compliance 

Permits
Required? Status

Air Quality

Requires Individual New Source Review Permit (1)
yes
Renewal

General Permit to Limit Potential to Emit (GPLPE)
no
N/A

Title V Operating Permit (2)
yes
Complete

NOx Reasonably Available Control Technology (RACT)
yes
Complete

NOx Clean Air Interstate Rule (CAIR) Source
yes
Complete

Acid Rain Program
no
N/A

Prevention of Significant Deterioration (PSD)
no
N/A

Maximum Achievable Control Technology (MACT)
no
N/A

Federal Non-Attainment New Source Review
no
N/A

Emissions Offsets
no
N/A

Water/Wastewater

CT DEP's General Permit for Stormwater and Dewatering from

Construction Activities

(DEP-PERD-GP-015)
yes
Complete CT DEP's General Permit for Stormwater Associated with Industrial

Activities

(DEP-PERD-GP-014)
yes
Complete

NPDES Individual Discharge Permit (Wastewater/Stormwater) (3)
no
N/A Rivers and Harbors Act Section 10/Clean Water Act Section 404

Permit
no
N/A

Clean Water Act Section 401 Water Quality Certification
no
N/A

Connecticut Groundwater Discharge Permit
no
N/A

Connecticut Pretreatment Wastewater Permit
no
N/A

Connecticut Wastewater Discharge Permit
no
N/A

Order of Conditions from Conservation Commission
no
N/A

Section 10/404 and 401 Water Quality Certifications
no
N/A

Siting Council

Approval Required
yes
To be filed

Threatened and Endangered Species (4)
no
Complete

Historic (5)
no
Complete

CT DPUC (if electric lines will be added) (6)
no
Complete

Stack Height

FAA Approval
no
N/A

Permit/

Compliance 

Permits
Required? Status 
NEPOOL

Section 1.3.9 ISO New England Transmission, Markets and Services

Tariff Approval (7)
yes
Complete

Local

Requires

Special Exception Permit
yes
Extension

Soil Erosion and Sediment Control Plan [do we need to refile?
yes
Complete

Building Permit [do we need a new permit for the tanks?]
yes
Complete

(1) Individual New Source Review Permits expire on July 7, 2009. These permits will be renewed prior to their expiration date.  Permit renewals were submitted to the DEP on November 16, 2007.
(2) The Title V Operating Permit expires on June 9, 2011. A renewal application will be submitted prior to the expiration date. The facility can operate while the Title V Permit is being renewed.

(3) 316(b) of the Clean Water Act for water intake.

(4) In a letter dated January 7, 2004, the Connecticut DEP Biologist/Environmental Analyst indicated that "I have reviewed Natural Diversity Data Base maps and files regarding the area delineated on the map you provided and listed above. According to our information, there are no known extant populations of Federal or State Endangered, Threatened or Special Concern Species that occur at the site in question."

(5) No existing historic structures are located on the site or in its immediate vicinity. Due to the limited size/height of the Project units, the Project will not impact the potentially historic structures in the broader Waterside and South End sections of Stamford. Because the soil has been disturbed by prior construction, it is highly unlikely that any archeological resources exist at the site and none were found during installation. A Phase IA cultural resource survey was conducted for the Project site and no evidence of cultural resources was found during the site walkover.

(6) The Connecticut Department of Public Utility Control ("DPUC") regulations of transmission lines at 16-11-137 provide that "No electric line, the nominal voltage of which is to exceed twenty thousand volts to ground, shall be constructed without prior commission approval of the manner and method of construction."

(7) As of February 1, 2005, NEPOOL 18.4 has been replaced by Section 1.3.9 of the ISO New England Transmission, Markets and Services Tariff. ISO New England's Planning Procedure 5-1 sets out the Procedure for Review of Governance of Participant's Proposed Plans. Section 2.3 of Planning Procedure 5-1 states that Proposed Plan Applications are required for new generation or changes in net station output of 5 MW or more.







Page 1 of 2











PAGE  
38
758045_4

