## Mulnite Schedule
FIGURE_ - BOOM BRIDGE SOLAR - DRAFT PROJECT SCHEDULE | Duration | Start Date | Completion Date
STAGE 0 - Origination
Site Control Finalized | 6 months | 2019-11-15 | 2020-05-15
Delivery term start date | 1 day | 2021-04-01 | 2021-04-01
Extension Terms (two, 6-mo.) | 12 mos. | 2021-04-02 | 2022-04-01
Engineering for Interconnection Application | 2 weeks | 2019-05-24 | 2019-06-07
Prelim layout, design and equipment selection | 2 weeks | 2019-05-24 | 2019-06-07
STAGE 1 - Phase 1 Development
Preliminary Engineering and survey work | 5-6 weeks | 2019-09-20 | 2019-10-25
10 % electrical design | 2 weeks | 2019-05-24 | 2019-06-07
10 % civil design | 30 days | 2019-11-30 | 2019-12-31
Submit Interconnection applications | 3-5 days | 2019-06-03 | 2019-06-07
Utility initial review | 90 days | 2019-06-10 | 2019-09-10
STAGE 2 - Phase 2 Development
Coordination with Town Officials | 8 months | 2020-01-08 | 2020-08-08
Communication w/ Neighbors-Abutters | 8-12 weeks | 2020-03-10 | 2020-06-01
Coordination with State Regulatory Agencies | 6-9 mos. | 2019-09-19 | 2020-06-19
CTDEEP Stormwater Coordination | 4-6 weeks | 2020-05-05 | 2020-06-09
CTDEEP - Stormwater Permitting Coordination | 90 days | 2020-06-10 | 2020-09-10
CT Siting Council Petition/Permitting Process | 4 - 5 mos. | 2020-06-10 | 2020-11-10
Interconnection Impact Study | 12-14 weeks | 2020-01-13 | 2020-04-17
GCE Received Facility Study Agreement | 1 day | 2020-05-01 | 2020-05-01
GCE Execute Facility Study Agreement | 8 weeks | 2020-05-04 | 2020-06-26
Eversource Performs Facility Study | 75 days | 2020-06-29 | 2020-09-11
Draft Interconnection Agreements received | 2 weeks | 2020-09-14 | 2020-09-25
Interconnection Agreements signed/executed by GCE | 2 -4 weeks | 2020-09-28 | 2020-10-23
STAGE 3 - Final Development
Siting Council Approval | 1 mo. | 2020-10-10 | 2020-11-10
DEEP Stormwater Permit Approval | 12 weeks | 2020-06-12 | 2020-09-04
Interconnection Agreements fully executed by Eversource | 2-4 weeks | 2020-10-26 | 2020-11-20
STAGE 4 - Final Engineering & Construction
100% Design | 4-6 weeks | Wed 11/11/2020 | Tues 12/22/2020
Building Permits | 30 days | Wed 12/23/2020 | Tues 1/26/2021
Site Preparation/Set-up | 10 days | Mon 3/1/2021 | Fri 3/12/2021
Civil Work | 30 days | Mon 3/15/2021 | Fri 4/23/2021
Array Installation | 90 days | Mon 4/26/2021 | Fri 8/20/2021
Electrical Installation | 60 days | Mon 8/23/2021 | Fri 11/12/2021
Commissioning | 10 days | Mon 11/15/2021 | Fri 11/26/2021
Permission to Operate | 2 days | Mon 11/29/2021 | Wed 12/1/2021