| Date: | PROJECT MANAGER: Insert Date |
| --- | --- |
| To: | DAS/CS QBS Unit (DAS.CS.RFQ@ct.gov) |
| From: | PROJECT MANAGER: Insert Your Name |
| Contract Number: | PROJECT MANAGER: Discuss with QBS Unit |
| Project Title: | PROJECT MANAGER: Insert Project Title |
| Project Location: | PROJECT MANAGER: Insert Project Location |
| Selection Type: | CMR Best Value Based Selection RFQ |

| 1.0 | CMR Screening Shortlist Rating Point System: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Standard Rating Points: The CMR Screening Shortlist Rating Criteria Categories have Standard Rating Points as indicated in the table below. |  |  |  |  |  |  |
| 1.2 | Adjusted Rating Points: DAS/CS Project Manager (PM): The Standard Rating Points for CMR Screening Shortlist Rating Criteria Categories are allowed to be adjusted only if the following conditions are met: |  |  |  |  |  |  |
|  |  |  | 1.2.1 | The Contract is for services of an unusual nature. |  |  |  |
|  |  |  | 1.2.2 | The PM for the project must complete the Adjusted Rating Points. |  |  |  |
|  |  |  | 1.2.3 | The Adjusted Rating Points must be approved (in writing) by the DAS/CS Assistant Director of Project Management (ADPM) for the project, the Director of Project Management (DPM), the DAS/CS Chief Architect, and the DAS/CS Chief Legal Officer (see page 3). |  |  |  |
|  |  |  | 1.2.4 | The Approved Adjusted Rating Points must be within the Allowable Point Range (as indicated in the table below) and must total 100 points exactly. |  |  |  |
| Criteria Number |  | CMR Screening Shortlist Rating Criteria Categories |  |  | # Standard Rating Points | # Allowable Point Range | # Adjusted Rating Points |
| 1 |  | Experience with Work of Similar Size and Scope as Required by this Contract |  |  | 35 | 35-45 | PM: Insert Points |
| 2 |  | Organizational / Team Structure for this Contract |  |  | 30 | 25-35 | PM: Insert Points |
| 3 |  | Past Performance Data |  |  | 20 | 20 (Not Adjustable) | 20 (Not Adjustable) |
| 4 |  | Partnering Experience |  |  | 15 | 10-20 | PM: Insert Points |
| Maximum Total Points Per Screening Shortlist Panel Member: |  |  |  |  | 100 | 100 | 100 |

| 2.0 |  | CMR Selection Interview Rating Point System: |  |  |
| --- | --- | --- | --- | --- |
| 2.1 |  | Standard Rating Points: The CMR Selection Interview - Qualitative Rating Criteria Categories have Standard Rating Points as indicated in the table below. |  |  |
| Criteria Number |  | CMR Selection Interview - Qualitative Rating Criteria Categories | Standard Rating Points |  |
| 1 |  | Experience | 10 |  |
| 2 |  | Project Organization, Personnel Experience, and Qualifications | 30 |  |
| 3 |  | Project Approach, Preliminary Project Plan, and BIM Utilization Plan | 20 |  |
| 4 |  | Past Performance on CMR projects, GC Projects, or Other Relevant Performance Data | 15 |  |
| 5 |  | Schedule Performance | 15 |  |
| 6 |  | Safety Record | 10 |  |
| Maximum Total Points Available Per CMR Selection Interview Panel Member: |  |  | 100 |  |

| 3.0 | State Construction Services Selection Panel Members: |  |
| --- | --- | --- |
|  | In accordance with the Connecticut General Statutes (C.G.S.) Section 4b-56, the following DAS/CS Panel Member(s) and Observer(s) have been appointed for this CMR Services Selection. The following Agency Panel Member(s) and Observer(s) have been appointed by the User Agency head. All DAS/CS and Agency Panel Members shall attend both the Shortlisting/Screening Meeting and Selection/Interview Meeting. Observers are not required but can attend the Selection/Interview Meeting. |  |
|  | PM INSTRUCTIONS FOR DETERMINING DAS/CS PANEL MEMBERS: Discuss with ADPM, who will discuss with DPM and Chief Architect: |  |
|  | .1 | DAS/CS Panel Chair: Chief Architect or Director of Project Management (DPM). |
|  | .2 | DAS/CS Panel Member: DPM or ADPM. |
|  | .3 | DAS/CS Panel Member: ADPM or PM. |
|  | .4 | DAS/CS Panel Member: [To be selected by DPM in consultation with Chief Architect]. |

| DAS/CS Panel Members (Total Number of DAS/CS Panel Members: Major Project: four; Minor Project: two; CHEFA Project: three) |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1. | Panel Chair: | Insert Chief Architect or DPM Name | Email Address: | Insert Email Address |
|  | Title: | Insert Title |  |  |
| 2. | Panel Member: | Insert DPM or ADPM Name | Email Address: | Insert Email Address |
|  | Title: | Insert Title |  |  |
| 3. | Panel Member: | Insert ADPM or PM Name | Email Address: | Insert Email Address |
|  | Title: | Insert Title |  |  |
| 4. | Panel Member: | Insert PM or Panel Member Name | Email Address: | Insert Email Address |
|  | Title: | Insert Title |  |  |
| Agency Panel Members (Total Number of Agency Panel Members: Major Project: one; Minor Project: one; CHEFA Project: two) |  |  |  |  |
| 1. | Panel Member: | Insert Agency Panel Member Name (typically the Agency PM on 1105) | Email Address: | Insert Email Address |
|  | Title: | Insert Title |  |  |
| (Use Below For CSCU CHEFA Projects Only) |  |  |  |  |
| 2. | Panel Member: | Insert Agency Panel Member Name | Email Address: | Insert Email Address |
|  | Title: | Insert Title |  |  |
| Observer(s) (Non-Voting Member; recommended limit of two per Agency; must sign 1261 Observer Certification and 1761 CMR Selection Observer Certification) |  |  |  |  |
| 1. | Observer Name: | Insert Observer Name | Email Address: | Insert Email Address |
|  | Title: | Insert Title |  |  |
| 2. | Observer Name: | Insert Observer Name | Email Address: | Insert Email Address |
|  | Title: | Insert Title |  |  |
| 3. | Observer Name: | Insert Observer Name | Email Address: | Insert Email Address |
|  | Title: | Insert Title |  |  |
| 4. | Observer Name: | Insert Observer Name | Email Address: | Insert Email Address |
|  | Title: | Insert Title |  |  |

| 4.0 | CMR Milestone Schedule: PM INSTRUCTIONS: Meet with QBS Unit to discuss dates and times. |
| --- | --- |
|  | IMPORTANT: PM must confirm and schedule meeting dates and times highlighted below in Outlook BEFORE sending this 1701 CMR RFQ Web Advertisement Transmittal for signature. |

| RFQ Web Advertisement Date on CTsource: |  |  | Date: See QBS Unit | Time: See QBS Unit |
| --- | --- | --- | --- | --- |
| QBS Submittal Booklets Due Date on CTsource: |  |  | Date: See QBS Unit | Time: See QBS Unit |
| Shortlisting/Screening Meeting for Panelists: |  |  | Date: See QBS Unit | Time: See QBS Unit |
| RFP Invitation Letter sent to Shortlisted Firms & 00 11 19.2 Notice of RFP for CMR Services: |  |  | Date: See QBS Unit | Time: Not Applicable |
| RFP Web Advertisement Date on CTsource for Shortlisted Firms Only: |  |  | Date: See QBS Unit | Time: See QBS Unit |
| Site Visit Meeting with Shortlisted Firms: |  |  | Date: See QBS Unit | Time: See QBS Unit |
|  | Location: | PM INSERT |  |  |
|  | Parking Instructions: | PM INSERT |  |  |
| Last Date for Shortlisted Firms to Submit RFP Questions to DAS: |  |  | Date: See QBS Unit | Time: Not Applicable |
| RFP Due Date on CTsource: |  |  | Date: See QBS Unit | Time: See QBS Unit |
| CMR Technical Proposal Review Meeting for Panelists: |  |  | Date: See QBS Unit | Time: See QBS Unit |
| Selection/Interview Meeting with Shortlisted Firms: |  |  | Date: See QBS Unit | Time: See QBS Unit |
| CMR Price Proposal opens on CTsource: |  |  | Date: See QBS Unit | Time: See QBS Unit |
| CMR Price Proposal Review Meeting for DAS: |  |  | Date: See QBS Unit | Time: See QBS Unit |
| CMR “Best Value” Firm Notification sent to "Best Value" Firm: |  |  | Date: See QBS Unit | Time: Not Applicable |
| Scope Review Meeting with Apparent “Best Value” Firm |  |  | Date: See QBS Unit | Time: See QBS Unit |
| Conditional Selection Letter Sent to Selected Firm |  |  | Date: See QBS Unit | Time: Not Applicable |
| Notice to Proceed to Preconstruction Services Sent to CMR: |  |  | Date: See QBS Unit | (sent 63 days after Selection) |
| 100% Pre-Design Study Available to CMR: |  |  | Date: See QBS Unit | (same day as above) |
| 50% Schematic Design Documents Available to CMR: |  |  | Date: See QBS Unit | (sent 58 days NTP) |
| 100% Schematic Design Documents Available to CMR: |  |  | Date: See QBS Unit | (sent 46 days after 50% SD) |
| 50% Design Development Documents Available to CMR: |  |  | Date: See QBS Unit | (sent 73 days after 100% SD) |
| 100% Design Development Documents Available to CMR: |  |  | Date: See QBS Unit | (sent 45 days after 50% DD) |
| 50% Construction Documents Available to CMR: |  |  | Date: See QBS Unit | (sent 88 days after 100% DD) |
| 100% Construction Documents Available to CMR: |  |  | Date: See QBS Unit | (sent 65 days after 50% CD) |
| Reconciliation Meeting: |  |  | Date: See QBS Unit | (scheduled 2 days after 100% CD) |
| Revise Contract Documents: |  |  | Date: See QBS Unit | (finished 45 days after meeting) |
| CMR Trade Bid Packages out to Bid: |  |  | Date: See QBS Unit | (out to bid 31 days after revisions) |
| CMR Receives Trade Bid Packages Back: |  |  | Date: See QBS Unit | (bidding time 42 days [6 weeks]) |
| Trade Bid Packages Review: |  |  | Date: See QBS Unit | (24 days to review trade bids) |
| CMR GMP Proposal Submittal Date: |  |  | Date: See QBS Unit | (36 days to submit GMP; [24+36=60]) |
| CMR GMP Agreement Award and NTP to Construction: |  |  | Date: See QBS Unit | (74 days to review/negotiate GMP) |
| Construction Start Date: |  |  | Date: See QBS Unit | (estimated 5 days after NTP) |
| Substantial Completion Date: |  |  | Date: See QBS Unit | (construction phase) |
| Acceptance of the Work Date: |  |  | Date: See QBS Unit | (90 days after Sub. Completion) |

| 5.0 | Reference Documents: (examples include studies, master plans, etc.). The following Reference Documents will be made available to firms as follows: |
| --- | --- |
|  | PM INSTRUCTIONS: List all available Reference Documents FOR FIRMS below (if none, state “None”). IMPORTANT: PM must determine (1) which documents can be shared with ALL Firms, and (2) which documents can be shared ONLY with Shortlisted Firms. |
| 5.1 Reference Documents to Share With ALL Firms (Included with RFQ Web Advertisement): |  |  |
| - PM: Insert List of Documents. - PM: Email Documents (or Send Shared Link) to QBS Unit at DAS.CS.RFQ@ct.gov |  |  |
| 5.2 Reference Document(s) to Share ONLY With Shortlisted Firms (Included with Shortlist Notification): |  |  |
| - PM: Insert List of Documents. - PM: Email Documents (or Send Shared Link) to QBS Unit at DAS.CS.RFQ@ct.gov |  |  |

| Signatures Required FOr All CMR RFQ WEB ADVERTISEMENT APPROVALS (INCLUDING ADJUSTED RATING POINTS): |  |  |  |  |
| --- | --- | --- | --- | --- |
| Insert PM Name |  |  |  |  |
| (Print PM Name) |  | (PM Signature) |  | - (Date) |
| Insert ADPM Name |  |  |  |  |
| (Print Project’s ADPM Name) |  | (Project’s ADPM Signature) |  | - (Date) |
| Insert DPM Name |  |  |  |  |
| (Print DAS/CS DPM Name) |  | (DAS/CS DPM Signature) |  | - (Date) |
| Insert Chief Architect Name |  |  |  |  |
| (Print DAS/CS Chief Architect Name) |  | (DAS/CS Chief Architect Signature) |  | - (Date) |
| Insert Chief Legal Officer Name |  |  |  |  |
| (Print DAS/CS Chief Legal Officer Name) |  | (DAS/CS Chief Legal Officer Signature) |  | - (Date) |

| DAS/CS Project Manager: Send the following documents to DAS.CS.RFQ@ct.gov: |  |
| --- | --- |
| 1. | 1105 Capital Project Initiation Request: PDF document (completed, approved, and signed). |
| 2. | 1700 CMR RFQ Web Advertisement: Word document (completed). |
| 3. | 1701 CMR RFQ Web Advertisement Transmittal (this document): Word document (completed). |
| 4. | 1701 CMR RFQ Web Advertisement Transmittal (this document): PDF document (completed and signed). |

| cc: | DAS Deputy Commissioner: | D. Hobbs | DAS/CS ADPM for Project: | PM: Insert Name |
| --- | --- | --- | --- | --- |
|  | DAS/CS Chief Legal Officer: | J. Padula | DAS/CS Project Manager: | PM: Insert Name |
|  | DAS/CS Chief Architect: | D. Barkin | DAS/CS Panel Member: | PM: Insert Name |
|  | DAS/CS Director of Project Management: | P. Simmons | Agency Panel Member: | PM: Insert Name |
|  | DAS/CS Director of Support Services: | C. Russell | File: | PM: Insert Project Number |
|  | DAS/CS QBS Unit: | R. Cutler / G. Fehrs / T. Wargo |  |  |
|  | DAS/CS Legal Affairs: | R. Tamborra / A. Buzzard / C. Phelps / T. Keating |  |  |
|  | Observers and Others: | PM: Insert Name(s) |  |  |