## Slide 1
Executive Board Meeting
November 24, 2020

## Slide 2: Agenda
Welcome and introductions
2021 Calendar Approval
SLDS grant timeline
  Legal agreements
  Research planning
  Technical upgrade
CREATES overview and discussion
Prioritized Research Agenda Review

## Slide 3: Agenda
Welcome and introductions
2021 Calendar Approval
SLDS grant timeline
  Legal agreements
  Research planning
  Technical upgrade
CREATES overview and discussion
Prioritized Research Agenda Review

## Slide 4: Agenda
Welcome and introductions
2021 Calendar Approval
SLDS grant timeline
  Legal agreements
  Research planning
  Technical upgrade
CREATES overview and discussion
Prioritized Research Agenda Review

## Slide 5: Agenda
Welcome and introductions
2021 Calendar Approval
SLDS grant timeline
  Legal agreements
  Research planning
  Technical upgrade
CREATES overview and discussion
Prioritized Research Agenda Review

## Slide 6: P20 WIN Vision
P20 WIN informs sound policies and practice through the secure sharing of critical longitudinal data across the participating agencies to ensure that individuals successfully navigate supportive services and educational pathways into the workforce.
  Agreed upon by Executive Board in June 2020

## Slide 7: SLDS Grant – Connecticut Deliverables
Add Data Sources: OHE, DCF, DSS and CCEH
Build and Sustain Analytic Capacity
Boost Data Matching
Produce Research & Corresponding Data tools
  5+ research projects, data tools and communication

## Slide 8
Kentucky Education and Workforce Reporting System

## Slide 9: Original SLDS Grant timeline – Major activities
Quarter / Activity | Q3 2020 | Q4 2020 | Q1 2021 | Q2 2021 | Q3 2021 | Q4 2021 | Q1 2022 | Q2 2022 | Q3 2022 | Q4 2022 | Q1 2023 | Q2 2023 | Q3 2023 | Q4 2023 | Q1 2024
Onboarding new agencies |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sustainability plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Hiring analytical / technical staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Technical upgrade |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Predictive models |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Students at lowest levels of readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Financial aid |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Workforce training |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Barriers to success |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 10: Revised SLDS Grant timeline – Major activities
Quarter / Activity | Q3 2020 | Q4 2020 | Q1 2021 | Q2 2021 | Q3 2021 | Q4 2021 | Q1 2022 | Q2 2022 | Q3 2022 | Q4 2022 | Q1 2023 | Q2 2023 | Q3 2023 | Q4 2023 | Q1 2024
Onboarding new agencies |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Research planning groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Build analytic capacity |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Technical upgrade planning group |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Build technical capacity |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
College and career readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Workforce training |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Student readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Financial aid |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Barriers to success |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sustainability plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Identify hiring needs
Identify hiring / resource needs
Align with IT optimization, CREATES timing

## Slide 11: Agenda
Welcome and introductions
2021 Calendar Approval
SLDS grant timeline
  Legal agreements
  Research planning
  Technical upgrade
CREATES overview and discussion
Prioritized Research Agenda Review

## Slide 12: Agenda
Welcome and introductions
2021 Calendar Approval
SLDS grant timeline
  Legal agreements
  Research planning
  Technical upgrade
CREATES overview and discussion
Prioritized Research Agenda Review