## Partners
CT SWAP Communication and Engagement Action Tracker
need to add "annually" to many of these and emphasize need for regular outreach
For CT SWAP Revision Period 2024-2025+ (with an eye toward implementation)
Conservation focused existing or potential partners
Goal 1: Increased active engagement of conservation organizations and agencies
Objective 1.1 |  | Increase awareness and interest in CT SWAP by initiating strategically timed, periodic communication targeted at assisting conservation partners in identifying and assuming a role in the CT SWAP revision and implementation | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Lead* | Sequence**
Action | 1.1.1 | Make the conservation partner list (List) accessible to all members of the CT SWAP Team and ask the Team for contributions of contacts; continue to stratgically expand the List (e.g., to partners with implementation capacity, large networks). |  |  |  | CT SWAP Core Team | 1a
| 1.1.2 | Develop a schedule for periodic email newsletters to be sent to partners on the List with an ultimate focus of building an implementation network; continue consistent communication into implementation. |  |  |  | CT SWAP Core Team | 1a
| 1.1.3 | Using the newsletter, CT DEEP websites and other channels, recruit key existing partners to share their SWAP implementation stories (use open-ended responses to survey to help find stories) and other SWAP related newsworthy items; share stories (successes and failures) through a variety of communication channels. |  |  |  | DEEP Comms Staff | 1b
| 1.1.4 | Make a direct ask of all conservation partners on the List to use their connections and diverse communications expertise to assist the CT SWAP Team professionals; request that they report back (provide a short form with the request) to help track extent of outreach. |  |  |  | Advisory Team | 1b
| 1.1.5 | Ask each SWAP technical team to make a draft list of top 5-10 priorities for collaborative conservation actions (e.g., research, education, restoration) and why each is a priority and share with subject matter experts for input and help fill data gaps. |  |  |  | CT SWAP Core Team | 1b
| 1.1.6 | Target 10 specific high priority groups (e.g., university and agency scientists, NGOs, nature centers, municipalities) and share relevant information with them (e.g., draft lists, priority actions, potential opportunities for collaboration with them) consistently and in a timely manner; as part of communication with these groups, provide specific opportunities for them to engage (e.g., collaborate) or otherwise provide feedback (e.g., use short, targeted surveys and ways to connect with appropriate CT DEEP staff to explore options). |  |  |  | CT SWAP Core Team | 2
Objective 1.2 |  | Enhance existing and build new relationshps with key conservation organizations necessary to achieve conservation outcomes for SGCN | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Lead | Sequence
Action | 1.2.1 | Using the List as a resource, identify a prioritized list of 10-20 conservation organizations that are key to successful SWAP implementation (e.g., have large memberships, access to needed capacity) and commit to focused engagement with them during the revision (and beyond). |  |  |  | Advisory Team | 1a
| 1.2.2 | Reach out to leaders of key conservation organizations identified above (3-5/Advisory Team member) to shedule one-on-one meetings (in-person as possible) with them to initiate discussions aimed at understanding their interests, introduce the SWAP, identify areas of shared interest and potential collaboration and opportunities to connect their memberships with the SWAP. Track contacts and have a specific plans for following up with them; co-identify opportunities for meaningful partner contributions throughout the revision process and beyond. |  |  |  | Advisory Team | 1b
| 1.2.3 | Seek opportunities to actively participate (e.g., have a SWAP booth, make a presentation, lead a session) in 4-8 key conservation organization events (i.e., those with broad reach such as CACIWC, CLCC) to continue to build relationships, share information and initiate discussion about the SWAP with members. |  |  |  | Advisory Team | 1c
Objective 1.3 |  | Ensure that the revised CT SWAP includes clear and specific goals, objectives, actions and ways partners can contribute and share information |  |  |  | Lead | Sequence
Action | 1.3.1 | Focus messaging on key partners' specific interests and ways specific types of partners and their members (e.g., land trusts, outdoor recreation groups) can contribute to the CT SWAP revision and implementation; provide a variety of options that include ways smaller entities can contribute; distribute through the partner list directly, encourage sharing with their members and followers through partner channels. Use effective and easily sharable methods (e.g., electronic fact sheets, videos). |  |  |  | DEEP Comms Staff | 1a
| 1.3.2 | As part of the revision process, develop goals, objectives and actions with input from conservation partners, including ways that specific categories of partners can contribute to implementing actions; share with key partners. |  |  |  | CT SWAP Team | 1b
| 1.3.3 | Develop and provide Best Management Practices and other relevant guidance to key partners (e.g., land trusts and municipalities) regarding ways to contribute to implementing the SWAP (e.g., managing lands to benefit SGCN). |  |  |  | CT SWAP Team | 2
| 1.3.4 | Ensure regular (bi-annual) communication to partners related to the Conservaiton Action Tracker as a way to continue to engage and update them as well as remind partners to contribute to the tool and use it. |  |  |  | CT SWAP Team | 3
| 1.3.5 | Develop an online system to encourage and support data centralization and sharing among conservation partners. |  |  |  | CT SWAP Team | 3
Objective 1.4 |  | Create collaborative opportunities for conservation partners related to their shared interest in CT's SWAP | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Lead | Sequence
Action | 1.4.1 | Using the opportunity to inform CT SWAP revision as an incentive, hold a partners workshop (have a CT SWAPworkshop/session at CT Conference on Natural Resources) to encourage dialogue among partners and gather input for the revision as well as build the foundation for an ongoing CT SWAP implementation network. |  |  |  | CT SWAP Core Team | 2
| 1.4.2 | Set the expectation and create a communication platform for the CT SWAP implementation network to share project outputs and outcomes, ideas for future projects, opportunities for collaboration, capacity needs, etc. related to CT SWAP implementation. |  |  |  | CT SWAP Team | 2
| 1.4.3 | Identify and promote collaboration within existing programs (UConn Natural Resources Conservation Academy) and networks (Cooperative Extension, CLCC, COEEA) to advance conservation outcomes for CT's SGCN. |  |  |  | CT SWAP Team | 2
Objective 1.5 |  | Use partners' input and capacity to identify and co-create 1-5 products (e.g., information, tools, grahics) to be updated, added to or used to support the 2025 SWAP | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Lead | Sequence
Action | 1.5.1 | Identify 1-5 highest prioriy products suggested by partners as needing to be updated or added to the 2025 CT SWAP (see survey data for specific ideas as a starting point). |  |  |  | CT SWAP Team | 1
| 1.5.2 | Ask 10-20 partners to beta test the Conservation Action Tracker to help assess its utility and work out potential issues. |  |  |  | CT SWAP Team | 1
| 1.5.3 | Ask 10-20 partners to beta test planned online functions (e.g., accessibility of maps or other spatial information, filtering capacity, etc..see survey results) of the revised SWAP. |  |  |  | CT SWAP Core Team | 2
| 1.5.4 | Work with internal and external subject-matter experts (e.g., CT DEEP Municipal Liaison, CAT consultant) to ensure data collection tools are scalable (link local to larger scale actions). |  |  |  | CT SWAP Core Team | 2
| 1.5.5 | Identify 1-5 partner-identified needs for Best Management Practices (e.g., vegetation management, invasive species control) and co-produce them with appropriate partners (end-users). |  |  |  | CT SWAP Team | 3
Potential partners (organizations/agenices not conservation focused but conservation related/interested)
Goal 2: Increased understanding of potential partners' interests and connection of those interests to appropriate topics in the CT SWAP
Objective 2.1 |  | Increased awareness of potential partners' interests and idenfication of potential common interests related to CT's SWAP |  |  |  | Lead | Sequence
Action | 2.1.1 | Identify 10-20 potential partner organizations (including novel partners) that could make a significant contribution to the CT SWAP revision and implementation (build on interview--SWAP and relevancy--and survey data). |  |  |  | Advisory Team | 1a
| 2.1.2 | Make genuine efforts to listen and learn about 10-20 potential partners' interests (e.g., community gardening, menthal and physical health) and find mutually beneficial ways to make connections between CT's SWAP and those interests. |  |  |  | CT SWAP Team | 1b
| 2.1.3 | Request potential partners who are trusted sources of credible information (e.g., AEE, community groups, extension, watershead groups) to be a face of SWAP communication and conduit for information among their membershps/constituencies. |  |  |  | Advisory Team | 1c
| 2.1.4 | Reach out to leaders of 10-20 potential partner organizations identified above (3-5/Advisory Team member) to shedule one-on-one meetings (in-person as possible) with them to learn about their interests and needs and potential connections between their interests and CT SWAP. Identify areas of shared interest and potential collaboration and opportunities to connect their memberships with the SWAP. Use personal connections and/or the interviews and survey list. Track contacts and have a specific plan for following up with them. |  |  |  | Advisory Team | 2
| 2.1.5 | Identify 4-8 potential partner events to support and attend to increase awareness and provide targeted information and tools most relevant to the interests of those attending the particular event. |  |  |  | Advisory Team | 2
Goal 3: Increased active engagement of potential partners
Objective 3.1 |  | Provide pathways and incentives for potential partners to contribute to SWAP implementation |  |  |  | Lead | Sequence
Action | 3.1.1 | CT DEEP keeps an updated website with a calendar of SWAP-related events and opportunities to provide feedback, continue throughout the lifetime of the SWAP (e.g. natural events and projects occurring during those times to keep folks interested all times of the year [using SWAP targets]; encourae people to provide input on specific and timely information throught the life of the revision and beyond). |  |  |  | CT Core Team | 1a
| 3.1.2 | Ensure relevant SWAP-related information is accessible to potential partners (e.g., easy to find, communicated clearly and in plain language, translated into different languages as appropriate depending on the target audience). |  |  |  | DEEP Comms Team | 1b
| 3.1.3 | Building on information about key potential partners' interests in common with CT's SWAP priorities (e.g., habitat conservation/management), identify and communicate specific options for contributing to SWAP implementation for a large and smaller organizations. |  |  |  | CT SWAP Team | 2
| 3.1.4 | Provide training/professional development to interested key partners (e.g., school districts, nature centers) to increase knowledge about the SWAP and promote use and implementation (e.g., hands-on skills) of the SWAP specific to their organization/agency interests. |  |  |  | CT SWAP Team | 3
| 3.1.5 | Work with DEEP educators and Diversity Program to develop lesson plans and customize to include include SWAP information in Project WILD for CT schools, day cares, nature centers, after school programs, and indoor/outdoor activities. |  |  |  | CT SWAP Core Team | 3
| 3.1.6 | Highlight partners' SWAP-related contribution consistently in outreach materials and reward stellar contributions (e.g., Green Circle Awards). |  |  |  | DEEP Comms Team | 3
| 3.1.7 | Invite interested potential partners to participate in SWAP-related projects (e.g., citizen science, habitat restoration. Community gardens). |  |  |  | CT SWAP Team | 3
| 3.1.8 | As possible, provide resources or make connections (e.g., to conservation organizations) to assist partners in contributing to SWAP implementation (e.g., providing materials, supplies, training, expertise) to facilitate participation. |  |  |  | CT SWAP Team | 3
| 3.1.9 | Provide training/professional development to interested key partners (e.g., school districts, nature centers) to increase knowledge about the SWAP and promote use and implementation (e.g., hands-on skills) of the SWAP specific to their organization/agency |  |  |  | CT SWAP Team | 3
CT SWAP Team (in-reach)
Goal 4: | Increased internal-agency awareness engagement and support for the CT SWAP***
Objective 4.1 |  | Improved intra-agency communication and enagement related to CT's SWAP |  |  |  | Lead | Sequence
Action | 4.1.1 | Enhance communication within CT DEEP related to CT's SWAP revision (e.g., for CT DEEP establish channels of communication in each division, bureau and opportunities to include SWAP/story maps, etc.). |  |  |  | CT SWAP Core Team | 1a
| 4.1.2 | Ensure all external outreach materials are shared within relevant CT DEEP staff. |  |  |  | CT SWAP Core Team | 1a
| 4.1.3 | Ensure that high-level managers and decision makers within CT DEEP (e.g., Bureau chiefs, Commissioner) are informed about and ideally engages in/supports the CT SWAP revision and implementation. |  |  |  | CT SWAP Core Team | 1a
| 4.1.4 | Find capacity to coordinate outreach and partner engagement for CT SWAP (after consulting team contract is over). For example, establish a standing CT SWAP outreach subgroup to support communication and engagement related to CT's SWAP. Solicit participation from conservation partners. |  |  |  | CT SWAP Core Team | 2
Objective 4.2 |  | Ensure efficient use of existing agency/institutional resources and capcities by CT SWAP Team |  |  |  | Lead | Sequence
Action | 4.2.1 | Utilize existing agency expertise and capacity and connections to assit in engaging with existing and potential partners and promoting CT's SWAP. |  |  |  | CT SWAP Core Team | 1
*1. CT SWAP Core Team: Wildlife Diversity Coordinator, UConn, TCI 2. CT SWAP Advisory Team: #1 above plus additional CT DEEP staff 3. CT DEEP Communications staff: Select CT DEEP communications professionals 4. Taxa teams: All the subject matter expert teams participating in the SWAP revision 5. CT SWAP Team: This includes 1,2, 3 and 4 above plus any additional individuals from within DEEP, UConn or other that will have an active role in the 2025 revision (and likely implementation).
**1=ASAP, most urgent, other actions depend on, should be initiated in 2024 2=Urgent but can/needs to wait until higher priority actions occur, should be initiated by late 2024 or early 2025 3=It can/needs to wait until second half of 2025 or post finalization of the plan
***Increased intra-agency/institution regarding CT's SWAP is likely needed within other cooperating entities as well, so these actions may apply.
Note on L3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: need to add "annually" to many of these and emphasize need for regular outreach