## Public
CT SWAP Public Outreach Communication and Engagement Strategy
For CT SWAP Revision Period 2024-2025+ (with an eye toward implementation)
Goal 1: Increased awareness of CT SWAP by the CT general public
Objective 1 |  | Increase awareness of (and interest in) CT SWAP by developing strategically timed, regular communication targeted at increasing awareness of the CT SWAP revision and implementation | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Lead* | Sequence**
Action | 1.1.1 | Inventory/research/list available communication mechanisms available thru DEEP and beyond to reach the public. Assess and prioritize for relevancy and use. |  |  |  | CT SWAP Core Team | 1a
| 1.1.2 | Develop a schedule for periodic communications to be sent/posted for public consumption with an ultimate focus of building an awareness and interest; continue consistent communication into implementation. |  |  |  | CT SWAP Core Team | 1a
| 1.1.3 | Using these mechanisms, including CT DEEP websites, social media, and other channels, develop/ share SWAP implementation stories (use open-ended responses to survey to help find stories) and other SWAP related newsworthy items; share stories (successes and failures) through a variety of communication channels. |  |  |  | DEEP Comms Staff | 1b
Objective 2 |  | provide a diveristy of meaningful opportunities for public input in each phase of the SWAP revision and implementation | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Focus on identifying and building relationshps with partners necessary to achieve conservation outcomes for SGCN. | Lead | Sequence
Action | 1.2.1 | Using the List as a resource, identify a prioritized list of opportunites to solicit public input |  |  |  | Advisory Team | 1a
Objective 3 |  | Ensure that the revised CT SWAP includes clear and specific goals, objectives, actions and ways the public can provide input and interact with the CT SWAP during revision and implementation. |  |  |  | Lead | Sequence
| 1.3.2 | As part of the revision process, develop goals, objectives and actions with input from the public |  |  |  | CT SWAP Team | 1b
| 1.3.3 | Ensure regular communication to update and remind them how to input and interact and use the SWAP. |  |  |  | CT SWAP Team | 3
| 1.3.4 | Develop an online system to encourage and support data centralization and sharing. |  |  |  | CT SWAP Team | 3