## Base
Connecticut Department of Transportation |  |  | Project: |  |  |  | Connecticut Department of Transportation |  |  |  | Project: | 0 |  |  | Connecticut Department of Transportation |  |  |  |  | Project: | 0 |  |  | Connecticut Department of Transportation |  |  |  |  | Project: | 0
2800 Berlin Turnpike, PO Box 317546 |  |  | By: |  | Checked: |  | 2800 Berlin Turnpike, PO Box 317546 |  |  |  | By: | 0 | Checked: | 0 | 2800 Berlin Turnpike, PO Box 317546 |  |  |  |  | By: | 0 | Checked: | 0 | 2800 Berlin Turnpike, PO Box 317546 |  |  |  |  | By: | 0 | Checked: | 0
Newington, CT 06131-7846 |  |  | Date: |  |  |  | Newington, CT 06131-7846 |  |  |  | Date: |  |  |  | Newington, CT 06131-7846 |  |  |  |  | Date: |  |  |  | Newington, CT 06131-7846 |  |  |  |  | Date:
|  |  | Page No. | 1 | of | 4 |  |  |  |  | Page No. | 2 | of | 4 | [5 empty] | Page No. | 3 | of | 4 | [5 empty] | Page No. | 4 | of | 4
CTDOT ABC Decision Making Process | [5 empty] | 2017-10-10 | CTDOT ABC Decision Making Process | [6 empty] | 2017-10-10 | CTDOT ABC Decision Making Process | [7 empty] | 2017-10-10 | CTDOT ABC Decision Making Process | [7 empty] | 2017-10-10
Site Information | [6 empty] | Preliminary Cost Evaluation | [7 empty] | ABC Rating procedure | [8 empty] | Cost Analysis |  |  | 0 | >30%
| Project Description: | [14 empty] | Enter values for each aspect of the project. Attach back-up data if applicable | [7 empty] | Factor = | #DIV/0! |  | 1 | 20% < Factor < 30%
[8 empty] | Estimated conventional construction project cost = | [15 empty] | Net percentage of conventional cost |  |  | 2 | 10% < Factor < 20%
[10 empty] | Required Bridge |  |  |  |  | Average Daily Traffic |  |  | 0 | No traffic impacts |  |  |  |  | Negative value means that ABC has |  |  | 3 | 5% < Factor < 10%
[10 empty] | Overbuild |  | 0 |  |  | Combined traffic on and under |  |  | 1 | Less than 10000 |  |  |  |  | less net cost when compared to |  |  | 4 | 0% < Factor < 5%
| Prop. ABC Method: | [8 empty] | Total conventional bridge cost |  | 0 | [5 empty] | 2 | 10000 to 40000 |  |  |  |  | conventional construction |  |  | 5 | Factor <0%
[18 empty] | 3 | 40000 to 70000
[18 empty] | 4 | 70000 to 100000 |  |  |  |  | Envir. /Water Handling |  |  | 0 | No Restrictions (entry of 0 = not considered in score)
[8 empty] | Estimated CE&I Costs per month | [9 empty] | 5 | More than 100000 | [7 empty] | 1 | minor construction limitations
[9 empty] | Field office monthly cost | [17 empty] | 2
[9 empty] | CE&I staff monthly cost (field plus main office) | [5 empty] | User Impact Reduction |  | #DIV/0! | 0 | Zero | [7 empty] | 3 | moderate construction limitations for portions of the work
| Conventional Construction Method: | [7 empty] | Total CE&I Monthly Cost = |  |  | 0 |  |  | Calculated by spreadsheet |  |  | 1 | 1% to 20% | [7 empty] | 4
[18 empty] | 2 | 21% to 40% | [7 empty] | 5 | significant limitations on work
[9 empty] | Notes: | Small field office = $xxx per month | [7 empty] | 3 | 41% to 60%
[10 empty] | Medium office = $xxx per month | [7 empty] | 4 | 61% to 80% |  |  |  |  | Waterway Limitations |  |  | 0 | No impact (entry of 0 = not considered in score)
[10 empty] | Large office = $xxx per month | [7 empty] | 5 | 81% to 100% | [7 empty] | 1 | Minor impacts
[10 empty] | Staff = $20,000 per person per month | [16 empty] | 2
Roadway on Bridge | [7 empty] | Net time savings for ABC = | [5 empty] | months | Bridge Location |  |  | 0 | Rural Bridge away from town center | [7 empty] | 3 | Seasonal recreational impacts
[15 empty] | Stakeholder Impact |  |  | 1 | Rural bridge near town center | [7 empty] | 4 | Significant recreational impacts
| Average Daily Traffic |  |  | vehicles per day |  |  |  | Estimated Percent Premium for ABC = | [9 empty] | 2 | Suburban bridge away from town center | [7 empty] | 5 | Significant commercial impacts
[18 empty] | 3 | Suburban bridge near major traffic generators
| Conventional Construction | [6 empty] | MPT savings with ABC | [9 empty] | 4 | Urban Bridge near major traffic generators
|  | Delay Time (Per Delay Time Sheets) |  | minutes |  |  |  | Things that you can eliminate from conventional construction by using ABC | [9 empty] | 5 | Urban Bridge near emergency services
|  | Construction Impact Duration |  | Days |  |  |  |  | Overbuild for staging |  |  | 0
|  | Aggregate Impact Time | 0 | Person Days |  |  |  |  | Temporary bridge |  |  | 0 |  |  | Use of Typical Details |  |  | 1 | Complex and unfavorable geometry
| ABC | [7 empty] | Temporary signal |  |  | 0 | [5 empty] | 2 | Curved and skewed bridges |  |  |  |  | ABC Rating |  |  |  | Weight | Adjusted | Maximum | Adjusted
|  | Delay Time (Per Delay Time Sheets) |  | minutes |  |  |  |  | Other |  |  | 0 | [5 empty] | 3 | Curved bridges | [7 empty] | Score | Factor | Score | Score | Score
|  | Construction Impact Duration |  | Days |  |  |  |  | Total MPT Savings with ABC |  |  | 0 | [5 empty] | 4 | Skewed Bridges | [5 empty] | Average Daily Traffic |  | 0 | 10 | 0 | 5 | 50
|  | Aggregate Impact Time | 0 | Person Days | [13 empty] | 5 | Simple geometry well suited for typical details | [5 empty] | User Impact Reduction |  | #DIV/0! | 30 | #DIV/0! | 5 | 150
[25 empty] | Bridge Location |  | 0 | 5 | 0 | 5 | 25
Roadway Below Bridge | [7 empty] | Cost analysis | [6 empty] | Work Zone Geometry |  |  | 1 | Short duration project with good geometry & flow | [5 empty] | Use of Typical Details |  | 0 | 5 | 0 | 5 | 25
[15 empty] | Detour quality and/or |  |  | 2 | Short duration project with moderate geometry & flow | [5 empty] | Work Zone Geometry |  | 0 | 8 | 0 | 5 | 40
| Average Daily Traffic |  |  | vehicles per day |  |  |  | Premium for ABC = |  |  |  | 0 |  |  | MPT Quality |  |  | 3 | Average project duration with average geometry & flow | [5 empty] | Site Conditions |  | 0 | 5 | 0 | 5 | 25
[18 empty] | 4 | Long duration project with moderate geometry & flow | [5 empty] | Railroad Impacts |  | 0 | 5 | 0 | 0 | 0
| Conventional Construction | [6 empty] | CEI Cost Savings = |  |  |  | 0 | [5 empty] | 5 | Long duration project with complex geometry & flow | [5 empty] | Cost Analysis |  | 0 | 30 | 0 | 5 | 150
|  | Delay Time (Per Delay Time Sheets) |  | minutes | [20 empty] | Envir. /Water Handling |  | 0 | 5 | 0 | 0 | 0
|  | Construction Impact Duration |  | Days |  |  |  | MPT savings with ABC = |  |  |  | 0 |  |  | Site Conditions |  |  | 0 | significant limitations on work | [5 empty] | Waterway Limitations |  | 0 | 5 | 0 | 0 | 0
|  | Aggregate Impact Time | 0 | Person Days | [10 empty] | Utilities/ROW/Env. Compliance |  |  | 1 | moderate construction limitations for portions of the work | [8 empty] | Total Score | #DIV/0! | Max. Score | 465
| ABC | [6 empty] | Net cost change for ABC = |  |  |  | 0 | [5 empty] | 2
|  | Delay Time (Per Delay Time Sheets) |  | minutes |  |  |  |  | ABC is less expensive than conventional | [8 empty] | 3 | minor construction limitations | [8 empty] | ABC Rating | #DIV/0!
|  | Construction Impact Duration |  | Days | [13 empty] | 4
|  | Aggregate Impact Time | 0 | Person Days |  |  |  | Net percentage of conventional cost = |  |  |  | #DIV/0! | [5 empty] | 5 | No Restrictions | [8 empty] | ABC Rating Scale
[28 empty] | 60-100 | Use ABC
Percent Reduction in Aggregate Impact Time | [14 empty] | Railroad Impacts |  |  | 0 | No Railroad (entry of 0 = not considered in score) | [8 empty] | 50-60 | Consider ABC
| Conventional Construction | [16 empty] | 1 | Freight Siding (Less than 1 train per week) | [8 empty] | 0-50 | Do not use ABC
|  | Total Aggregate Impact Time | 0 | Person Days | [13 empty] | 2 | Light Freight (1 Train per week to 1 Train per day)
| ABC | [16 empty] | 3 | Heavy Freight (More than 1 Train per day)
|  | Total Aggregate Impact Time | 0 | Person Days | [13 empty] | 4 | Commuter rail
[18 empty] | 5 | Electrified Commuter Rail
| User Impact Reduction |  | #DIV/0!
Note: Negative value indicated that ABC has more impact
[25 empty] | Note: | Weight factors determined by CTDOT. Do not adjust factors without prior consultation.

## Detour Delay Time
Connecticut Department of Transportation | [9 empty] | Project:
2800 Berlin Turnpike, PO Box 317546 | [9 empty] | By: | Checked:
Newington, CT 06131-7846 | [9 empty] | Date:
ABC Decision Matrix - Supplementary Spreadsheet
Detour Delay Time
[10 empty] | Sheet No. | of
Traffic Delay Calculation Recommendations Key |  |  |  |  | Input areas
Calculations and results
Detour Delays | [9 empty] | Comments
1. These caculations would be used if a detour was planned. The adjustment factor is to account for the anticipated volume of traffic on the detour.
| Detour Segment 1 Length |  |  | miles
| Segment 1 speed limit |  |  | mph
| Segment 1 Congestion Factor |  |  | See Note 1
| Segment 1 Time |  | 0 | minutes
2. Segment Congestion Factor variables may be reduced for short term detours if the project will include special advance notice to motoring public during construction phase with the effect of reducing overall short term traffic volumes.
| Detour Segment 2 Length |  |  | miles
| Segment 2 speed limit |  |  | mph
| Segment 2 Congestion Factor |  |  | See Note 1
| Segment 2 Time |  | 0 | minutes
| Detour Segment 3 Length |  |  | miles
| Segment 3 speed limit |  |  | mph
| Segment 3 Congestion Factor |  |  | See Note 1
| Segment 3 Time |  | 0 | minutes
| Detour Segment 4 Length |  |  | miles
| Segment 4 speed limit |  |  | mph
| Segment 4 Congestion Factor |  |  | See Note 1
| Segment 4 Time |  | 0 | minutes
| Detour Segment 5 Length |  |  | miles
| Segment 5 speed limit |  |  | mph
| Segment 5 Congestion Factor |  |  | See Note 1
| Segment 5 Time |  | 0 | minutes
Assumptions
| Number of Stops along detour |  |  | stop signs or signals
| Delays at stop signs |  | 0 | minutes |  |  | Delay Time per stop | 1 | minutes
| Aggregate Detour Time |  | 0 | minutes (use this in the Base Spreadsheet)
Note 1: This factor accounts for the additional delay on the detour route due to congestion. For example, a value of 1.25 equates to a
25% increase in travel time on the detour route.
Segment Congestion Factor
Conditions at Bridge
|  | Non-limited access highway, total ADT < 5,000 | Non-limited access highway, total ADT 5,000 - 10,000 | Non-limited access highway, total ADT > 10,000 | Limited access highway, directional ADT < 25,000 | Limited access highway, directional ADT > 25,000
Conditions on Detour Segment | Longer than 2.0 miles, ADT > 8,000 per lane | 1.5 | 1.75 | 2 | 2 | 2
| Longer than 2.0 miles, ADT< 8,000 per lane | 1.25 | 1.5 | 1.75 | 2 | 2
| 0.5 - 2.0 miles, ADT < 3,000 - 8,000 per lane | 1.25 | 1.25 | 1.5 | 1.75 | 2
| 0.5 - 2.0 miles, ADT < 3,000 per lane | 1 | 1.25 | 1.5 | 1.5 | 1.75
| Less than 0.5 mile, ADT < 3,000 per lane | 1 | 1 | 1.25 | 1.5 | 1.5
Conditions on Detour Segment - Guidance:
ADT per lane = ADT on segment / number of total available lanes on roadway
If length of detour and ADT per lane do not match one of the above categories, use higher value condition

## Alt Traffic Delay Time
Connecticut Department of Transportation |  |  |  |  | Project:
2800 Berlin Turnpike, PO Box 317546 |  |  |  |  | By: | Checked:
Newington, CT 06131-7846 |  |  |  |  | Date:
ABC Decision Matrix - Supplementary Spreadsheet
Alternating Traffic Delay Time
[5 empty] | Sheet No. | of
Traffic Delay Calculation Recommendations Key |  |  |  | Input areas
Calculations and results
One Way Alternating Traffic Delays |  |  |  |  | Comments
These calculations would be for a typical bridge replacement project where one way alternating traffic is proposed. The basis for this calculation is the following assumptions:
For each direction:
| Estimated Cycle Time |  | minutes (See note 2)
| Average Delay Time | 0 | minutes (use this in the Base Spreadsheet)
** The estimated average cycle time can be assumed based on the following:
| ADT <2000 | 1 | minutes |  | 1. On average, a typical car will spend one half of a complete cycle at the signal. Some vehicles will arrive at the worst moment and wait an entire cycle to go. Some vehicles will arrive just as the light goes green and have no delay.
| 2001 < ADT < 4000 | 1.25 | minutes
| 4001 < ADT < 6000 | 1.5 | minutes
| 6001 < ADT < 8000 | 2 | minutes
Do not use alternating one way traffic for ADT over 8000
2. The values given are for one way alternating stop signs for low volume roads and and signals for higher volume roads.
3. For stop sign control, maximum length of alternating traffic must be no greater than 400 feet and clear sightline must be provided between the two opposing traffic stop signs.

## Reduced Lane Delay Time
Connecticut Department of Transportation |  |  |  |  | Project:
2800 Berlin Turnpike, PO Box 317546 |  |  |  |  | By: | Checked:
Newington, CT 06131-7846 |  |  |  |  | Date:
ABC Decision Matrix - Supplementary Spreadsheet
Reduced Lane Delay Time
[5 empty] | Sheet No. | of
Traffic Delay Calculation Recommendations Key |  |  | Input areas
Calculations and results
Lane Reduction Delays |  |  |  |  | Comments
| Heavy Commute Peak Period 1 |  |  |  | 1. These calculations would be used if staged construction was planned where there is a proposed reduction in the number of lanes. The basis of the delay times is that a lane can accommodate 1400 vehicles per hour without delay. Increased delays would result as the lane volume increases.
|  | Hourly volume during peak periods |  | total vehicles per hour
|  | Number of Lanes in service during peak |  | lanes
|  | Peak Lane Volume | 0 | vehicles per hour per lane
|  | Average delay time per vehicle | 0 | minutes (see basis to the right)
|  | Aggregate delay time for this peak period | 0 | vehicle minutes per hour
|  | Length of peak period | 0 | hours (see note below)
|  | Aggregate delay time for this period | 0 | vehicle minutes
|  | Note: Length of Peak Period: enter 1 for light traffic; 2 for medium traffic; 3 for heavy traffic |  |  | 2. The assumption is that the delay time increases linearly from 1400 vehicles per hour (see Basis of Delay Time Plot to Right). The rate of increase can be easily adjusted by changing the delay value for the 2400 vph line in the table to the right (blue cell).
Heavy Commute Peak Period 2
|  | Hourly volume during peak periods |  | total vehicles per hour
|  | Number of Lanes in service during peak |  | lanes
|  | Peak Lane Volume | 0 | vehicles per hour per lane
|  | Average delay time per vehicle | 0 | minutes
|  | Aggregate delay time for this peak period | 0 | vehicle minutes per hour | 3. The peak hourly volume can be estimated to be 10% of the ADT if specific hourly volumes are not available.
|  | Length of peak period |  | hours (see note below)
|  | Aggregate delay time for this period | 0 | vehicle minutes |  |  | Lane | Delay |  | Assuming Linear zeroing out at 1400
[7 empty] | Volume | (min.)
|  | Note: Length of Peak Period: enter 1 for light traffic; 2 for medium traffic; 3 for heavy traffic |  |  |  |  | Demand
| Off peak periods | [5 empty] | 0 | 0 |  | Slope = | 0.03
|  | Average Hourly volume during off-peak periods |  | total vehicles per hour |  |  | 200 | 0
|  | Number of Lanes in service during peak |  | lanes | 4. The off peak hourly volume can be estimated to be 3% of the ADT if specific hourly volumes are not available. |  | 400 | 0
|  | Peak Lane Volume | 0 | vehicles per hour per lane |  |  | 600 | 0
[7 empty] | 800 | 0
|  | Average delay time per vehicle | 0 | minutes |  |  | 1000 | 0
[7 empty] | 1200 | 0
|  | Aggregate delay time for this peak period | 0 | vehicle minutes per hour |  |  | 1400 | 0
|  | Length of peak period | 24 | hours (24 hours minus peak hours) |  |  | 1600 | 6
|  | Aggregate delay time for this period | 0 | vehicle minutes |  |  | 1800 | 12
[5 empty] | 5. Reduced ADT input values may be used for short term lane reductions (2 to 3 day intervals) if special advance notice to motoring public is implemented during construction phase with the effect of temporarily reducing ADT. |  | 2000 | 18
[7 empty] | 2200 | 24
[7 empty] | 2400 | 30 | Change this number to change the slope of the line and the values
Average delay time
|  | Aggregate delay time for period 1 | 0 | vehicle minutes (from above)
|  | Aggregate delay time for period 2 | 0 | vehicle minutes (from above)
|  | Aggregate delay time for off peak period | 0 | vehicle minutes (from above)
|  | Total Aggregate delay time | 0 | vehicle minutes
|  | Total ADT |  | vehicles
|  | Average Delay time per vehicle | 0 | minutes (use this in the Base Spreadsheet)