## Cover Page and Version
Community Benefit Annual Status Report - Response Workbook & Report
Connecticut Office of Health Strategy Version 1.0

## Summary
Hospital Community Benefit Annual Status Report
Hospital Name: | St. Vincent's Medical Center | Required
Submission Date: | 2023-09-29 | Required
Connecticut General Statutes §19a-127k requires on or after January 1, 2023, each hospital in Connecticut to submit community benefit program reporting to the Office of Health Strategy (OHS). Inclusive of community benefit program reporting are: hospitals’ Community Health Needs Assessment (CHNA) and Implementation Strategy, the Community Health Needs Assessment Report, the Implementation Strategy Report, and the Annual Status Report. Submission of this report on or before October 1 to OHS with complete answers to the Report Responses, satisfies Connecticut hospitals’ requirement to submit their Annual Status Report to the State. The Annual Status Report portion of community benefit reporting shall be submitted to OHS via the Community Benefit Portal:
OHS Community Benefit Portal
The submission shall:
1. Be submitted on or before October 1, 2023, and annually thereafter.
2. Use this excel template for the responses with complete answers.
3. Be based on the filing year of the hospitals’ most recently completed IRS Form 990 submitted to OHS pursuant to Connecticut General Statutes §19a-649.
Any examples provided in this template are for illustrative purposes only, and should not be construed as demonstrating or not demonstrating community benefit. Any questions regarding the completion or submission of this report shall be directed to: ohs@ct.gov.
Helpful Links:
Connecticut General Statutes §19a-127k
Connecticut General Statutes §19a-649
OHS Community Benefit Portal
ohs@ct.gov

## Workbook Contents
Hospital Community Benefit Annual Status Report Workbook Contents
Cover Page and Version
Summary
Report Responses:
Response 1A
Response 1B
Response 2
Response 3
Attestation
Appendix:
Appendix A - Definitions
Appendix B - Example Responses

## Response 1A
Response 1A
A description of major updates regarding community health needs, priorities and target populations, if any.
In the description of major updates to the community benefit program, which can come from the Community Health Needs Assessment, Implementation Strategy, programs or actions included in the Implementation Strategy, or other relevant sources of the community benefit program, please use Table 1, and provide detailed information in the template format. Updates may include improvements, barriers, lessons learned, qualitative or quantitative data that supports the update, or other pertinent information. You may append any supporting documentation such as a project management plan, or data that gives further insights to the major updates. If there are no major updates, please indicate as such below. Information provided should match the filing year from your hospital's most recent IRS Form 990 submission to the Connecticut Office of Health Strategy (filing year 2022).
Table 1
Major updates
Community Health Needs | The 2019 CHNA was conducted in collaboration with the Health Improvement Alliance, a coalition of community based organizations that serve the Greater Bridgeport region of Connecticut and are committed to broad collaboration and meaningful community engagement to improve the health and wellbeing of residents across Greater Bridgeport. Priority health needs were grouped into three overarching focus areas: access to care, behavioral health, and healthy lifestyles. Individual task forces, comprised of HIA members, work together on each focus area. In October 2019, HIA launched the 2019-2022 Community Health Implementation Plans (CHIPs) for the three focus areas mentioned above. Just six short months later, responding to the COVID-19 pandemic became the focus for all HIA partner organizations, shifting the focus of the work outlined in the 2019-2022 CHIPs. From 2019-2022, SVMC and Bridgeport Hospital (BH), along with the four HIA task forces, made significant progress towards CHIP goals in the Greater Bridgeport region. It is important to note that the community benefit expenses reported in the attached report under response 3 are only a fraction of what we spent in 2022 on IRS recognized community benefit expenses as reported on Schedule H, Form 990. We incurred an additional $31,759,505.0 in charity care and Medicaid under payment and a total of $7,102,672.0 in other community benefits. Taken together, IRS recognized community benefit expenses equaled 6.77% of total operating expenses. A number of community education outreach activies were suspended due to the COVID 19 and attempts to resume 2021 were not achieved due to lack of participation. For the great majority of Connecticut hospitals, the 2019 CHNA and CHIP, encompassing the years 2020 through 2022, is the applicable CHIP for the 2022 annual status reporting period. Within a few short months of the finalization of the CHIP, the U.S. declared a public health emergency as a result of COVID-19 and hospitals directed all of their resources to respond to the pandemic and coordinated with the Lamont administration to effect a comprehensive public health response. Hospitals invested heavily in preparing for a high volume of critically ill COVID-19 patients and also contributed to the public health response by setting up extensive community testing and vaccination sites. Without exception, community health directors and their staff were called to action in the service of the pandemic response. Attention was diverted necessarily away from needs and priorities outlined in hospital CHIPs and directed instead to community outreach and education, initially focused on measures to test for and protect against the virus, and later on promoting vaccine confidence. Attention was also increasingly paid to unmet basic needs that emerged as a consequence of the pandemic including related to food security, housing, and transportation. Hospitals joined with their community partners, such as FQHCs, community action agencies, and health departments, and directed their support to communities identified by the CDC as at greatest risk and experiencing the worst disparities with respect to infection rates, outcomes, and social need. These efforts, largely independent from the CHIP, continued through all of 2020 and 2021 and began to ease in 2022, the final year of the approved CHIPs. By 2022, hospitals began working with their communities to reassess community needs in a markedly changed landscape, with increasing rates of psychiatric and substance use, unmet and more serious medical needs as a consequence of delayed care, and developmental impacts on children as a consequence of two years of disrupted education. During 2022 hospitals and their community partners viewed as less valuable picking up where they left off on 2019 needs and action plans as originally envisioned and instead focused on formulating new triennial plans aligned with the latest data and community input regarding needs and priorities. The unusual circumstances surrounding 2022 as a year of transition are reflected in the 2022 annual status report.
Priorities | 1.Healthy lifestyles 2.Access to care 3.Behavioral health
Target Populations | Disadvantaged communities, people of color, and others who have historically lacked adequate access to services.

## Response 1B
Response 1B
A description of any major changes to the proposed implementation strategy from the most recently submitted implementation plan and associated hospital actions.
In your description, please include in Table 2 a description of any major changes, and why there were major changes to the hospitals’ implementation strategy and associated actions. Information provided should match the filing year from your hospital's most recent IRS Form 990 submission to the Connecticut Office of Health Strategy (filing year 2022).
Table 2
Major changes to the implementation strategy and associated hospital actions
#1
#2
#3
#4
#5
#6
#7
#8
#9
#10

## Response 2
Response 2
A description of progress made regarding the hospital's actions in support of its implementation strategy.
The description in this worksheet should include the following:
· The need that the action is addressing, and whether it was identified, or not identified, in the most recently submitted Community Health Needs Assessment, or is newly added since the last CHNA.
· The relevant implementation strategy.
· The action the hospital is taking in support of its implementation strategy.
· The goal(s) of the action, and the timeline for achieving the goal(s)
· The measure(s) corresponding to the action(s), and the result(s) of the measure(s).
· The name of the hospital staff member who is overseeing the action(s).
· The name(s) of the organizations which partnered with the hospital for each of the hospital’s actions in support of its implementation strategy.
In your answer for Response 2, use the corresponding tabs: "Response 2 - Need 1," "Response 2 - Need 2," and "Response 2 - Need 3." Only one need per tab should be used. For example, Need 1 and Need 2 should not both be "Food Insecurity." If additional tabs are required to illustrate progress made for more than three needs, reach out to ohs@ct.gov with how many additional tabs are required, and an updated template will be sent to you. Each action for Response 2 should correspond with a need. Note, the actions you input in the Response 2 tabs will auto populate the Response 3 - Table 3 tab. The Information provided should match the filing year from your hospital's most recent IRS Form 990 submission to the Connecticut Office of Health Strategy (filing year 2022).

## Response 2 - Need 1
Response 2 - Need 1
Identified Health Need:
Healthy Lifestyles
In CHNA
Yes
Implementation Strategy Included in submission?
Yes
The hospital’s actions in support of its implementation strategy:
| Action | Action Goal | Timeline | Measure | Measure Results | Owner | Partnered Organization(s)
1 | Utilize American Heart Association's Life's Simple 7 | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | number of people served, number of events | not started due to Covid | Parish Nurse Program | Health Improvement Alliance
2 | Design a KYN campaign targeted to adults ages 18-49 | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | number of people served, number of events | not started due to Covid | HIA Healthy Lefestyles Task Force | Health Improvement Alliance
3 | Determine effectiveness of KYN screenings in their current sites and work with task force partners to make adjustments as needed based on data available | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | analysis of data obtained through screenings Calendar Year 2019 - 2022 - served 538 patients | in progress | HIA Healthy Lefestyles Task Force | Health Improvement Alliance
4 | Continue to partner with community health workers to link KYN participants to follow-up care | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | number of follow-up appointments & community resources: In 2019, 35 referrals were made to CHWs in 2020, CHWs referred 14 patients to follow-up care and additional community resources (Feb 2020, right before Covid) | completed | HIA Healthy Lefestyles Task Force | Health Improvement Alliance
5 | Determine effectiveness of expanding KYN to include hAlc screenings and practice providing automated BP cuffs for ongoing BP monitoring and expand where feasible | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | Added A1C in 2016; analysis of data obtained through screenings: In 2020: 33 were found to be in the pre-diabetic range (not previously diagnosed with diabetes) (42%) 5 not previously diagnosed with diabetes and were found to be in the diabetes range (6%) 5 known diabetics and were found to be in the uncontrolled diabetes range (6%) In 2021, 56 A1Cs - 24 unknown pre-deiabetic, 11 unknown diabetic; 60 BP checks - 20 Stage 2, 17 Satge 1, 4 elevated, 25 cuffs distributed In 2022: 126 A1Cs - 57 unknown prediabetic, 5 unknown diabetic; 161 BP checks - 76 stage 2, 40 stage 1, 12 elevated, 96 cuffs distributed | completed | HIA Healthy Lefestyles Task Force | Health Improvement Alliance
6 | St. Vincent’s will enhance the existing blood pressures screenings in the lobby to provide free automated blood pressure cuffs with education on usage and tracking guides to those people who screen >135 systolic or >85 diastolic. | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | From Oct 2019 to Feb 2020, served 618 persons for blood pressure (573), blood sugar (42) and cholesterol (3). Program was shut down due to Covid and not resumed. | completed | Cardiology Department
7 | Determine barriers related to access to available free and low - cost fitness opportunities and develop ways to address these | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | Walk n talk events: 1 | completed | Mission Services | Health Improvement Alliance
8 | Continue to work towards regional Bike Share programs and promote/support safe biking/walking in neighborhoods through complete streets policies, partnerships with police/law enforcement, planning and zoning, and other city/town officials | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | # of people who use the available bike shares | not started due to Covid | HIA Healthy Lefestyles Task Force | Health Improvement Alliance
9 | Develop an educational campaign around e-cigarettes/vaping | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | track vaping usage among youth | not started due to Covid | HIA Healthy Lefestyles Task Force | Health Improvement Alliance
10 | Identify local youth prevention coalitions and collaborate to track vaping usage in youth | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | track vaping usage among youth | not started due to Covid | HIA Healthy Lefestyles Task Force | Health Improvement Alliance
11 | Promote Tobacco 21 ordinance roll out in the City of Bridgeport and support the passage of local ordinances or state laws around Tobacco 21 | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | # of local Tobacco 21 ordinances/track the passage of a state law | not started due to Covid | HIA Healthy Lefestyles Task Force | Health Improvement Alliance
12 | Promote local tobacco cessation resources | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | # of participants referred to tobacco cessation resources | not started due to Covid | HIA Healthy Lefestyles Task Force | Health Improvement Alliance
13 | Evaluate implementing prescription to fruit and vegetable programs | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | Grant funding for program, number of Bridgeport Bucks distributed 2021: Received grant funding from United Way to purchase Bridgeport Bucks currency redeemable at Bridgeport Farmers Market Collaborative markets for fresh fruits and vegetables. 3000 - $5 bucks distributed to those in need. Distrbuted through physicians, nutritionists, ED, partners, Farm Stand | completed | Mission Services & Philanthropy | Health Improvement Alliance
14 | Invite the CT Food Bank Mobile Pantry to distribute free food from the St. Vincent’s parking lot once monthly | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | # of Mobile pantries, # of persons served; pivoted to an internally funded food distribution of shelf-stable items in May of 2020 32 pantries held from 10/1/2019 - 9/30/2022 11,044 persons served | May 2019 - April 2020 - CT Food Bank May 2020 - July 2022 - St. Vincent's funded Complete | Parish Nurse Program | Health Improvement Alliance
15 | Determine national best practices for addressing social determinants of health as related to healthy lifestyles and decreasing hypertension and diabetes | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | Identified best practices | not started due to Covid | HIA Healthy Lefestyles Task Force | Health Improvement Alliance
16 | Start to build partnerships to work towards addressing SDOH, potential areas include Adverse Childhood Experiences (ACES), advocacy around increasing the minimum wage, WIC and SNAP acceptance in more venues. | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | # of identified partnerships, grants to fund work HEC grant work with HIA WIC and SNAP accepted at Farm Stand | completed | Mission Services | Health Improvement Alliance
17 | Staff salaries for individuals whose sole responsibility is coordinating, providing and reporting community benefits (100%) as well as percentage of time for staff that has dedicated a portion of their time for community benefits reporting. Staff time dedicated to advancing CHNA/CHIP actions and priorities. | Community Benefit Operations | FY22 | Salaries | completed | HHC System Office
18 | Continue to co-lead the HIA, including Steering Committee monthly meeting, communications committee meetings, tracking and evaluation committee, planning meeting | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | # of meetings held, staff hours captured in community benefit operaitons approximately 100 meetings held over three years | completed | Mission Services | Bridgeport Hospital/Health Improvement Alliance
19 | Staff attend Healthy LifestylesTask Force meetings | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | aproximately 30 meetings held - attended by a minimum of 1 staff, in addition to co-chair | completed | Mission Services | Milford Health Department/Health Improvement Alliance
20 | Staff co-chairs Task Force meeting | By February 2022, promote healthy lifestyles in the Greater Bridgeport region to reduce diagnosed hypertension and diabetes in adults by 3%. | FY19-22 | Approximately 30 meetings led | completed | Mission Services | Milford Health Department/Health Improvement Alliance
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Response 2 - Need 2
Response 2 - Need 2
Identified Health Need:
Access to Care
In CHNA
Yes
Implementation Strategy Included in submission?
Yes
The hospital’s actions in support of its implementation strategy:
| Action | Action Goal | Timeline | Measure | Measure Results | Owner | Partnered Organization(s)
1 | Determine how to best educate the community about the importance of having a medical home, particularly in the young adult population and implement strategies as appropriate | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | In 2021, received two grants to support the hiring of CHWs. Hired 2 CHWs in May 2022 | completed | Who is the lead/owner of the goal at HHC - can be person/people or departments within organization | Partner organizations to be listed by catogory not partner name (e.g. food pantry, local health department, not specific organizations)
2 | Promote available medical services in the region | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | # of resources created, distributed Enhanced website, created Covid vaccine advocacy videos; updated and distributed provider flyer for uninsured (1000+) | completed | Health Improvement Alliance | Health Improvement Alliance
3 | Collaborate to increase referrals from partner organizations to primary care providers | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | Number of referrals to primary care | incomplete - data not collected | Health Improvement Alliance | Health Improvement Alliance
4 | In collaboration with Southwest Community Health Center, (formerly St. Vincent’s Family Health Center), we conduct primary care clinics which are staffed by our Internal Medicine Residents, as a major component to their education. This is located on Lindley Street in Bridgeport. In this model of care, patient are assigned to a specific Resident, who acts as the PCP in collaboration with Boarded Physician Educators who lead this program. This promotes continuity of care for the patient and therefore enhances the quality of that care, as they identify with whom they establish an ongoing and trusted rapport. | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | patient compliance with appointments, # of referrals | completed | Health Improvement Alliance | Southwest Community Health Center
5 | We at SVMC, through our Foundation, provide an annual venue that we call our Medical Mission at Home. This is held in Bridgeport at a local school. We have multiple volunteers who provide healthcare t many levels. There is biometric testing, nursing and physician evaluation and exams, vaccinations, pharmacy, distribution of needed items:(reading glasses, winter coats, shoes and sox, toiletries) pastoral care support, and lunch. It is open to the community without a scheduled appointment. Last year, we embraced just about 400 patients. The community benefit to population management is that both SVMC and SWCHC are on-site to refer patients to PCP services at both entities. We are working to establish an on-going rapport with a PCP for their healthcare delivery. We have videos that we could share with you. | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | # of persons served, # of referrals, # of events October 2019 - September 2022: conducted 3 Medical Missions served 746+ patients provided more than 129 referrals | completed | Philanthropy/Mission Services
6 | St. Vincent’s Medical Center has established a central call center to improve ease of scheduling an appointment at any of our SVMC/ MSG sites. | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | number of persons served | incomplete - we were acquired by Hartford HealthCare | SVMC
7 | Produce and distribute educational materials on the importance of dental care | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | # of CHWs in GBT region who have successfully completed a dental training workshop # of referrals % change in dental service utilization affected by covid | incomplete due to covid | Access to Care Task Force | Health Improvement Alliance
8 | Promote available dental services in the region | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | # of CHWs in GBT region who have successfully completed a dental training workshop # of referrals % change in dental service utilization affected by covid | incomplete due to covid | Access to Care Task Force | Health Improvement Alliance
9 | Continue to improve and expand the dental referral system between partner organizations | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | Pilot dental program - began but then was affected by covid | incomplete due to covid | Access to Care Task Force | Bridgeport University, Americares, Health Improvement Alliance
10 | Advocate for improved dental insurance coverage | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | # of CHWs in GBT region who have successfully completed a dental training workshop # of referrals % change in dental service utilization affected by covid | not started | Access to Care Task Force | Health Improvement Alliance
11 | Because of the collaborative efforts between SVMC and SWCHC, patients now have access to Dental services through SWCHC. There has been an enhanced emphasis on dental health and hygiene for our community as a result this collaboration. | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | persons served - negatively affected by Covid. Many people still behind on dental visits | incomplete | Access to Care Task Force | Health Improvement Alliance
12 | Identify gaps in specialty care access for Medicaid and uninsured patients and investigate ways to increase availability and access | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | of focus groups with specialty care providers # of new providers accepting Medicaid and uninsured patients Annual update of specialty care database | not started due to covid | Access to Care Task Force | Health Improvement Alliance
13 | Collaborate with specialty care providers to increase the number of providers who accept Medicaid and uninsured patients | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | of focus groups with specialty care providers # of new providers accepting Medicaid and uninsured patients Annual update of specialty care database | not started | MultiSpecialty Group
14 | By transferring the Family Health Center to SWCHS, an FQHC site, we were able to re-purpose our financial resources to create, grow and better staff specialty clinics which are offered at 2979 Main Street in Bridgeport. We have increased the number of hours and days, as well as, introduced new services such as Orthopedics (3 full days per week), Plastic Reconstructive Surgery, Infectious Disease, G.I. and Nephrology. This has been a tremendous addition to population health management. | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | Significant expansion in specialty and sub-specialty care. Enhances access and availability of services and update of specialty care database. We have also significantly reduced the wait times for scheduling specialty and sub-specialty appointments. | incomplete - Covid and other factors have reduced our specialty care clinics | MultiSpecialty Group
15 | Continue to be involved in the state medical transportation efforts and share local experiences at the state level | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | attend state medical transportation efforts | not started | Access to Care Task Force | Health Improvement Alliance
16 | Continue communications with Veyo and invite them to task force meetings for quarterly updates and communicate those updates with partners organizations | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | # of task force meetings attended by Veyo Track initiatives and local outcomes with Veyo | not started | Access to Care Task Force | Health Improvement Alliance
17 | Determine accessibility of additional medical transportation options, including public transportation and medical ride programs and develop strategies based on this assessment | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | Monitor the number of visits and query patients about challenges in transportation to and from the facilities. Work to provide resource assistance in securing transportation. | not started | Mission Services
18 | Both the SWCHC facility and the St. Vincent’s Family Health Center Specialty Clinic are located on major bus routes. This provides for greater ease of access to both primary and specialty care clinics. | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | Monitor the number of visits and query patients about challenges in transportation to and from the facilities. Work to provide resource assistance in securing transportation. | not started | Mission Services
19 | Complete a CLAS assessment with local partner organizations to determine current gaps and implement CLAS strategies as needed | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | Completion of Assessment: completed 5 areas - affected by Covid with 13 organization participating | completed | Access to Care Task Force/Mission Services | Health Improvement Alliance
20 | Collect CLAS implementation tools and disseminate within partner organizations within Access to Care and throughout HIA organizations | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | # of tools collected and distribution to partners | not started due to covid | Access to Care Task Force | Health Improvement Alliance
21 | Continue to grow CLAS to meet the specific needs of the patients in our area and satisfy population health management resources. | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | Continue to track growth relative to CLAS initiative. | not started due to covid | Mission Services | Health Improvement Alliance
22 | Staff salaries for individuals whose sole responsibility is coordinating, providing and reporting community benefits (100%) as well as percentage of time for staff that has dedicated a portion of their time for community benefits reporting. Staff time dedicated to advancing CHNA/CHIP actions and priorities. | Community Benefit Operations | FY22 | Salaries | completed | HHC System Office
23 | Continue to operate the Hope Pharmacy | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | # of persons served, value of prescriptions, # of prescriptions FY20 data: 4,550 patients with 11,300 prescriptions. FY21 data: 4,549 patients with 14,863 medication prescriptions valued at $1.26M. FY22 data: 4,195 patients with 17,627 medication prescriptions valued at approximately $700K. | completed | Pharmacy | Mission Services/Community Benefit
24 | Continue to co-lead the HIA, including main monthly meeting, communications committee meetings, tracking and evaluation committee, planning meeting | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | # of meetings held, staff hours captured in community benefit operaitons approximately 100 meetings held over three years | completed | Mission Services | Bridgeport Hospital/Health Improvement Alliance
25 | Staff attend Access to Care Task Force meetings | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | aproximately 30 meetings held - attended by a minimum of 1 staff, in addition to co-chair | completed | Mission Services | Optimus/emme coalition
26 | Staff co-facilitates Task Force meeting | By February 2022, only 13% of adults in Greater Bridgeport will report not having a medical home and 74% will report visiting a dentist at least once in the past year | FY20-22 | Approximately 30 meetings led | completed | Mission Services | Bridgeport Hospital/Health Improvement Alliance
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Response 2 - Need 3
Response 2 - Need 3
Identified Health Need:
Behavioral Health
In CHNA
Yes
Implementation Strategy Included in submission?
Yes
The hospital’s actions in support of its implementation strategy:
| Action | Action Goal | Timeline | Measure | Measure Results | Owner | Partnered Organization(s)
1 | Align resources and build collaboration between organizations to increase access and awareness to community health workers and peer support specialists | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | # of initiatives - Know Your Numbers In 2021, received two grants to support the hiring of CHWs. Hired 2 CHWs in May 2022 | In progress | Mission Services | Health Improvement Alliance
2 | Participate in funding opportunities such as BUILD Health | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | # of funding opportunities with participation of members | not started due to covid | Behavioral Health Task Force | Health Improvement Alliance
3 | Develop strategies to link clinical and non-clinical services | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | # of strategies to link clinical and nonclinical services | not started due to covid | Behavioral Health Task Force | Health Improvement Alliance
4 | Establish or expand mobile or community based resource in the greater Bridgeport area | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | # of initiatives to establish or expand mobile or community based resources | not started due to covid | Behavioral Health Task Force | Health Improvement Alliance
5 | Educate providers on resources (physicians, hospitals, others) | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | # provider education initiatives | not started due to covid | Behavioral Health Task Force | Health Improvement Alliance
6 | Develop strategy to educate the general community on available resources for non-crisis services | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | # educational strategies for non-crisis services - 1 stategy completed - leveragingThe Hub resources | completed | Behavioral Health Task Force | Health Improvement Alliance
7 | Develop strategy to educate the general community on available resources for crisis services | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | # educational strategies for crisis services | not started due to covid | Behavioral Health Task Force | Health Improvement Alliance
8 | Develop strategies to reach selected communities (youth, young adult, elderly, etc.) | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | # strategies to reach selected communities | not started due to covid | Behavioral Health Task Force | Health Improvement Alliance
9 | Refine Bridgeport Care Coordination Team (CCT) | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | # organizations actively involved from current to end of CHIP. Challenged during Covid, then regrouped via Zoom in Cotober 2020. Met ~ 96 times in FY21-22 - weekly, 1.5 hours/wk 10-15 partner agencies participate, currently serving 8 people | completed | St. Vincent's Behavioral Health | Bridgeport Region CCT
10 | Improve attendance at meetings and involvement of organizations | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | # organizations actively involved from current to end of CHIP. Challenged during Covid, then regrouped via Zoom in Cotober 2020. Met ~ 96 times in FY21-22 - weekly, 1.5 hours/wk 10-15 partner agencies participate, currently serving 8 people | completed | St. Vincent's Behavioral Health | Bridgeport Region CCT
11 | Establish a dedicated patient navigator for CCT | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | Establishment of patient navigator | not started | St. Vincent's Behavioral Health | Bridgeport Region CCT
12 | Improve information sharing across organizations | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | Tracking/results sharing improvement - meeting weekly - Met ~ 96 times in FY21-22 - weekly, 1.5 hours/wk 10-15 partner agencies participate, currently serving 8 people | completed | St. Vincent's Behavioral Health | Bridgeport Region CCT
13 | Track outcomes and share results on a quarterly basis | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | Tracking/results sharing improvement - meeting weekly - Met ~ 96 times in FY21-22 - weekly, 1.5 hours/wk 10-15 partner agencies participate, currently serving 8 people | completed | St. Vincent's Behavioral Health | Bridgeport Region CCT
14 | Evaluate state and local best practices for improvement of CCT including re-establishing participation in Health and Housing stability work group | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | Tracking/results sharing improvement - meeting weekly - Met ~ 96 times in FY21-22 - weekly, 1.5 hours/wk 10-15 partner agencies participate, currently serving 8 people | completed | St. Vincent's Behavioral Health | Bridgeport Region CCT
15 | Ensure smooth operation and timeliness of meetings of the Task Force. | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | Monthly meetings held: ~ 30 | completed | Behavioral Health Task Force | Health Improvement Alliance
16 | Staff salaries for individuals whose sole responsibility is coordinating, providing and reporting community benefits (100%) as well as percentage of time for staff that has dedicated a portion of their time for community benefits reporting. Staff time dedicated to advancing CHNA/CHIP actions and priorities. | Community Benefit Operations | FY22 | salaries | completed | HHc System Office
17 | Continue to co-lead the HIA, including main monthly meeting, communications committee meetings, tracking and evaluation committee, planning meeting | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | # of meetings held, staff hours captured in community benefit operaitons approximately 100 meetings held over three years | completed | Mission Services | Bridgeport Hospital/Health Improvement Alliance
18 | Staff attend Behavioral Health Task Force meetings | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | aproximately 30 meetings held over three years - attended by a minimum of 1 staff, in addition to co-chair | completed | Mission Services/Behavioral Health | Health Improvement Alliance
19 | Staff facilitates Task Force meeting | By February 2022, the Primary Care Action Group’s (PCAG) efforts will result in a 2% increase in social and emotional support for adults in the Greater Bridgeport area. | FY20-22 | Approximately 30 meetings ledover three years | completed | Mission Services | RNP, The Hub
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Response 2 - Need 4
Response 2 - Need 4
Identified Health Need:
Identified Health Need Here
In CHNA
Yes, No, Newly Added
Implementation Strategy Included in submission?
Yes or No
The hospital’s actions in support of its implementation strategy:
| Action | Action Goal | Timeline | Measure | Measure Results | Owner | Partnered Organization(s)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Response 2 - Need 5
Response 2 - Need 5
Identified Health Need:
Identified Health Need Here
In CHNA
Yes, No, Newly Added
Implementation Strategy Included in submission?
Yes or No
The hospital’s actions in support of its implementation strategy:
| Action | Action Goal | Timeline | Measure | Measure Results | Owner | Partnered Organization(s)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Response 3
Response 3
A description of the direct funding and other resources allocated or expended that supported the actions taken in support of the hospital's implementation strategy.
In your description, please use the tab "Response 3 – Table 3." Note, you should provide a description for any actions that were inputted from Response 2. The actions you input in the Response 2 tabs will auto populate the Response 3 - Table 3 tab. For Response 2 Need 2 and Need 3, scroll down Table 3 (lines 56 and 108, respectively) to find the corresponding actions from Response 2 Need 2 and Need 3. For Table 3, column G (Community Benefit Part I Category), column H (Community Building Part II Category), and Column I (Why the action does not demonstrate community benefit or community building), indicate for each action the appropriate community benefit or community building category, or why the action did not demonstrate community benefit or building. For each action, only one column (G, H, I) should be filled out. For example, it is not appropriate for column G and I to be filled out on the same row. Applicable community benefit and community building categories are provided in column K (Response 3 - Table 3 tab). Answers that do not include the above information are incomplete.

## Response 3 - Table 3
Response 3 - Table 3
[6 empty] | Indicate with the appropriate category if the action demonstrated Part I, Part II, or if the action did not demonstrate community benefit or building and why |  |  | *Applicable Community Benefit Part I Categories: Financial Assistance at Cost, Medicaid, Other means-tested government programs, community health improvement services and community benefit operations, health professions education, subsidized health services, research, and cash and in-kind contributions for community benefit.
| Hospital Action in support of the hospital’s Implementation Strategy | Direct Funding Allocated ($) | Direct Funding Allocated Description | Other Resources Allocated ($) | Other Resources Allocated Description | Community Benefit Part I Category* | Community Building Part II Category** | Why the action does not demonstrate community benefit or community building | **Applicable Community Building Part II Categories: physical improvements and housing, economic development, community support, environmental improvements, leadership development and training for community members, coalition building, community health improvement advocacy, workforce development, and other.
Response 2 - Need 1
1 | Utilize American Heart Association's Life's Simple 7
2 | Design a KYN campaign targeted to adults ages 18-49
3 | Determine effectiveness of KYN screenings in their current sites and work with task force partners to make adjustments as needed based on data available |  |  | 1097 | staff hours | Community Health Improvement
4 | Continue to partner with community health workers to link KYN participants to follow-up care
5 | Determine effectiveness of expanding KYN to include hAlc screenings and practice providing automated BP cuffs for ongoing BP monitoring and expand where feasible
6 | St. Vincent’s will enhance the existing blood pressures screenings in the lobby to provide free automated blood pressure cuffs with education on usage and tracking guides to those people who screen >135 systolic or >85 diastolic.
7 | Determine barriers related to access to available free and low - cost fitness opportunities and develop ways to address these
8 | Continue to work towards regional Bike Share programs and promote/support safe biking/walking in neighborhoods through complete streets policies, partnerships with police/law enforcement, planning and zoning, and other city/town officials
9 | Develop an educational campaign around e-cigarettes/vaping
10 | Identify local youth prevention coalitions and collaborate to track vaping usage in youth
11 | Promote Tobacco 21 ordinance roll out in the City of Bridgeport and support the passage of local ordinances or state laws around Tobacco 21
12 | Promote local tobacco cessation resources
13 | Evaluate implementing prescription to fruit and vegetable programs |  |  | 3539 | staff hours for farm stand | Community Health Improvement
14 | Invite the CT Food Bank Mobile Pantry to distribute free food from the St. Vincent’s parking lot once monthly |  |  | 103235 | staff hours, food purchases | Community Health Improvement
15 | Determine national best practices for addressing social determinants of health as related to healthy lifestyles and decreasing hypertension and diabetes
16 | Start to build partnerships to work towards addressing SDOH, potential areas include Adverse Childhood Experiences (ACES), advocacy around increasing the minimum wage, WIC and SNAP acceptance in more venues.
17 | Staff salaries for individuals whose sole responsibility is coordinating, providing and reporting community benefits (100%) as well as percentage of time for staff that has dedicated a portion of their time for community benefits reporting. Staff time dedicated to advancing CHNA/CHIP actions and priorities. | 348331.67 | staff salaries |  |  | CB operations
18 | Continue to co-lead the HIA, including Steering Committee monthly meeting, communications committee meetings, tracking and evaluation committee, planning meeting
19 | Staff attend Healthy LifestylesTask Force meetings
20 | Staff co-chairs Task Force meeting
21 | 0
22 | 0
23 | 0
24 | 0
25 | 0
26 | 0
27 | 0
28 | 0
29 | 0
30 | 0
31 | 0
32 | 0
33 | 0
34 | 0
35 | 0
36 | 0
37 | 0
38 | 0
39 | 0
40 | 0
41 | 0
42 | 0
43 | 0
44 | 0
45 | 0
46 | 0
47 | 0
48 | 0
49 | 0
50 | 0
| Total Need 1 | 348331.67 |  | 107871
Response 2 - Need 2
1 | Determine how to best educate the community about the importance of having a medical home, particularly in the young adult population and implement strategies as appropriate
2 | Promote available medical services in the region
3 | Collaborate to increase referrals from partner organizations to primary care providers
4 | In collaboration with Southwest Community Health Center, (formerly St. Vincent’s Family Health Center), we conduct primary care clinics which are staffed by our Internal Medicine Residents, as a major component to their education. This is located on Lindley Street in Bridgeport. In this model of care, patient are assigned to a specific Resident, who acts as the PCP in collaboration with Boarded Physician Educators who lead this program. This promotes continuity of care for the patient and therefore enhances the quality of that care, as they identify with whom they establish an ongoing and trusted rapport. |  |  | 1350961 | Staff the Family Health Center | Subsidized Health Servces
5 | We at SVMC, through our Foundation, provide an annual venue that we call our Medical Mission at Home. This is held in Bridgeport at a local school. We have multiple volunteers who provide healthcare t many levels. There is biometric testing, nursing and physician evaluation and exams, vaccinations, pharmacy, distribution of needed items:(reading glasses, winter coats, shoes and sox, toiletries) pastoral care support, and lunch. It is open to the community without a scheduled appointment. Last year, we embraced just about 400 patients. The community benefit to population management is that both SVMC and SWCHC are on-site to refer patients to PCP services at both entities. We are working to establish an on-going rapport with a PCP for their healthcare delivery. We have videos that we could share with you. |  |  | 82779 | staff hours | Community Health Improvement
6 | St. Vincent’s Medical Center has established a central call center to improve ease of scheduling an appointment at any of our SVMC/ MSG sites.
7 | Produce and distribute educational materials on the importance of dental care
8 | Promote available dental services in the region
9 | Continue to improve and expand the dental referral system between partner organizations
10 | Advocate for improved dental insurance coverage
11 | Because of the collaborative efforts between SVMC and SWCHC, patients now have access to Dental services through SWCHC. There has been an enhanced emphasis on dental health and hygiene for our community as a result this collaboration.
12 | Identify gaps in specialty care access for Medicaid and uninsured patients and investigate ways to increase availability and access
13 | Collaborate with specialty care providers to increase the number of providers who accept Medicaid and uninsured patients
14 | By transferring the Family Health Center to SWCHS, an FQHC site, we were able to re-purpose our financial resources to create, grow and better staff specialty clinics which are offered at 2979 Main Street in Bridgeport. We have increased the number of hours and days, as well as, introduced new services such as Orthopedics (3 full days per week), Plastic Reconstructive Surgery, Infectious Disease, G.I. and Nephrology. This has been a tremendous addition to population health management.
15 | Continue to be involved in the state medical transportation efforts and share local experiences at the state level
16 | Continue communications with Veyo and invite them to task force meetings for quarterly updates and communicate those updates with partners organizations
17 | Determine accessibility of additional medical transportation options, including public transportation and medical ride programs and develop strategies based on this assessment |  |  | 125484 | transportation, patient access to care | Community Health Improvement
18 | Both the SWCHC facility and the St. Vincent’s Family Health Center Specialty Clinic are located on major bus routes. This provides for greater ease of access to both primary and specialty care clinics.
19 | Complete a CLAS assessment with local partner organizations to determine current gaps and implement CLAS strategies as needed
20 | Collect CLAS implementation tools and disseminate within partner organizations within Access to Care and throughout HIA organizations
21 | Continue to grow CLAS to meet the specific needs of the patients in our area and satisfy population health management resources.
22 | Staff salaries for individuals whose sole responsibility is coordinating, providing and reporting community benefits (100%) as well as percentage of time for staff that has dedicated a portion of their time for community benefits reporting. Staff time dedicated to advancing CHNA/CHIP actions and priorities. | 348331.67 | staff salaries |  |  | CB operations
23 | Continue to operate the Hope Pharmacy |  |  | 297522 | operations and staffing | Subsidized Health Servces
24 | Continue to co-lead the HIA, including main monthly meeting, communications committee meetings, tracking and evaluation committee, planning meeting
25 | Staff attend Access to Care Task Force meetings
26 | Staff co-facilitates Task Force meeting
27 | 0
28 | 0
29 | 0
30 | 0
31 | 0
32 | 0
33 | 0
34 | 0
35 | 0
36 | 0
37 | 0
38 | 0
39 | 0
40 | 0
41 | 0
42 | 0
43 | 0
44 | 0
45 | 0
46 | 0
47 | 0
48 | 0
49 | 0
50 | 0
| Total Need 2 | 348331.67 |  | 1856746
Response 2 - Need 3
1 | Align resources and build collaboration between organizations to increase access and awareness to community health workers and peer support specialists
2 | Participate in funding opportunities such as BUILD Health
3 | Develop strategies to link clinical and non-clinical services
4 | Establish or expand mobile or community based resource in the greater Bridgeport area
5 | Educate providers on resources (physicians, hospitals, others)
6 | Develop strategy to educate the general community on available resources for non-crisis services
7 | Develop strategy to educate the general community on available resources for crisis services
8 | Develop strategies to reach selected communities (youth, young adult, elderly, etc.)
9 | Refine Bridgeport Care Coordination Team (CCT)
10 | Improve attendance at meetings and involvement of organizations
11 | Establish a dedicated patient navigator for CCT
12 | Improve information sharing across organizations
13 | Track outcomes and share results on a quarterly basis
14 | Evaluate state and local best practices for improvement of CCT including re-establishing participation in Health and Housing stability work group
15 | Ensure smooth operation and timeliness of meetings of the Task Force.
16 | Staff salaries for individuals whose sole responsibility is coordinating, providing and reporting community benefits (100%) as well as percentage of time for staff that has dedicated a portion of their time for community benefits reporting. Staff time dedicated to advancing CHNA/CHIP actions and priorities. | 348331.67 | staff salaries |  |  | CB operations
17 | Continue to co-lead the HIA, including main monthly meeting, communications committee meetings, tracking and evaluation committee, planning meeting
18 | Staff attend Behavioral Health Task Force meetings
19 | Staff facilitates Task Force meeting
20 | 0
21 | 0
22 | 0
23 | 0
24 | 0
25 | 0
26 | 0
27 | 0
28 | 0
29 | 0
30 | 0
31 | 0
32 | 0
33 | 0
34 | 0
35 | 0
36 | 0
37 | 0
38 | 0
39 | 0
40 | 0
41 | 0
42 | 0
43 | 0
44 | 0
45 | 0
46 | 0
47 | 0
48 | 0
49 | 0
50 | 0
| Total Need 3 | 348331.67 |  | 0
Response 2 - Need 4
1 | 0
2 | 0
3 | 0
4 | 0
5 | 0
6 | 0
7 | 0
8 | 0
9 | 0
10 | 0
11 | 0
12 | 0
13 | 0
14 | 0
15 | 0
16 | 0
17 | 0
18 | 0
19 | 0
20 | 0
21 | 0
22 | 0
23 | 0
24 | 0
25 | 0
26 | 0
27 | 0
28 | 0
29 | 0
30 | 0
31 | 0
32 | 0
33 | 0
34 | 0
35 | 0
36 | 0
37 | 0
38 | 0
39 | 0
40 | 0
41 | 0
42 | 0
43 | 0
44 | 0
45 | 0
46 | 0
47 | 0
48 | 0
49 | 0
50 | 0
| Total Need 4 | 0 |  | 0
Response 2 - Need 5
1 | 0
2 | 0
3 | 0
4 | 0
5 | 0
6 | 0
7 | 0
8 | 0
9 | 0
10 | 0
11 | 0
12 | 0
13 | 0
14 | 0
15 | 0
16 | 0
17 | 0
18 | 0
19 | 0
20 | 0
21 | 0
22 | 0
23 | 0
24 | 0
25 | 0
26 | 0
27 | 0
28 | 0
29 | 0
30 | 0
31 | 0
32 | 0
33 | 0
34 | 0
35 | 0
36 | 0
37 | 0
38 | 0
39 | 0
40 | 0
41 | 0
42 | 0
43 | 0
44 | 0
45 | 0
46 | 0
47 | 0
48 | 0
49 | 0
50 | 0
| Total Need 5 | 0 |  | 0
| Total Direct Funding and Other Resources | 1044995.01 |  | 1964617

## Appendix A - Definitions
Definitions
Community benefit partners means federal, state and municipal government entities and private sector entities, including, but not limited to, faith-based organizations, businesses, educational and academic organizations, health care organizations, health departments, philanthropic organizations, organizations specializing in housing justice, planning and land use organizations, public safety organizations, transportation organizations and tribal organizations, that, in partnership with hospitals, play an essential role with respect to the policy, system, program and financing solutions necessary to achieve community benefit program goals.
Community benefit program means any voluntary program or activity to promote preventive health care, protect health and safety, improve health equity and reduce health disparities, reduce the cost and economic burden of poor health and improve the health status for all populations within the geographic service areas of a hospital, regardless of whether a member of any such population is a patient of such hospital.
Community benefit program reporting means the community health needs assessment, implementation strategy and annual report submitted by a hospital to the Office of Health Strategy pursuant to the provisions of this section.
Community health needs assessment means a written assessment, as described in 26 CFR 1.501(r)-(3).
Health disparities means health differences that are closely linked with social or economic disadvantages that adversely affect one or more groups of people who have experienced greater systemic social or economic obstacles to health or a safe environment based on race or ethnicity, religion, socioeconomic status, gender, age, mental health, cognitive, sensory or physical disability, sexual orientation, gender identity, geographic location or other characteristics historically linked to discrimination or exclusion.
Health equity means that every person has a fair and just opportunity to be as healthy as possible, which encompasses removing obstacles to health, such as poverty, racism and the adverse consequences of poverty and racism, including, but not limited to, a lack of equitable opportunities, access to good jobs with fair pay, quality education and housing, safe environments and health care.
Hospital means a nonprofit entity licensed as a hospital pursuant to chapter 368v that is required to annually file Internal Revenue Service form 990. “Hospital” includes a for-profit entity licensed as an acute care general hospital.
Implementation strategy means a written plan, as described in 26 CFR 1.501(r)-(3), that is adopted by an authorized body of a hospital and documents how such hospital intends to address the needs identified in the community health needs assessment.
Meaningful participation means that (A) residents of a hospital's community, including, but not limited to, residents of such community that experience the greatest health disparities, have an appropriate opportunity to participate in such hospital's planning and decisions, (B) community participation influences a hospital's planning, and (C) participants receive information from a hospital summarizing how their input was or was not used by such hospital.

## Appendix B - Example Responses
Response 1A
A description of major updates regarding community health needs, priorities and target populations, if any.
Major updates
Community Health Needs | • Adding Substance Use Disorders as a high priority o After further discussions with the community collaborative, the hospital has decided to make substance use disorder a high priority given new data outlining the issue in the surrounding neighborhoods (data appended)
Priorities | The only change in priority is the newly added Substance Abuse Disorder.
Target Populations | Substance Abuse Disorder added two new neighborhoods • The Narrows neighborhood • The Meadows neighborhood
Response 1B
A description of any major changes to the proposed implementation strategy from the most recently submitted implementation plan and associated hospital actions.
Major changes to the implementation strategy and associated hospital actions
#1 | Dr. John Snow is no longer overseeing the hospital’s action to increase protective factors for children relating to Social Determinants of Health. This is due to Dr. Snow retiring. Dr. Elizabeth Blackwell is now overseeing the hospital’s action.
#2 | The hospital found that greater than 35% of homes in the hospital’s primary service area are food insecure. The hospital is increasing each grant award to $75,000 for community-based organizations to partner with the hospital and establish community gardens, provide educational resources and supplies, establish rules in writing, and execute on sustainability plan.
#3
#4
#5
#6
#7
#8
#9
#10
Response 2
A description of progress made regarding the hospital's actions in support of its implementation strategy.
Response 2 - Need 1
Identified Health Need:
Food Insecurity
In CHNA
Yes
Implementation Strategy Included in submission?
Yes
The hospital’s actions in support of its implementation strategy:
Action | Action Goal | Timeline | Measure | Measure Results | Owner | Partnered Organization(s)
Grants provided to community based organizations (CBO) | Increase by 50% homes that are food secure | October 1, 2021 - September 30, 2022 | Survey based on USDA measures "high food security," "marginal food security," "low food security," and "very low food security." Increase 50% of households identified as low food security or very low food security to marginal food security or high food security. | 40% increase | Giada De Laurentis, BSN, RN | Better Together Charity Local Health Department Food Bank of Gotham
Response 3
A description of the direct funding and other resources allocated or expended that supported the actions taken in support of the hospital's implementation strategy.
Response 3 - Table 3
Indicate with the appropriate category if the action demonstrated Part I, Part II, or if the action did not demonstrate community benefit or building and why
Hospital Action in support of the hospital’s Implementation Strategy | Direct Funding Allocated ($) | Direct Funding Allocated Description | Other Resources Allocated ($) | Other Resources Allocated Description | Community Benefit Part I Category* | Community Building Part II Category** | Why the action does not demonstrate community benefit or community building
Response 2 - Need 1
Grants provided to community based organizations (CBO) | 300000 | 3 grants awarded at $100,000 each | 25000 | In-kind staff time for 3 employees working on grants | Cash and in-kind contributions for community benefit