## Slide 1
April 19, 2012
Quarterly Meeting
Partner with Stakeholders to
Drive Innovation and Smart Growth
CJIS Governing Board

## Slide 2
CJIS Goals and Objectives
CISS Project Plan
CISS Requirements
CJIS Program Management
CIDRIS Status
OBTS Status
Information Any Way You Want It
Agenda

## Slide 3
CJIS Goals and Objectives
Provide each agency the IT autonomy to achieve their business goals
Optimize existing IT investments and infrastructure within CJIS agencies
Develop a universal adaptor (dial tone) type service so that CJIS agencies can connect to Information Sharing (IS) system easily
Create a security model that meets State and federal standards
Provide services that are boringly predictable
Use the “Forced Multiplier” to help leverage existing resources to “do more with a lot less”

## Slide 4: CISS So Far . . .
Security Design Approved
Search Design Proceeding
  Analysis of Agency Data Sources and Connections
Overall System Architecture Review Drafted
Development of Proofs of Concepts Begun
Information Exchange Design Progressing
  Middleware Design and Training Materials
Notes: 4
4

## Slide 5
Connecticut’s Information Sharing System
(CISS)
DOC
OBTS
PRAWN
OBIS
CRMVS
CIB
ETC…
SOR
RMS
RMS
RMS
DMV
BOPP
DPDS
DESPP
CPCA
DCJ
Courts
LEAs
CISS Will Look Like This . . .
OVA
CSSD

## Slide 6: CISS Delivery Sequence
December 2012
Uniform Arrest Report
March 2013
Infractions
Judicial Common
Exchanges
Post Arrest
Disposition
Post Judgment
Misdemeanors
Arraignment, 1st
Appearance
Establish Framework
& Infrastructure
July 2012
Proofs of Concepts
Initial “Portal” OBTS Search
September 2012

## Slide 7: Executing Search Query
Simple keyword search
Natural language
(John Does’ with blue eyes)
Wildcard search
Advanced Search
(Refine results based on selected parameters)

## Slide 8: Search Results
-----------------------------------
-----------------------------------
-----------------------------------
Custom Refiners
Internet Search Layout
Grid Layout
Table Layout
Refine Results (blue eyes)
Results with blue eyes
Sorting Options
Pagination

## Slide 9: Result Details
Warrant

## Slide 10
Federated Search Results
Table Layout
Pagination

## Slide 11: CISS Development Milestones
Phase | JFM | A | M | J | J | A | S | O | N | D | J | F
Infrastructure |  |  |  |  |  |  |  |  |  |  |  | 
Requirements - Wave 1 |  |  |  |  |  |  |  |  |  |  |  | 
Proof of Concepts Design |  |  |  |  |  |  |  |  |  |  |  | 
Requirements - Wave 2 |  |  |  |  |  |  |  |  |  |  |  | 
POC Development |  |  |  |  |  |  |  |  |  |  |  | 
Design OBTS Search and Portal |  |  |  |  |  |  |  |  |  |  |  | 
Develop OBTS Search and Portal |  |  |  |  |  |  |  |  |  |  |  | 
Design Uniform Arrest Workflow |  |  |  |  |  |  |  |  |  |  |  | 
Acceptance OBTS Search/Portal |  |  |  |  |  |  |  |  |  |  |  | 
Develop UAR Workflow |  |  |  |  |  |  |  |  |  |  |  | 
Deploy OBTS Search/Portal |  |  |  |  |  |  |  |  |  |  |  | 
Acceptance UAR Workflow |  |  |  |  |  |  |  |  |  |  |  | 
Deploy UAR Pilot |  |  |  |  |  |  |  |  |  |  |  | 
Deploy UAR Full |  |  |  |  |  |  |  |  |  |  |  | 
Design Infractions Workflow |  |  |  |  |  |  |  |  |  |  |  | 
Develop Infractions Workflow |  |  |  |  |  |  |  |  |  |  |  | 
Acceptance Infractions Workflow |  |  |  |  |  |  |  |  |  |  |  | 
Primarily ACS Team
Primarily State
Team
(There is Only One Team)

## Slide 12: CISS – The Next Three Months
Design Process is Underway
  Security Design: April Completion
  Middleware Design: April Completion
  Search Design: May Completion
  Initial Portal Design: May Completion
Workflows, Searches and Information Exchanges
  Requirements and Design in Waves
  Detailed Design Follows Requirements Approval
Project Plan
  Published at Least Quarterly
  Always Looking Out 9-12 Months
Notes: 12
12

## Slide 13: CISS Requirements
Requirements Validation
  Workflow requirements
    8 Workflow diagrams approved
  Reports and Forms Validation
    5/31/2012
Agency Source System Technical Documentation
  Document agency source systems by 4/30/2012
  Validate CT RMS installations by 4/25/2012
Field Observations to Document Agency Business Processes
  Planning is underway; tentatively May and June

## Slide 14
CISS Tasks | April |  |  |  | May |  |  |  | June |  |  | 
 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25
Technical Discovery: |  |  |  |  |  |  |  |  |  |  |  | 
Judicial Branch |  |  |  |  |  |  |  |  |  |  |  | 
Department of Corrections |  |  |  |  |  |  |  |  |  |  |  | 
Board of Pardons & Paroles |  |  |  |  |  |  |  |  |  |  |  | 
Department of Criminal Justice |  |  |  |  |  |  |  |  |  |  |  | 
Department of Emergency Services & Public Protection |  |  |  |  |  |  |  |  |  |  |  | 
Division of Public Defender Services |  |  |  |  |  |  |  |  |  |  |  | 
Department of Motor Vehicles |  |  |  |  |  |  |  |  |  |  |  | 
CT Police Chiefs Association |  |  |  |  |  |  |  |  |  |  |  | 
CISS Reports & Forms |  |  |  |  |  |  |  |  |  |  |  | 
Statewide RMS |  |  |  |  |  |  |  |  |  |  |  | 
Agency Field Observations |  |  |  |  |  |  |  |  |  |  |  | 
CISS Business Milestones

## Slide 15
CJIS Program Management
Program
Management Plan
Identify
Implementation
Team
Develop Program
Integration
Standards and
Processes
Develop
Implementation
Schedule
Develop
Testing
Plan
Develop
Change
Management
Plan
Develop
Communications
Plan
Develop
CJIS Security
Solution
Develop
Training
Plan
Gather and
Report Lessons
Learned
Establish
Program Office,
Define
Governance
CJIS Governing Board
Strategic Plan
CJIS Business Objectives /
Goals
Governor’s Vision for
Technology

## Slide 16: CJIS Project Management Office Milestones
PMO Setup | JFM | A | M | J | J | A | S | O | N | D | J | F
Establish Program Office - Define Governance |  |  |  |  |  |  |  |  |  |  |  | 
Budget |  |  |  |  |  |  |  |  |  |  |  | 
Identify Implementation Team |  |  |  |  |  |  |  |  |  |  |  | 
Develop Communications Plan |  |  |  |  |  |  |  |  |  |  |  | 
3rd Quarter Implementation Schedule |  |  |  |  |  |  |  |  |  |  |  | 
Develop Change Mgmt. Plan |  |  |  |  |  |  |  |  |  |  |  | 
Risk/Issue Mgmt. Plan |  |  |  |  |  |  |  |  |  |  |  | 
Develop Quality Mgmt. Plan |  |  |  |  |  |  |  |  |  |  |  | 
Implement Project Management in Jazz |  |  |  |  |  |  |  |  |  |  |  | 
Update CJIS Security Plan |  |  |  |  |  |  |  |  |  |  |  | 
Master Project Plan & Sub Plans: CISS, OBTS, CIDRIS |  |  |  |  |  |  |  |  |  |  |  | 
CISS Success Metrics |  |  |  |  |  |  |  |  |  |  |  | 
Service Level Agreement with DAS-BEST |  |  |  |  |  |  |  |  |  |  |  | 
CJIS GB Strategic Plan |  |  |  |  |  |  |  |  |  |  |  | 
Completed
Target Completion Date

## Slide 17: CJIS Communication Plan
Updated CJIS Monthly Newsletter
First Issue in May as an Electronic Publication to all CJIS Stakeholders
Governing Board
Executive Summary, Progress, User Feedback, Plain Talk and Tech Talk
CJIS Community Surveys
OBTS, CISS, CIDRIS
Quarterly Report
Quarterly Presentation
Identify Areas for Improvement

## Slide 18
Watch for the debut of CJIS Roadmap coming to an inbox near you

## Slide 19: Performance Metrics
11 Strategic Metrics
21 Operational Metrics
9 Tactical Metrics
Roll-up to Executive Dashboard

## Slide 20: CIDRIS - Accomplishments
Deployment
Deployed Troop B, Troop L, with Troop A next
UAR for OUI arrests w/criminal charges
Deploy the rest of the Troops over the next few months based on the new draft DESPP schedule
Added companion UAR for OUI arrests that also have criminal charges
Testing with DESPP, DMV, and Judicial
Validation Programming and Improved Training
DESPP and NexGen have added additional validation programming to reduce errors sent to CIDRIS
DESPP is improving their training

## Slide 21: CIDRIS – The Next Three Months
Deployment
Work with Judicial, DESPP, and DMV to accelerate deployment schedule for remaining troops
Paperless OUIs
Judicial, DESPP, and DMV
Transition to permanent application maintenance and support to the CJIS Operations Team
Application Maintenance & Support
Develop needed Technology
Develop needed Business Processes

## Slide 22: OBTS Accomplishments
7.1 QUARTERLY RELEASE
The Offender Based Tracking System (OBTS) team completed and implemented the February OBTS 7.1 quarterly release on schedule
SYSTEM PERFORMANCE
Event Processing Improvements – Rate of 6,800 messages per hour exceeded with no backlogs
Data Integrity Enhancements
Inquiry Processing Improvements – 65% Average increase in response time
Notes: User Group Meeting
Introductions
OBTS/CDIRIS/CISS Overview
Provides Open Forum for Feedback and Information Sharing

## Slide 23
Chart: 
| Exact Name - George Lopez | Exact Name - Gary Roundtree | Exact Name - John Smith | Exact Name - Luis Rivera
3/7 Production Baseline | 106 | 93 | 432 | 1140
4/13 Production Baseline | 28 | 16 | 139 | 180
Exact Name Search
Smart Name Search
Chart: 
| Smart Name - Natalie Lorentson | Smart Name - Robert Ready | Smart Name - Latosha Black | Smart Name - Luis Salto
3/7 Production Baseline | 5 | 1200 | 900 | 900
4/13 Production Baseline | 1 | 215 | 1 | 342
Seconds
Seconds

## Slide 24
Full Docket Search
Partial Docket Search
Chart: 
| F02BCR110258416S | H17BCR110048449S | K21NCR110116085S | W11DMV100221818S
3/7 Production Baseline | 4 | 6 | 7 | 2
4/13 Production Baseline | 1 | 1 | 6 | 5
Chart: 
| Partial Docket 317546 | Partial Docket 168153 | Partial Docket 649687 | Partial 262050 | Average Seconds
3/7 Production Baseline | 2 | 3 | 19 | 3 | 6.75
4/13 Production Baseline | 2 | 3 | 14 | 1 | 5
Seconds
Seconds

## Slide 25: Accomplishments OBTS/CIDRIS/AFIS User Group
USER GROUP MEETINGS
The first User Group Meeting was held on February 21st at the Department of Emergency Services and Public Protection in Middletown. The User Group members included participants from the CJIS Team, CPCA, DESPP, DMV, DOC, local Law Enforcement Agencies (LEAs), and Judicial.
CONTINUOUS IMPROVEMENTS
The first OBTS “Help Us Help You” Survey has been distributed to the User Group for feedback in the areas of system usage, performance, data quality, and training.
Notes: User Group Meeting
Introductions
OBTS/CDIRIS/CISS Overview
Provides Open Forum for Feedback and Information Sharing

## Slide 26: Where We Are Now OBTS 7.2 – May Quarterly Release
Enhancements
Judicial
    New Verdict Finding
  System Performance
    Scheduler Optimization
    Code Fix for Quicker Indexing
    Improve Inquiry Response Times
Notes: The May 7.2 Release is under construction and we expect to include Enhancements and Mitigation Issues.
For Enhancements – Judicial is implementing anew Verdict Finding, NI – for Not Guilty by Reason of Insanity. This new verdict finding will assist the courts to better identify cases and charges with this finding. The Operational team will be making changes to OBTS to support the new verdict.
The Operational team is continuing their efforts in System Performance and identified three areas for improvements in this release. The Scheduler Optimization …………………………..
Proper Indexing …………………………
And continuing effort to optimize each of the underliny infrastructure components that support OBTS.

## Slide 27: Where We Are Now OBTS 7.2 – May Quarterly Release
Issues Mitigation
  Improve System Memory Resource Usage
  Message Console Stop and Start Correction
Enhancements
Judicial
    New Verdict Finding
  System Performance
    Scheduler Optimization
    Code Fix for Quicker Indexing
    Improve Inquiry Response Times
Notes: The May 7.2 Release is under construction and we expect to include Enhancements and Mitigation Issues.
For Enhancements – Judicial is implementing anew Verdict Finding, NI – for Not Guilty by Reason of Insanity. This new verdict finding will assist the courts to better identify cases and charges with this finding. The Operational team will be making changes to OBTS to support the new verdict.
The Operational team is continuing their efforts in System Performance and identified three areas for improvements in this release. The Scheduler Optimization …………………………..
Proper Indexing …………………………
And continuing effort to optimize each of the underlying infrastructure components that support OBTS.

## Slide 28: Where We Are Going Data Purity Initiative
Judicial
CRVMS
Corrections Dept.
OBIS
State Police
MNI/CCH
CIB
PRAWN
POR
OBTS

## Slide 29: Information Any Way You Want It
Sources-Information
Delivery-Device Independence
CISS
CIDRIS
OBTS
CISS
CIDRIS
OBTS
Office PC/Laptop
Tablets-iPad, Android, Google’s Ice Cream Sandwich
Mobile Phone-Any Smart Phone

## Slide 30: Information Any Way You Want It
Benefits
Ability to Make Good Decisions
Timely Information Available 24X7
Delivery to Your Preferred Device

## Slide 31
CJIS Project Status Dashboard

## Slide 33
Building Connecticut’s Information Sharing System