## Federal APDU Budget
DCF SACWIS Replacement Project
Federal APDU and Project Costs - Including Reimbursement of State Employee Salaries
Phase 1 - Initial Planning Stage
Creation of the APDU and Statement of Work
Initial Purchase of Equipment for VDI
Phase | Services/Equipment | Monthly Cost | Units | Total Phase Costs | Potential Revenue
1 | State Employee Resources | 83850 | 8 | 670800 | 603720
1 | KPMG- APDU & SOW | 167000 | 8 | 1336000 | 1202400
1 | Advantech-QA/Project Mgmt | 18750 | 8 | 150000 | 135000
1 | VDI Equipment Start up | 724000 | 1 | 724000 | 651600
| Phase 1 Total |  |  | 2880800 | 2592720
Phase 2 - Production Estimate
Creation of the System, Testing, Quality Assurance and Acceptance
Purchase of VDI Equipment and Worker Mobility Equipment
Phase | Services/Equipment | Monthly Cost | Units | Total Phase Costs | Potential Revenue
2 | State Employee Resources | 100000 | 36 | 3600000 | 2520000
2 | KPMG- APDU & SOW | 50000 | 36 | 1800000 | 1260000
2 | Advantech-QA/Project Mgmt | 18750 | 36 | 675000 | 472500
2 | VDI Equipment Start up | 4200000 | 1 | 4200000 | 2940000
2 | Worker Mobility Equipment | 4000000 | 1 | 4000000 | 2800000
2 | System Production | 650000 | 36 | 23400000 | 16380000
| Phase 2 Total |  |  | 37675000 | 26372500
| Phase 1 & 2 Total |  |  | 40555800 | 28965220

## State Projected Exp and Rev
DCF SACWIS Replacement Project
Projected State Budget for Phase 1 and 2 - Excluding State Employee Expenses and Revenues
Phase 1 - Initial Planning Stage
Creation of the APDU and Statement of Work
Initial Purchase of Equipment for VDI
Phase | Services/Equipment | Monthly Cost | Units | Total Phase Costs | Potential Revenue
1 | KPMG- APDU & SOW | 167000 | 8 | 1336000 | 1202400
1 | Advantech-QA/Project Mgmt | 18750 | 8 | 150000 | 135000
1 | VDI Equipment Start up | 724000 | 1 | 724000 | 651600
| Phase 1 Total |  |  | 2210000 | 1989000
Phase 2 - Production Estimate
Creation of the System, Testing, Quality Assurance and Acceptance
Purchase of VDI Equipment and Worker Mobility Equipment
Phase | Services/Equipment | Monthly Cost | Units | Total Phase Costs | Potential Revenue
2 | KPMG- APDU & SOW | 50000 | 36 | 1800000 | 1260000
2 | Advantech-QA/Project Mgmt | 18750 | 36 | 675000 | 472500
2 | VDI Equipment Start up | 4200000 | 1 | 4200000 | 2940000
2 | Worker Mobility Equipment | 4000000 | 1 | 4000000 | 2800000
2 | System Production | 650000 | 36 | 23400000 | 16380000
| Phase 2 Total |  |  | 34075000 | 23852500
| Phase 1 & 2 Total |  |  | 36285000 | 25841500