## CEPA Project Inventory
2026-02-17
Sponsoring Agency | Project Name | Project Location(s) | Scoping Notice Published | Deadline for Public Scoping Comments | Six-Month Update Due (Sec. 22a-1a-7 of the RCSA) | Project Status Update Published | Post-Scoping Notice Published | Environmental Impact Evaluation (EIE) Published | Agency Record of Decision (ROD) | OPM Determination of Adequacy | CEPA Process Cancelled | Notes
DOT | Exit 46, Route 15 Improvements | New Haven, Woodbridge | 2026-01-20 | 2026-02-19 | 2026-08-19
DECD | Mason Street East and West | Greenwich | 2026-01-20 | 2026-02-20 | 2026-08-20
DOT | MOVE New Haven - Bus Rapid Transit | Hamden, New Haven, West Haven | 2026-01-20 | 2026-03-05 | 2026-09-05 | [6 empty] | Originally scoped on 1/6/26, revised 1/20/26
DPH | Indian Springs Consolidation with the New Milford Regional System | Danbury, Brookfield | 2026-01-06 | 2026-02-06 | 2026-08-06
DPH | Kenosia Wells Water Treatment Facility | Danbury | 2026-01-06 | 2026-02-07 | 2026-08-07
DOT | Heroes Tunnel Rehabilitation | Hamden, New Haven, Woodbridge | 2025-12-16 | 2025-01-28 | 2026-07-28
UConn | UConn Golf Practice Facility Project | Mansfield | 2025-12-16 | 2026-01-16 | 2026-07-16
DOH | Windsor Locks Transit-Oriented Development (TOD) - Phases 1 and 2 | Windsor Locks | 2025-12-16 | 2026-01-16 | 2026-07-16
DOH | Pierson School Adaptive Reuse | Clinton | 2025-12-02 | 2026-01-02 | 2026-07-02
DEEP | Town of Coventry Water Pollution Control Facility (WPCF) | Coventry | 2025-11-18 | 2025-12-18 | N/A |  | 2026-02-03 | pending
DECD | Oyster Harbor Village | New Haven | 2025-11-18 | 2025-12-19 | 2026-06-19
DOH | Starr Winchester Homeownership | New Haven | 2025-11-18 | 2025-12-18 | 2026-06-18
DOH | River Ridge Apartments | Hamden | 2025-11-04 | 2025-12-04 | 2026-06-04
DOH | Judds Homestead | Fairfied | 2025-12-02 | 2026-01-02 | 2026-07-02 | [6 empty] | Originally scoped on 11/4/25, revised 12/2/25
CTMD | Army National Guard Aircraft Hangar Alteration/Addition | Groton | 2025-10-21 | 2025-11-20 | 2026-05-20
DOH | Bacon Congregate | Hartford | 2025-10-07 | 2025-11-07 | 2026-05-07
DOH | Hartford Trade School | Hartford | 10/7/2025 | 2025-11-07 | 2026-05-07
DPH | West Queen Street Water Main Interconnection | Southington | 2025-09-16 | 2025-10-16 | N/A |  | 2026-01-20
DPH | South Central Connecticut Regional Water Authority Rehabilitation of Lake Whitney Dam | Hamden | 2025-09-16 | 2025-10-16 | 2026-04-16
DPH | Ridgefield High School and Middle School Interconnection | Ridgefield | 2025-09-02 | 2025-10-02 | N/A |  | 2026-01-20
DEEP | Proposed Modification of Easements to Allow a 199-psig Natural Gas Distribution Pipeline Within Portions of Hurd State Park and Connecticut Valley Railroad State Park Trail | Middletown, Haddam/Higganum, and East Hampton | 2025-08-19 | 2025-09-18 | 2026-03-18
DPH | Jewett City Water Company Storage Tank and Pumping Station | Griswold | 2025-08-19 | 2025-09-19 | N/A |  | 2026-01-06
DPH | Berlin and Meriden Interconnection | Berlin | 2025-08-19 | 2025-09-19 | N/A |  | 2026-01-06
DECD | Former Windsor Street Data Center | Hartford | 2025-08-05 | 2025-09-04 | N/A |  | 2025-10-07
DOH | Horizon View | Montville | 2025-08-05 | 2025-09-05 | 2026-03-05
DECD | 113 & 125 Canal Street | Shelton | 2025-07-22 | 2025-08-22 | N/A |  | 2025-10-07
DOH | The Homes at Avon Park | Avon | 2025-07-22 | 2025-08-22 | 2026-02-22
DOH | Windward Apartments | Bridgeport | 2025-07-08 | 2025-08-08 | 2026-02-08 | [6 empty] | Originally scoped on 6/17/25, revised 7/8/2025
UConn | UConn Boathouse Relocation Project | Coventry | 2025-05-20 | 2025-06-19 | N/A |  | 2025-10-21
DOH | Oak Woods | Plymouth | 7/3/2023 ¦ 2/6/2024 | 2024-03-06 | 2024-09-06 | [6 empty] | initial scoping notice published on 7/3/23. Rescoped in 2/6/24.
DOH | 2980 State Street | Hamden | 2025-05-20 | 2025-06-20 | N/A |  | 2025-09-02
DEEP | Regional Composting Facility and Recycling Infrastructure | Manchester | 2025-05-20 | 2025-06-19 | N/A |  | 2025-07-22 | 2025-11-18 | 2026-01-20 |  |  | EIE originally posted 10/21/2025, revised 11/18/2025
DEEP | Regional Composting Facility and Recycling Infrastructure | Kent, Ridgefield | 2025-05-20 | 2025-06-19 | N/A |  | 2025-07-22 | 2026-01-20 |  |  |  | EIE originally posted 9/16/2025, revised 11/18/2025, revised 1/20/2026
DEEP | Regional Composting Facility and Recycling Infrastructure | Kent, Ridgefield | 2025-05-20 | 2025-06-19 | N/A |  | 2025-07-22
DAS | Capital Area System Central Plant Upgrades | Hartford | 6/6/2023 ¦ 6/20/2023 | 2023-07-07 | N/A | 2024-07-16 | 2025-01-21 |  |  |  |  | estimating update approx. June 2024
DEEP | Building a Regional Composting Facility for Southeastern Connecticut | Preston | 2025-05-20 | 2025-06-19 | N/A |  | 2025-07-22 | 2025-11-18 | 2026-01-20 |  |  | EIE originally posted 9/16/2025, revised 11/18/2025
DMHAS | Connecticut Valley Hospital Solar Project at Eddy Home | Middletown | 2025-05-20 | 2025-06-20 | 2026-07-06 | 2026-01-06
DECD | Enfield Station Brownfield Remediation | Enfield | 2025-05-06 | 2025-05-22 | N/A |  | 2025-11-18 |  |  |  |  | Originally scoped on 4/22/25, revised 5/6/25.
DEEP | Franklin Water & Sewer Extension | Franklin | 2025-04-22 | 2025-05-22 | N/A |  | 2025-08-05 | pending
DECD | Town of Griswold Route 164 Water Main Extension | Griswold | 2025-06-03 | 2025-06-19 | 2025-12-19 | [6 empty] | Originally scoped on 4/22/25, revised 5/20/25 and again on 6/3/25
DECD | Park Hill and School Hill Water Line Extension | East Windsor | 2025-04-08 | 2025-05-08 | 2025-11-08
DECD | Woodland Pacific | Stamford | 2025-02-18 | 2025-03-21 | N/A |  | 2025-07-22
DECD | CTSG Shoreline Soccer Remediation and Redevelopment | Bridgeport | 2024-11-05 | 2024-12-05 | N/A |  | 2025-04-08
DECD | AGI Site Remediation Project | Bridgeport | 2024-11-05 | 2024-12-05 | N/A |  | 2025-04-08
DOH | 45 Meadow Street | Norwalk | 2024-10-08 | 2024-11-08 | N/A |  | 2025-07-22
DEEP | Tunxis Hill Park Flood Control Project | Fairfield | 2024-09-17 | 2024-10-17 | N/A |  | 2025-01-21
DEEP | Fairchild Wheeler Flood Control Project | Fairfield | 2024-09-17 | 2024-10-17 | N/A |  | 2025-01-21
DOH | Parcel B | Naugatuck | 2024-09-03 | 2024-10-03 | 2025-04-03
DPH | Connecticut Water Company Green Springs System Consolidation | Madison | 2024-08-20 | 2024-09-20 | N/A |  | 2024-10-22
DEEP | Town of Vernon Exit 67 Sanitary Sewer Extension | Vernon | 2024-08-06 | 2024-09-05 | N/A |  | 2024-11-05
DPH | Portland Water Department Development of Public Drinking Water Infrastructure | Portland | 2024-08-06 | 2024-09-06 | N/A |  | 2024-10-08
DOH | 122 Wilton Road | Westport | 2024-08-06 | 2024-09-06 | 2025-03-06
DOH | 1600 New Britain Avenue | Farmington | 2024-08-06 | 2024-09-06 | 2025-03-06
DOH | Cheshire Highland | Cheshire | 2024-08-06 | 2024-09-06 | 2025-03-06
DOT | Retaining Wall Replacement Along Route 44 | Putnam | 2024-07-16 | 2024-08-16 | N/A |  | 2024-11-05
DOH | The Elle at North Main | West Hartford | 2024-07-16 | 2024-08-16 | 2025-02-16
DOH | West Ridge Apartments | New Haven | 2024-07-02 | 2024-08-02 | 2025-02-02
DOH | Hanover Street Residences | Bridgeport | 2024-06-04 | 2024-07-04 | 2025-01-04
DOH | St. Edmunds Retreat - Septic System Repairs | Stonington | 2024-05-21 | 2024-06-21 | 2024-12-21
DOH | 10 Liberty Street | New Haven | 2024-05-07 | 2024-06-07 | N/A |  | 2024-11-05
DPH | Middlebury Commons Interconnection with CT Water Company Naugatuck Region | Middlebury | 2024-04-16 | 2024-05-16 | N/A |  | 2024-10-22
DOT | Removal of Traffic Signals on Route 9 [and Associated Improvements] | Middletown | 2024-04-16 | 2024-05-31 | 2026-01-08 | 2025-07-08 | [5 empty] | Name changed to include "and Associated Improvements" in the 5/7/2024 Environmental Monitor. Notice that public comment period would be extended until 5/31/2024 was published in the 5/21/2024 Environmental Monitor (previous deadline was 5/16/2024).
DOH | Jack's Farm | Cheshire | 2024-03-19 | 2024-04-19 | N/A |  | 2024-10-08
DECD | Science Park Tract A | New Haven | 2024-03-19 | 2024-04-18 | N/A |  | 2024-08-06
DECD | Coliseum Parcel 1C | New Haven | 2024-03-19 | 2024-04-18 | N/A |  | 2024-08-06
DOH | Oak Woods | Plymouth | 2024-02-06 | 2024-03-06 | 2024-09-06 | [6 empty] | Originally scoped 7/3/2023, revised 2/6/2024
DPH | Nathan Hale Systen Main Extension to Plains Road | Coventry | 2024-01-16 | 2024-02-16 | N/A |  | 2024-05-07
DECD | AB Eco Park Project | North Haven / New Haven | 2023-12-05 | 2024-01-04 | N/A | 2024-07-02 |  |  |  |  | 2024-09-17 | 9/17/2024 Notice of Cancellation
DOH | The Monarch | New Haven | 2023-12-05 | 2024-01-05 | N/A |  | 2024-08-06
DOH | Waltersville Commons | Bridgeport | 2023-12-05 | 2024-01-05 | N/A | 2024-08-20 | 2025-07-08
DOH | Oak Park (Phase 1) | Stamford | 2023-11-21 | 2023-12-21 | N/A |  | 2024-09-03
DOH | Church Street Commons | Hebron | 2023-11-21 | 2023-12-21 | 2025-02-20 | 2024-08-20
DECD | Former Scovil Mill Remediation Project | Haddam | 2023-11-07 | 2023-12-07 | N/A |  | 2024-03-05
DOT | Naugatuck Railroad Station Relocation | Naugatuck | 2023-10-17 | 2023-11-29 | N/A | 2024-05-21 | 2024-09-03
DOT | Relocation of Route 8 Southbound (SB) Interchange 34 | Waterbury | 2023-10-17 | 2023-11-30 | N/A | 2024-05-21 | 2024-08-20
DOH | State and Chapel Development | New Haven | 2023-10-17 | 2023-11-17 | N/A |  | 2024-05-21
UConn | Coventry Boathouse Upgrades Project - REVISED Scoping Notice | Coventry | 2023-10-17 | 2023-11-07 | N/A | [6 empty] | project cancelled - will rescope as needed - https://updc.uconn.edu/boathouse/
DECD | Return to the Riverbend | Middletown | 2023-10-03 | 2023-11-02 | N/A |  | 2024-05-07
DOH | MLK Tyler | New Haven | 2023-09-19 | 2023-10-19 | N/A |  | 2024-05-07
DECD | Belding Mill Redevelopment Project | Putnam | 2023-09-19 | 2023-10-19 | N/A |  | 2024-03-05
DOT | Replacement of Bridge No. 00853, Route 16 over Salmon River | East Hampton | 2023-09-19 | 2023-10-19 | N/A |  | 2025-07-08
DOH | 85 Tremont St | Meriden | 2023-08-22 | 2023-09-22 | N/A |  | 2024-04-16
DECD | Business Park North | Norwich | 2023-08-08 | 2023-09-07 | N/A |  | 2025-05-06 |  |  |  |  | Original post-scoping notice on 4/8/25 - revised on 5/6/25 to remove references to future EIE
DOH | The Camelot Flats and Lofts | West Hartford | 2023-08-08 | 2023-09-08 | N/A | 2024-04-16 | 2024-10-08
UConn | New School of Nursing Building | Mansfield | 2023-08-08 | 2023-09-08 | N/A | 2024-03-05 | 2024-05-07
DOH | Wall Street Place | Norwalk | 2023-08-08 | 2023-09-08 | N/A |  | 2024-04-02
DOH | MLK Apartments | Hartford | 2023-08-08 | 2023-09-08 | N/A |  | 2024-03-19
DOH | 80 South Road | Farmington | 2023-08-08 | 2023-09-08 | N/A |  | 2024-03-19
DOH | Ellis Street Commons | New Britain | 2023-07-03 | 2023-08-03 | N/A |  | 2024-03-19
DOH | West Hartford Fellowship Housing Redevelopment Phase I | West Hartford | 2023-07-03 | 2023-08-03 | N/A |  | 2024-03-19
UConn | Whitney House Demolition at the University of Connecticut | Mansfield | 2023-07-03 | 2023-08-04 | N/A |  | 2023-10-03
DAS | Capitol Area System (CAS) Central Plant Upgrades | Hartford | 2023-06-20 | 2023-07-07 | N/A | 2/6/2024, 7/6/2024 | 2025-01-21 |  |  |  |  | Original scoping notice 6/6/2023; revised 6/20/203
DPH | Pleasant View Water Main Interconnection Project | New Milford | 2023-06-20 | 2023-07-20 | N/A |  | 2023-09-19
DECD | Webster Block Project | Norwalk | 2023-06-06 | 2023-07-06 | N/A |  | 2023-08-08
DOT | Track Improvement and Mobility Enhancement (Time-1): Metro North Railroad | Bridgeport, Stratford | 2023-04-04 | 2023-05-09 | 2024-05-07 | 2023-11-07 | [5 empty] | post-scoping notice anticipated on/before 2/20/24
DEEP | Barber Pond Dam Removal | Bloomfield | 2023-03-21 | 2023-04-20 | 2026-01-08 | 2025-07-08
DOT | Removal of Exit 21 Off-Ramp on Interstate 84 Eastbound (EB) | Waterbury | 2023-03-07 | 2023-04-10 | N/A |  | 2023-10-03
DPH | Interconnection of Montville and Seven Oaks | Montville | 2023-03-07 | 2023-04-06 | N/A |  | 2023-09-05
DPH | Cedar Heights Water Main Interconnection | Brookfield, Danbury | 2023-03-07 | 2023-04-06 | N/A |  | 2023-09-05
DPH | Craigmoor Water Main Interconnection | Ridgefield | 2023-03-07 | 2023-04-06 | N/A |  | 2023-09-05
DEEP | Seymour Reservoir No. 4 Dam Repair Project | Oxford | 2023-02-21 | 2023-03-24 | N/A |  | 2023-06-06
DECD | Bella Vista Apartments Project | Ansonia | 2023-02-07 | 2023-03-09 | N/A | [5 empty] | 2023-06-20 | 6/20/23 Notice of Cancellation
DPH | Durham Center Water System Main Extension | Durham, Middletown | 2023-01-17 | 2023-02-17 | N/A | 2024-02-06 |  |  |  |  | 2024-09-03 | 9/3/24 Notice of Cancellation
DECD | Former Ames Corporate Headquarters - Redevelopment Project | Rocky Hill | 2023-01-17 | 2023-02-16 | N/A |  | 2023-08-08
DECD | Elmwood Lofts - Municipal Brownfield Grant | West Hartford | 2022-12-06 | 2023-01-06 | N/A |  | 2024-06-18
DPH | Extension of Water Lines from Winsted into Barkhamsted | Barkhamsted | 2022-11-22 | 2022-12-22 | N/A |  | 2023-03-21
DEEP | Bozrah Sanitary Sewer Extension | Bozrah | 2022-11-08 | 2022-12-08 | N/A | 2023-05-16 | 2023-11-07 | 2023-11-21 | 2024-05-21 | 2024-07-02
DECD | River Mill Redevelopment Project | Thompson | 2022-11-08 | 2022-12-08 | N/A |  | 2023-08-08
DECD | Community Recreation Center Project | New London | 2022-11-08 | 2022-12-08 | N/A |  | 2023-06-06
DECD | Garfield Mills Remediation Project | New London | 2022-11-08 | 2022-12-08 | N/A |  | 2023-02-21
DECD | Former White Oak Remediation and Redevelopment Project | Plainville | 2022-11-08 | 2022-12-08 | N/A |  | 2023-02-21
DECD | Riverfront Park Trail & Commercial Development Project | Hartford, Windsor | 2022-11-08 | 2022-12-08 | N/A |  | 2023-02-21
DECD | Daniel’s Mill Adaptive Reuse and Remediation Project | Vernon | 2022-11-08 | 2022-12-08 | N/A |  | 2023-02-07
DECD | Steelpointe Harbor - Mixed-Use Development Project | Bridgeport | 2022-10-18 | 2022-11-17 | N/A |  | 2022-12-20
DPH | Norwalk First Taxing District - Grupes Dam Rehabilitation | New Canaan | 2022-09-06 | 2022-09-26 | N/A |  | 2023-03-21 |  |  |  |  | Initial scoping notice was published 7/5/2022 and it was reposted 9/6 to enable a public scoping meeting to be scheduled.
DAS | Sale and Transfer of Properties at 18-20 and 30 Trinity Street in Hartford | Hartford | 2022-07-19 | 2022-08-19 | N/A | 2024-07-16 | 2024-11-19 |  |  |  |  | earrlier update 2/6/2024
DOT | Rehabilitation of Bridge 00793A – Route 15 Northbound Over Quinnipiac River | Wallingford | 2022-07-19 | 2022-08-19 | N/A |  | 2023-02-07
DOT | Safety Improvements on Route 82 (Phase 1) | Norwich | 2022-06-07 | 2022-07-08 | N/A | 2024-03-05 | 2024-10-22
DOT | Elimination of Bridge Nos. 00388 and 00389 (Route 17) and Construction of Roundabout | Glastonbury | 2022-05-17 | 2022-06-27 | N/A |  | 2022-12-20
DOT | Revised Scope - Replacement of Bridge No. 00162 (I-95 over Metro North Railroad) and Bridge No. 00161 (I-95 over First Avenue) | West Haven | 2022-05-03 | 2022-06-03 | N/A |  | 2022-11-22
DOT | Intersection Improvements on Route 10 & 322, Removal of Bridge 00518 and Replacement of Bridges 00646 & 05753 | Southington, Cheshire | 2022-05-03 | 2022-06-03 | N/A |  | 2022-11-22
DPH | Cromwell Emergency Interconnections | Cromwell, Middletown, Berlin, Rocky Hill | 2022-03-22 | 2022-04-22 | N/A |  | 2022-06-21 | N/A | N/A | N/A | N/A
DPH | Bergstrom Wellfield and Treatment Plant | Bethel | 2022-03-22 | 2022-04-22 | N/A |  | 2022-06-21 | N/A | N/A | N/A | N/A
DPH | Wallens Hill Storage Tank | Winchester | 2022-03-22 | 2022-04-22 | N/A |  | 2022-07-19
DPH | Crystal Lake Storage Tank | Winchester | 2022-03-22 | 2022-04-22 | N/A |  | 2022-07-19
DOH | Haystack Woods | Norfolk | 2022-03-22 | 2022-04-21 | 2022-10-21
UCONN | Mansfield Apartments Redevelopment at the University of Connecticut | Mansfield | 2022-02-22 | 2022-03-24 | N/A |  | 2022-06-07 | 2022-10-04 | 2023-01-03 | 2023-01-17 |  | 1/3/2023 ROD corrects defects in ROD posted 12/20/2022
DOT | Route 85 Improvements - South of Route 82 | Montville and Salem | 2022-02-22 | 2022-03-30 | N/A |  | 2022-11-08
DOT | Reconfiguration of Route 17 On-Ramp to Route 9 Northbound | Middletown | 2022-01-18 | 2022-02-18 | N/A |  | 2022-08-16
DEEP | Suffield Wildlife Management Area Prescribed Burn | Suffield | 2021-12-21 | 2022-01-31 | N/A | N/A | 2022-02-22 | N/A | N/A | N/A | N/A
DAS | Kensington State Fish Hatchery Solar Project | Berlin | 2021-12-07 | 2022-01-07 | N/A | 2023-05-16 | 2023-06-20 |  |  |  |  | Updated project status on 5/16/23 replaces project status update on 9/20/22 ¦ Post-Scoping Notice expected 7/3/2023
DAS | State of Connecticut Department of Correction Solar Projects | Cheshire | 2021-12-07 | 2022-01-06 | N/A |  | 2022-09-20
DAS | State of Connecticut Department of Correction Solar Projects | Enfield and Somers | 2021-12-07 | 2022-01-06 | N/A |  | 2022-09-20
UCONN | Mirror Lake Improvements at the University of Connecticut | Mansfield | 2021-11-16 | 2021-12-16 | N/A | N/A | 2022-02-22 | 2022-04-05 | 2022-09-20 | 2022-10-04 |  | EIE reposted 8/2/2022 in association with notices published in newspapers
UCONN | South Campus Residence Hall at the University of Connecticut | Mansfield | 2021-11-16 | 2021-12-16 | N/A | 2022-05-17 | 2022-10-18
DoAg | Southbury Training School Farm Building Demolition | Southbury | 2021-11-02 | 2021-12-03 | N/A | N/A | 2021-12-21 | N/A | N/A | N/A | N/A
DOH | Wellington at Madison, Multifamily Housing | Madison | 2021-11-02 | 2021-12-02 | 2022-06-02
DOH | Enfield Manor – Elderly/Disabled Housing Development | Enfield | 2021-11-02 | 2021-12-02 | 2022-06-02
DEEP | Ox Brook Flood Control Master Plan | Bridgeport | 2021-10-05 | 2021-11-04 | N/A | N/A | 2021-12-07 | 2022-02-22 | 2022-06-21 | 2022-07-19
DOT | Replacement of Bridge No. 00162 - I-95 over Metro North Railroad | West Haven | 2021-09-21 | 2021-10-29 | N/A | 2022-04-19 | N/A | N/A | N/A | N/A | 2022-05-03 | Project scope expanded and re-scoped on 5/3/2022.
DOH | Eagleville Green, Mansfield - Multifamily Housing Development | Mansfield | 2021-09-21 | 2021-10-21 | 2022-10-19 | 2022-04-19
DOH | Deming Road Multifamily Housing | Berlin | 2021-07-20 | 2021-08-19 | N/A | N/A | 2022-04-19 | N/A | N/A | N/A | N/A
DOH | Cedar Point Multifamily Development | Newington | 2021-07-20 | 2021-08-19 | 2022-02-19
DOH | Avery Park Revitalization Initiative – Woodland Springs Phase II | Stafford Springs | 2021-07-06 | 2021-08-05 | N/A | N/A | 2022-04-19 | N/A | N/A | N/A | N/A
DOT | Hop River State Park Trail | Columbia, Coventry | 2021-06-08 | 2021-07-09 | N/A | N/A | 2022-04-05 | N/A | N/A | N/A | N/A
DOT | Replacement of Bridge No. 04152, West Cedar Street over Five Mile River | Norwalk | 2021-05-18 | 2021-06-18 | N/A | N/A | 2021-12-21 | N/A | N/A | N/A | N/A
DOT | Replacement of Stiles Bridge - Route 191 over the Scantic River | East Windsor | 2021-04-20 | 2021-05-21 | N/A | N/A | 2021-12-07 | N/A | N/A | N/A | N/A
DPH | Crestwood Drive Water Main Extension | Naugatuck | 2021-03-16 | 2021-04-16 | N/A | 2021-09-21 | 2021-10-19 | N/A | N/A | N/A | N/A
DPH | Countryside Drive Association Consolidation with Norwich Public Utilities | Norwich | 2021-03-16 | 2021-04-16 | N/A | N/A | 2021-06-08 | N/A | N/A | N/A | N/A
DOT | Replacement of Bridge No. 04446 - Hop River Road over Hop River, Coventry and Columbia | Coventry, Columbia | 2021-01-19 | 2021-02-19 | N/A | N/A | 2021-08-17 | N/A | N/A | N/A | N/A
DPH | New Britain Water Department Batterson Park Water Main Extension | New Britain | 2020-12-22 | 2021-01-22 | N/A | N/A | 2021-03-16 | N/A | N/A | N/A | N/A
OPM | Special Notice: Proposed Generic Environmental Classification Document, submitted at the request of the Office of Policy and Management. | NA | 2020-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Adopted March 2, 2021
DOT | Ramp Widening I-95 NB Exit 27A | Bridgeport | 2020-10-06 | 2020-11-10 | N/A | N/A | 2021-05-04 | N/A | N/A | N/A | N/A
DEEP | City of Bridgeport Facilities Planning for East Side and West Side Wastewater Treatment Plants, Bridgeport | Bridgeport | 2020-10-06 | 2020-11-05 | N/A | N/A | 2021-01-05 | 2021-06-08 | 2021-10-19 | 2021-12-07 | N/A
DOT | Interchange Improvements to I-91, I-691 and Route 15, Meriden and Middletown | Meriden, Middletown | 2020-09-22 | 2020-10-23 | 6/22/2023 (actual 6/20) | 2022-12-20 | [5 empty] | post scoping notice expected on or before 8/22/2023
DOT | Old Farms Road Realignment and Improvements | Avon | 2020-07-21 | 2020-08-07 | N/A | N/A | 2020-12-22 | N/A | N/A | N/A | N/A
DPH | Huckleberry Hill Water Main Extension | Brookfield | 2020-05-05 | 2020-06-05 | N/A | N/A | 2020-07-07 | N/A | N/A | N/A | N/A
UCONN | UConn Structures Demolition – Spring Manor Farm Project | Mansfield | 2020-03-03 | 2020-04-02 | N/A | 2020-10-06 | 2021-05-04 | N/A | N/A | N/A | N/A
DPH | Cedar Ridge Apartments Public Water Interconnection | Willington, Mansfield | 2020-01-21 | 2020-02-21 | N/A | N/A | 2020-04-07 | N/A | N/A | N/A | N/A
DEEP | Regional Wastewater Study, (Ansonia, Beacon Falls, Derby, Naugatuck, Seymour) | Ansonia, Beacon Falls, Derby, Naugatuck, Seymour | 2019-11-05 | 2019-12-05 | N/A | Did not publish | 2021-09-21 | 2021-10-05 | 2022-08-02 | 2022-09-20
DECD | Berlin TOD Boulevard Project | Berlin | 2019-10-08 | 2019-11-07 | N/A | N/A | 2019-12-03 | N/A | N/A | N/A | N/A
DEEP | Cove River Tide Gate Reconstruction Project | West Haven | 2019-09-03 |  | N/A | N/A | 2020-01-07 | N/A | N/A | N/A | N/A
DEEP | Coventry Low-Pressure Sewer Extension | Coventry | 2019-08-20 |  | N/A | 2020-12-22 | 2021-08-17 | N/A | N/A | N/A | N/A
DPH | Chestnut Ridge Storage Tank | Bethel | 2019-07-02 |  | N/A | N/A | 2020-01-07 | N/A | N/A | N/A | N/A
DPH | Emergency Interconnection between Norwich Public Utilities, Ledyard WPCA and Town of Preston | Ledyard, Preston | 2019-05-21 |  | N/A | N/A | 2020-10-20 | N/A | N/A | N/A | N/A
UCONN | University of Connecticut Ice Hockey Arena Development | Mansfield | 2019-05-21 |  | N/A | N/A | 2019-10-22 | 2020-03-17 | 2020-07-07 | 2020-10-08 | N/A | 2/19/19 - New Dates Notice 9/3/19 - Update for EIE Notice Published January 8, 2019
DOT | I-95 Interchange 74 Improvements at Route 161 and Replacement of Bridge No. 00250 | East Lyme | 2019-05-07 |  | N/A | N/A | 2019-10-08 | N/A | N/A | N/A | N/A
CTARNG/CTMD | Connecticut Readiness Center - Connecticut Army National Guard/Connecticut Military Department - joint CEPA/NEPA | Putnam | 2019-04-16 |  | N/A | N/A | N/A | 2021-07-06
DECD | Bridgeport Municipal Airport Improvements | Stratford | 2019-02-19 |  | N/A | N/A
DEEP | Pachaug State Forest Prescribed Burns | Griswold, Voluntown | 2018-12-18 |  | N/A | N/A | 2019-03-19 | N/A | N/A | N/A | N/A
DPH | Derby Water Storage Tank | Derby | 2018-12-18 |  | N/A | N/A | 2019-02-05 | N/A | N/A | N/A | N/A
DECD | West Haven Waterfront Development | West Haven | 2018-11-06 |  | N/A | N/A | 2021-09-07 | N/A | N/A | N/A | N/A
DECD/DOH | East Hartford Veterans Terrace VT2 | East Hartford | 2018-11-06 |  | N/A | N/A
DECD/DOH | Canaan Parish | New Canaan | 2018-11-06 |  | N/A | N/A
DECD | Windham Intermodal Transportation Center | Windham | 2018-10-16 |  | N/A | N/A | 2019-04-16 | N/A | N/A | N/A | N/A
DECD/DOH | The Windward Appartments | Bridgeport | 2018-10-16 |  | N/A | N/A
DECD/DOH | Willow Creek Apartments | Hartford | 2018-10-16 |  | N/A | N/A
DECD/DOH | Farnham Courts Phase 2b | New Haven | 2018-10-16 |  | N/A | N/A
DOT | New Parking Garage at the Stamford Transportation Center | Stamford | 2018-10-02 |  | N/A | N/A | 2019-09-03 | N/A | N/A | N/A | N/A
CTARNG/CTMD | Connecticut Training Center Installation Master Plan, Connecticut Army National Guard | East Lyme, Lyme, Old Lyme, East Haven | 2018-10-02 |  | N/A | N/A | N/A | 2019-06-18
DPH | Re-Scoping: Stony Brook North and South Transmission Main Rehabilitation | Montville, Bozrah | 2018-09-18 |  | N/A | N/A | 2019-04-02 | N/A | N/A | N/A | N/A
DPH | Manchester Water Department, Glastonbury Watermain Extension | Glastonbury and Manchester | 2018-09-18 |  | N/A | N/A | 2018-11-06 | N/A | N/A | N/A | N/A
OPM | Orange Property Acquisition | Orange | 2018-08-07 |  | N/A | N/A | 2018-12-18 | N/A | N/A | N/A | 2018-12-18
DPH | Sprague NPU Emergency Interconnection | Sprague | 2018-07-03 |  | N/A | N/A | 2019-02-05 | N/A | N/A | N/A | N/A
DPH | Town Center Water Supply, Phase Three | Marlborough | 2018-06-19 |  | N/A | N/A | 2018-08-07 | N/A | N/A | N/A | N/A
DESPP | Connecticut State Police Training Facility | Griswold | 2018-05-22 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-18
DPH | Emergency Interconnections between Ledyard WPCA Water System and SCWA Water Systems | Ledyard | 2018-05-08 |  | N/A | N/A | 2018-08-07 | N/A | N/A | N/A | N/A
DPH | East Lyme Well 1A Raw Water Main and Well 6 Treatment Improvement Project | East Lyme | 2018-05-08 |  | N/A | N/A | 2018-07-03 | N/A | N/A | N/A | N/A
DECD/DOH | Neck Road Housing | Old Lyme | 2018-05-08 |  | N/A | N/A | N/A |  |  |  | 2024-10-08
DOT | Removal of Traffic Signals on Route 9 and Associated Improvements | Middletown | 2018-03-06 |  | N/A | N/A | 2022-04-05 | Project cancelled. Will re-scope. | Project cancelled. Will re-scope. | Project cancelled. Will re-scope. | Project cancelled. Will re-scope. | Project cancelled. Will re-scope with additional alternatives.
DEEP | Greater New Haven Water pollution Control Authority Combined Sewer Overflow Long-term Control Plan | New Haven | 2018-02-20 |  | N/A | N/A | N/A | 2021-03-16 | 2025-12-02 | 2026-02-17
DOH | Resilient Bridgeport: National Disaster Resilience and Rebuild by Design Project | Bridgeport | 2018-02-20 |  | N/A | N/A | N/A | 2019-01-08 | 11/5/19 and 12/3/2019 | 2019-12-03 | N/A | Update for EIE notice - 9/3/19
DEEP | Roraback Pond Dam Removal | Harwinton | 2018-02-06 |  | N/A | N/A | 2021-01-19 | N/A | N/A | N/A | N/A
DEEP | Putnam Memorial Pond Dam Removal | Redding | 2018-02-06 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-21
OPM | Whiting Street Improvement Project | Winsted | 2018-01-16 |  | N/A | N/A | 2018-03-06 | N/A | N/A | N/A | N/A
DECD/DOH | Crescent Crossings - Phase 1C | Bridgeport | 2018-01-16 |  | N/A | N/A
DECD/DOH | Washington Village - Phase II | Norwalk | 2018-01-16 |  | N/A | N/A
DAS | New Parking Structure (10 Clinton Street) | Hartford | 2018-01-02 |  | N/A | N/A | 2018-03-20 | N/A | N/A | N/A | N/A
UConn | Main Campus Parking Replacements Project | Mansfield | 2017-11-21 |  | N/A | N/A | 2018-07-03 | N/A | N/A | N/A | N/A
UConn | UConn NW Science Quad Improvements | Mansfield | 2017-11-21 |  | N/A | N/A | N/A | 2018-12-18 | 2019-07-08 | 2019-08-15 | N/A
DEEP | Wastewater Facilities Plan | Fairfield | 2017-11-07 |  | N/A | N/A | 2019-02-05 | N/A | N/A | N/A | N/A
DECD | Greater Waterbury - Naugatuck Valley Regional Industrial Park Expansion Project | Waterbury and Naugatuck | 2017-11-07 |  | N/A | N/A | 2018-01-16 | N/A | N/A | N/A | N/A
DEEP | Bridgeport Combined Sewer Overflow Long Term Control Plan Update | Bridgeport | 2017-10-03 |  | N/A | N/A | 2017-12-05 | N/A | N/A | N/A | N/A
DOT | Route 7 and Route 15 Interchange Project | Norwalk | 2017-10-03 |  | N/A | N/A | 2020-06-16 | 2023-07-18 | 2024-08-20 | 2025-01-07
DOT | Replacement and Improvement of East Avenue Railroad Bridge | Norwalk | 2017-09-19 |  | N/A | N/A | 2018-06-19 | N/A | N/A | N/A | N/A
UConn | UConn Athletic District Improvements | Mansfield | 2017-09-19 |  | N/A | N/A | 2018-05-22 | N/A | N/A | N/A | N/A
DOT | Replacement of Bridge on Cedar Heights Road over Rippowam River | Stamford | 2017-07-11 |  | N/A | N/A | 2018-09-04 | N/A | N/A | N/A | N/A
DEEP | Tylerville Water Main Project | Haddam and Chester | 2017-06-06 |  | N/A | N/A | 2018-01-16 | N/A | N/A | N/A | N/A
DPH | Bunker Hill Water Main and Sewer Extension, Watertown | Watertown | 2017-06-06 |  | N/A | N/A | 2018-01-16 | N/A | N/A | N/A | N/A | This project was originally scoped in two parts. The Sewer Extension Notice of Scoping was published on February 7, 2017 and the Bunker Hill Water Main Extension Notice of Scoping was published on April 4, 2017. The following notice is being published because the projects are proposed to be implemented simultaneously; however, no changes are proposed to either part of the project.
DECD | Derby Downtown Redevelopment Project - REVISED | Derby | 2017-06-06 |  | N/A | N/A | 2017-10-17 | N/A | N/A | N/A | N/A
DECD & CT Port Authority | State Pier Complex Improvements | New London | 2017-05-16 |  | N/A | N/A | 2017-07-25 | N/A | N/A | N/A | N/A
DOH | Spruce Ridge | Pawcatuck | 2017-05-16 |  | N/A | N/A | 2017-07-25 | N/A | N/A | N/A | N/A
DPH | Briar Cliff Booster and Long Meadow Water Main Extension | Bethel | 2017-05-16 |  | N/A | N/A | 2017-07-11 | N/A | N/A | N/A | N/A
DPH | East Side Pressure Zone Improvements | Southington | 2017-05-02 |  | N/A | N/A | 2017-07-25 | N/A | N/A | N/A | N/A
DEEP | Decommission of Route 7 Wastewater Treatment Facility and Construction of New Pump Station and Force Main to South St. Wastewater Treatment Facility | Ridgefield | 2017-05-02 |  | N/A | N/A | N/A | 2017-08-22 | 2018-09-21 | 2018-12-07 | N/A
DEEP | United Pond Dam and City Pond Dam Removal | Griswold | 2017-04-04 |  | N/A | N/A | 2019-08-20 | N/A | N/A | N/A | N/A
DPH | Bunker Hill Water Main Extension | Watertown | 2017-04-04 |  | N/A | N/A | 2018-01-16 | N/A | N/A | N/A | N/A | This project was originally scoped in two parts. The Sewer Extension Notice of Scoping was published on February 7, 2017 and the Bunker Hill Water Main Extension Notice of Scoping was published on April 4, 2017. The following notice is being published because the projects are proposed to be implemented simultaneously; however, no changes are proposed to either part of the project.
DPH | Watertown Sewer Extension | Watertown | 2017-02-07 |  | N/A | N/A | 2018-01-16 | N/A | N/A | N/A | N/A | This project was originally scoped in two parts. The Sewer Extension Notice of Scoping was published on February 7, 2017 and the Bunker Hill Water Main Extension Notice of Scoping was published on April 4, 2017. The following notice is being published because the projects are proposed to be implemented simultaneously; however, no changes are proposed to either part of the project.
DECD | Hockanum Mill | Vernon | 2017-02-07 |  | N/A | N/A | 2017-03-21 | N/A | N/A | N/A | N/A
DECD | Middletown Boat House Redevelopment | Middletown | 2016-11-22 |  | N/A | N/A | 2017-03-21 | N/A | N/A | N/A | N/A
DOH | Westbrook Village | Hartford | 2016-11-08 |  | N/A | N/A | 2017-11-07 | N/A | N/A | N/A | N/A
DECD | Montgomery Mills Redevelopment Project | Windsor Locks | 2016-11-08 |  | N/A | N/A | 2017-05-16 | N/A | N/A | N/A | N/A
DPH | Rocky Ledge Water Main Extension | Clinton | 2016-11-08 |  | N/A | N/A | 2017-02-07 | N/A | N/A | N/A | N/A
DOH | Columbus Commons | New Britain | 2016-11-08 |  | N/A | N/A | 2016-12-20 | N/A | N/A | N/A | N/A
DOH | Meriden Commons Phase I/II | Meriden | 2016-10-18 |  | N/A | N/A | 2016-12-20 | N/A | N/A | N/A | N/A
DOT | Safety Improvements on Route 127 at Evers Street | Bridgeport | 2016-09-20 |  | N/A | N/A | 2019-09-03 | N/A | N/A | N/A | N/A
DPH | Mulberry Point Water Main Extension | Guilford | 2016-09-20 |  | N/A | N/A | 2017-12-18 | N/A | N/A | N/A | N/A
DECD | Dixwell Q House Community Center Project | New Haven | 2016-09-20 |  | N/A | N/A | 2016-11-22 | N/A | N/A | N/A | N/A
DOT | Rehabilitation of the Heroes Tunnel | Woodbridge, Hamden, New Haven | 2016-09-06 |  | N/A | 2023-02-07 | [5 empty] | Project status update published 2/7/2023 was a cancellation notice
DEEP | Franklin Sewer and Water Main Extension | Franklin | 2016-08-16 |  | N/A | N/A | N/A | 2017-07-11 | 11/9/2018 | 2018-11-20 | N/A
DOT | Orange Railroad Station | Orange | 2016-08-16 |  | N/A | N/A | N/A | 2017-05-16 | N/A | N/A | 2018-07-17 | 9/6/16 - Revised Scoping Notice
DEEP | Seaside State Park Master Plan - Revised | Waterford | 2016-08-02 |  | N/A | N/A | N/A | 2017-06-20 | 2018-02-16 | 2018-03-02 | N/A | 7/11/17 - ERRATA ADDED WITH NEW COMMENT DEADLINE
DOT | Barnum Train Station | Bridgeport | 2016-08-02 |  | N/A | N/A | N/A | 2017-01-03 | N/A | N/A | 2019-01-22 | 2/5/19 - Clarification Notice regarding cancellation
CTMD | Evaluation for Maintenance Building at East Haven Rifle Range | East Haven | 2016-07-19 |  | N/A | N/A | 2021-09-07 | N/A | N/A | N/A | N/A
DECD | Preston River Walk Remediation | Preston | 2016-07-19 |  | N/A | N/A | 2016-10-04 | N/A | N/A | N/A | N/A
CTMD | Additional Landings of Helicopters at East Haven Rifle Range | East Haven | 2016-07-19 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-08
DOT | Major Rehabilitation or Replacement of Heroes Tunnel (Bridge 00773) Route 15 Through West Rock Ridge | Woodbridge, Hamden, New Haven | 2016-07-05 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2016-07-19
DOT | Rehabilitation / Replacement of Saugatuck River Bridge # 01349 at Route 136 | Westport | 2016-05-17 |  | N/A | N/A | 2020-08-04 | 2026-02-17
DOT | Improvements to I-84 Interchange 17, Chase Parkway Extension, Routes 63 & 64 | Middlebury & Waterbury | 2016-05-17 |  | N/A | N/A | 2021-08-03 | N/A | N/A | N/A | N/A
DOT | Safety and Operational Improvements on I-84 | West Hartford | 2016-05-17 |  | N/A | N/A | 2019-01-08 | N/A | N/A | N/A | N/A
DPH | Marlborough Town Center Public Water System Phase II | Marlborough | 2016-05-17 |  | N/A | N/A | 2016-07-05 | N/A | N/A | N/A | N/A
DOT | Major Intersection Improvements Route 34 - SR 490 (Wasserman Way) and Toddy Hill Road and SR 490 at I-84 Interchange 11 ramps. | Newtown | 2016-04-19 |  | N/A | N/A | 2019-06-18 | N/A | N/A | N/A | N/A
DAS | State Office Building Redevelopment | Hartford | 2016-04-05 |  | N/A | N/A | N/A | 2017-04-18 | 2017-06-26 | 2017-07-05 | N/A
DPH | North Stonington Water Main Extension | North Stonington | 2016-03-08 |  | N/A | N/A | 2016-12-20 | N/A | N/A | N/A | N/A
UConn | Construction of Student Recreation Center | Mansfield | 2016-02-02 |  | N/A | N/A | 2016-05-03 | N/A | N/A | N/A | N/A
DEEP | Cockaponset State Forest Prescribed Burn | Chester and Haddam | 2016-02-02 |  | N/A | N/A | 2016-03-22 | N/A | N/A | N/A | N/A
DOT | Replacement of Bridge #03993 - West St. | Middletown | 2016-01-19 |  | N/A | N/A | 2016-04-19 | N/A | N/A | N/A | N/A
OPM | Parking Improvements for Pratt and Whitney Field | East Hartford | 2015-12-08 |  | N/A | N/A | 2016-03-08 | N/A | N/A | N/A | N/A
DOT | Intersection Improvements Route 74 and Route 195 near Tolland Green | Tolland | 2015-11-17 |  | N/A | N/A | 2017-08-08 | N/A | N/A | N/A | N/A
DOT | New Parking Garage at Union Station | New Haven | 2015-11-17 |  | N/A | N/A | N/A | 2016-05-03 | 2017-10-11 | 2017-11-17 | N/A | 6/21/16 - Extended Comment Deadline
DEEP | Waterbury Water Pollution Control Comprehensive Facility Evaluation | Waterbury | 2015-11-03 |  | N/A | N/A | 2017-12-05 | N/A | N/A | N/A | N/A
DOT | Various Bridge Rehabilitations at I-84 & Route 8 Northbound with Temporary Bypass | Waterbury | 2015-11-03 |  | N/A | N/A | 2016-04-19 | N/A | N/A | N/A | N/A
DOH | The Hamlet on East South St. | Suffield | 2015-10-20 |  | N/A | N/A | 2016-03-22 | N/A | N/A | N/A | N/A
CAA | Installation of Wildlife Hazard Deterrent Fence at Groton - New London Airport | Groton | 2015-09-22 |  | N/A | N/A | N/A | 2016-05-17 | Not an action under CEPA. | Not an action under CEPA. | N/A
CAA | Wildlife Hazard Deterrent Fence, Hartford-Brainard Airport | Hartford and Wethersfield | 2015-09-22 |  | N/A | N/A | N/A | 2016-03-22 | Not an action under CEPA. | Not an action under CEPA. | N/A
DPH | Water and Sewer Line Extension and Housing Project | Stafford | 2015-09-08 |  | N/A | N/A | 2015-12-08 | N/A | N/A | N/A | N/A
DPH | Tarrifville Fire District Water Storage Tank Replacement | Simsbury | 2015-09-08 |  | N/A | N/A | 2015-11-03 | N/A | N/A | N/A | N/A
DOT | Relocation of I-91 Northbound (NB) Interchange and Widening of I-91 NB and Rt. 15 NB to I-84 EB | Hartford | 2015-08-18 |  | N/A | N/A | 2016-08-16 | N/A | N/A | N/A | N/A
CAA | Off-Airport Tree Obstruction Removal at the Danielson Airport | Killingly | 2015-06-16 |  | N/A | N/A | N/A | 2017-01-17 | Not an action under CEPA. | Not an action under CEPA. | N/A
CAA | Off Airport Tree Obstruction Removal for Hartford - Brainard Airport | Hartford | 2015-06-16 |  | N/A | N/A | N/A | 2016-12-20 | Not an action under CEPA. | Not an action under CEPA. | N/A
CAA | Off Airport Tree Obstruction Removal for Groton - New London Airport | Groton | 2015-06-16 |  | N/A | N/A | N/A | 2016-11-08 | Not an action under CEPA. | Not an action under CEPA. | N/A
CAA | Off Airport Tree Obstruction Removal for Waterbury-Oxford Airport | Oxford, Middlebury | 2015-06-16 |  | N/A | N/A | N/A | 2016-10-18 | Not an action under CEPA. | Not an action under CEPA. | N/A
CAA | Off Airport Tree Obstruction Removal for Bradley Airport | Windsor Locks, East Granby, Suffield | 2015-06-16 |  | N/A | N/A | N/A | 2016-10-18 | Not an action under CEPA. | Not an action under CEPA. | N/A
CAA | Environmental Assessment for Off-Airport Tree Obstruction Removal, Windham Airport | Windham | 2015-06-16 |  | N/A | N/A | N/A | 2016-03-22 | Not an action under CEPA. | Not an action under CEPA. | N/A | 3/22/2016 - Additional scoping notice
DPH | Lathrop Road Extension Water Main | Plainfield | 2015-06-02 |  | N/A | N/A | 2015-07-21 | N/A | N/A | N/A | N/A
DAS | Asnuntuck Community College New Manufacturing Center | Enfield | 2015-05-19 |  | N/A | N/A | 2015-11-03 | N/A | N/A | N/A | N/A
DPH | Covey Road Water Main Extension | Burlington | 2015-05-05 |  | N/A | N/A | 2015-07-21 | N/A | N/A | N/A | N/A
DAS | State Police Firearms Training Facility Relocation | East Windsor or Willington | 2015-05-05 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-18
DEEP | Springborn Dam Removal | Enfield | 2015-04-21 |  | N/A | N/A | 2016-03-08 | N/A | N/A | N/A | N/A
DOT | Seaview Avenue Corridor Improvements | Bridgeport | 2015-04-07 |  | N/A | N/A | 2018-08-21 | N/A | N/A | N/A | N/A
DECD | Downtown Crossing Phase II | New Haven | 2015-03-17 |  | N/A | N/A | 2016-05-17 | N/A | N/A | N/A | N/A
DOT | Replacement of Bridge No. 02866 - Route 275 over Willimantic River | Coventry and Mansfield | 2015-03-17 |  | N/A | N/A | 2015-05-05 | N/A | N/A | N/A | N/A
DEEP | Four Corners Sewer Extension | Mansfield | 2015-03-03 |  | N/A | N/A | N/A | 2016-02-02 | 2017-05-03 | 2017-05-24 | N/A
OPM | Milford Property Acquisition | Milford | 2015-02-17 |  | N/A | N/A | 2015-05-05 | N/A | N/A | N/A | N/A
UConn | University of Connecticut South Campus Development | Mansfield | 2015-02-17 |  | N/A | N/A | N/A | 2016-01-19 | 2016-05-06 | 2016-08-03 | N/A
DEEP | Hawleyville Low Pressure Sewer Extension | Newtown | 2015-02-03 |  | N/A | N/A | 2015-04-21 | N/A | N/A | N/A | N/A
DOT | Norwalk River Railroad Bridge (Walk Bridge) Replacement | Norwalk | 2015-02-03 |  | N/A | N/A | N/A | 2016-11-22 | 2017-06-01 | 2017-07-06 | N/A
DPH | East Side Water Storage Tank and Pump Station | Southington | 2015-01-20 |  | N/A | N/A | 2015-03-17 | N/A | N/A | N/A | N/A
DOT | I-84 Hartford Project | Hartford | 2014-12-16 |  | N/A | N/A | 2020-05-05 | N/A | N/A | N/A | 2020-05-05
DCS & Board of Regents | Middlesex Community College Facilities Master Plan 2014-2023 | Middletown | 2014-11-18 |  | N/A | N/A
DPH | Stony Brook Water Treatment Plant Improvements | Montville | 2014-10-07 |  | N/A | N/A | 2014-11-18 | N/A | N/A | N/A | N/A
DEEP | Old Lyme Coastal Wastewater Management Project | Old Lyme | 2014-07-22 |  | N/A | N/A | N/A | 2019-06-19
UConn | University of Connecticut West Hartford Campus | West Hartford | 2014-06-17 |  | N/A | N/A | 2018-06-05 | N/A | N/A | N/A | N/A
DPH | Groton Water Treatment Plant Upgrade | Groton | 2014-06-03
DVA | State Veterans' Cemetery Expansion Improvements | Middletown | 2014-04-22 |  | N/A | N/A | 2014-11-18 | N/A | N/A | N/A | N/A
DOT | Greater Waterbury Bus Storage and Maintenance Facility Project | Watertown | 2014-03-18 |  | N/A | N/A | 2014-05-20 | N/A | N/A | N/A | N/A
DOT | Valley Service Road Extension | North Haven | 2014-03-04 |  | N/A | N/A | 2014-11-18 | N/A | N/A | N/A | N/A
DECD | East Haven Industrial / Business Park | East Haven | 2014-02-18 |  | N/A | N/A | 2014-04-08 | N/A | N/A | N/A | N/A
DOT | New Haven Rail Yard Maintenance of Way Building and Parking Lot | New Haven | 2014-01-07 |  | N/A | N/A | 2014-03-18 | N/A | N/A | N/A | N/A
DOT | Meriden Transit Oriented Development | Meriden | 2013-12-17 |  | N/A | N/A | 2014-04-08 | N/A | N/A | N/A | N/A
DAS | Southbury Affordable-Elderly Housing Development | Southbury | 2013-11-19 |  | N/A | N/A | N/A | 2016-07-05 | 2019-01-08 | 2019-03-06 | N/A
DOT | Reconstruction of Atlantic Street and MNRR Bridge Replacement | Stamford | 2013-11-05 |  | N/A | N/A | 2014-06-17 | N/A | N/A | N/A | N/A
DECD | Francis J. Clarke Industrial Park Expansion | Bethel | 2013-10-08 |  | N/A | N/A | 2013-11-19 | N/A | N/A | N/A | N/A | CEPA review originally conducted in 1983. Project was resurrected and a scoping notice published on 08/06/2013. Project scope reduced and notice republished on 10/8/2013.
DECD | Governor's Station Multi-modal Transportation Oriented Development | Windsor Locks | 2013-09-17 |  | N/A | N/A
DECD | Former Connecticut Transit Bus Facility | New Haven | 2013-08-20 |  | N/A | N/A
DEEP | Housatonic River Restoration | Milford, New Milford, Seymour, Stratford, Watertown | 2013-07-16 |  | N/A | N/A | 2013-08-20 | N/A | N/A | N/A | N/A
DECD | National Coast Guard Museum Pedestrian Overpass Project | New London | 2013-06-18 |  | N/A | N/A | 2013-08-06 | 2014-07-08 | 2014-11-01 | 2015-01-07 | N/A
DECD | Bridgewater Associates | Stamford | 2013-05-21 |  | N/A | N/A | 2013-08-06 | N/A | N/A | N/A | N/A
DPH | Library Lane and George Washington Turnpike Water Main Project | Burlington | 2013-05-07 |  | N/A | N/A | 2013-06-04 | N/A | N/A | N/A | N/A
DESPP/DCS | Connecticut State Police Firearms Training Facility Relocation | Glastonbury | 2013-05-07 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-21
UConn | UConn Main Accumulation Area | Mansfield | 2013-04-16 |  | N/A | N/A | N/A | 2013-11-19 | 2014-02-06 | 2014-04-11 | N/A
DOT | Runway Safety Project, Sikorsky Airport | Stratford | 2013-03-19 |  | N/A | N/A | 2013-05-07 | N/A | N/A | N/A | N/A
DPH | Norwich Public Utilities Pumps Drives and Tanks | Lebanon | 2013-02-05 |  | N/A | N/A | 2013-05-07 | N/A | N/A | N/A | N/A
DPH | Route 69, New Haven Rd., Water Line | Prospect, Beacon Falls | 2013-02-05 |  | N/A | N/A | 2013-04-02 | N/A | N/A | N/A | N/A
DOT | Atlantic St/Henry St Intersection Improvement | Stamford | 2013-01-22 |  | N/A | N/A | 2014-05-06 | N/A | N/A | N/A | N/A
DPH | Spring Hill Reliability Improvement Project | Norwalk and New Canaan | 2013-01-08 |  | N/A | N/A | 2013-05-07 | N/A | N/A | N/A | N/A
DPH | New London Rd. (Route 1) Water Main Extension | Groton | 2012-12-04 |  | Not available | Not available | Not available
DOT | Windham Regional Transit District Bus Garage and Administration Building | Mansfield | 2012-11-06 |  | N/A | N/A | 2013-04-16 | N/A | N/A | N/A | N/A
DPH | Mohegan Park Water Tank | Norwich | 2012-08-07 |  | N/A | N/A | 2015-01-20 | N/A | N/A | N/A | N/A
DPH | Southern Stoney Brook Transmission Main Renewal | Montville | 2012-08-07 |  | N/A | N/A | 2013-01-08 | N/A | N/A | N/A | N/A
DPH | Royal Oaks Project | Norwich | 2012-08-07 |  | N/A | N/A | 2012-12-04 | N/A | N/A | N/A | N/A
DPH | Mohegan Park Water Tank - Design Phase | Norwich | 2012-08-07 |  | Not available | Not available | Not available
DOT | Rehabilitation of the Pucker St. Bridge over the Hop River | Coventry and Columbia | 2012-06-19 |  | N/A | N/A | 2015-04-21 | N/A | N/A | N/A | N/A
DOT | Stamford Transportation Center Parking and TOD | Stamford | 2012-05-08 |  | N/A | N/A | N/A | 2012-08-21 | 2013-01-18 | 2013-01-18 | N/A
DOT | Reconstruction of Old Farms Road | Avon | 2011-11-22 |  | N/A | N/A | 2016-07-19 | N/A | N/A | N/A | N/A
DOT | Old Saybrook Railroad Parking Lot Expansion | Old Saybrook | 2011-11-22 |  | N/A | N/A | 2013-08-20 | N/A | N/A | N/A | N/A
DOT | New Haven - Hartford - Springfield Corridor | New Haven - Hartford - Springfield Rail Improvements/High Speed Intercity Passenger Rail | 2011-09-20 |  | NA | NA | NA | 2012-05-08 | 2012-11-01 | 2013-01-17
DECD | Department of Economic and Community Development (DECD) proposed Environmental Classification Document | Statewide | 2011-06-07 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DPH | Deep River Water Treatment Plant and Transmission Main Replacement Meter and Microturbine | Lebanon and Bozrah | 2011-06-07 |  | N/A | N/A | 2015-01-20 | N/A | N/A | N/A | N/A
UConn | University of Connecticut Action for Additional Water Supply Sources | Mansfield, Tolland, Coventry | 2011-06-07 |  | N/A | N/A | N/A | 2012-11-06 | 2013-07-30 | 2013-09-16
DPW & Connecticut State University System & Eastern Connecticut State University | 2008 Campus Master Plan for Eastern Connecticut State University | Windham and Mansfield | 2011-03-08 |  | not available | not available | not available | not available | not available | not available | not available
Department of Information Technology (DOIT) | Broadband Technologies Opportunities Program (BTOP) Statewide Fiber Optic Network Project | Statewide | 2011-01-18 |  | N/A | N/A | 2011-03-08 | N/A | N/A | N/A | N/A
DEEP | Norwich Combined Sewer Overflow Control Plan | Norwich |  |  | N/A | N/A | N/A | 2015-10-06 | 2016-04-22 | 2016-05-12 | N/A
SPECIAL NOTE | ** Excludes Special Notices and NEPA-only publications and Land Transfers**
SPECIAL NOTE | **Each column contains the date of the most recent publication to the Environmental Monitor. These may be updates or modifications to previous publications.**
Last updated 11/24/2021
Formulas:
N/A = IF([Post-Scoping Notice Published]>[Deadline for Public Scoping Comments],"N/A",IF([Project Status Update Published]="",+EDATE([Deadline for Public Scoping Comments], 6),+EDATE([Project Status Update Published], 6)))
N/A = IF([Post-Scoping Notice Published]>[Scoping Notice Published],"N/A",IF([Project Status Update Published]="",+EDATE([Scoping Notice Published], 6),+EDATE([Project Status Update Published], 6)))