## Cover Page
|  | IMPORTANT NOTES: | 1. Formal approval by your local or regional board of education, or equivalent governing body for schools must be obtained prior to submitting your Increasing Educator Diversity Plan. Be prepared to provide the day, month and year that the plan was approved by the board or equivalent governing body as part of the upload of your submission. 2. In the absence of an original motion or a preexisting board or board equivalent policy expressly conferring authority on the superintendent or equivalent schools administrator to make any necessary Plan revisions, the school board or equivalent governing body will be expected to formally approve any necessary revisions to its Plan prior to resubmitting the revised Plan by May 15, 2024
COVER PAGE
District: | Ellington
Vision: | Ellington schools will employe a teacher workforce that represents the diversity of background and lived experience in the broader community.
Theory of Action | If the district partners with the Teacher Residency Program (TRP), area ed prep programs, and stakeholders of color, then we will attract more teachers of color to our district.
Team Lead: | Carolyn Yakaitis, Coordinator of HR
Team Members: | Oliver Barton, Carolyn Yakaitis, Tracey Deptula
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does this aspiration (vision) fit into the overall state vision for increasing educator diversity and the work to achieve educational equity?
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is our theory of action clearly articulated and does it establish a direct connection with the goals we identified?
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is the team led by a strong, committed leader who feels responsible for ensuring that goals are achieved?
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does the team represent and/or have strong relationships with all the relevant educators in the pipeline, including teachers and school-based leaders? Does the team have access to the people and information that they need to involve for problem-solving and keeping the work on track? Has the team established relevant partnerships needed to ensure the success of the goals? Do team members engage local stakeholders (influential individuals and groups) to advance the work? Are team members motivated and inspired by the goals and theory of action so that they stay determined to make changes in spite of distractions and challenges?
Increasing Educator Diversity
Plan Template

## Recruitment
RECRUITMENT
Goal | Who Manages the Goal? | Strategies/Key Activities (How are we going to do it?) |  |  | Indicators of Progress | Resources Required | Risks and Mitigation | Communication/ Engagement Efforts
(What are we trying to do?) | (name, position) | What? | Who Owns This? | By When? | (How will we know if we are on track for success?) | (What people, time, money, and technology will be needed?) | (What could go wrong? How will we make that less likely to happen?) | (Who needs to be consulted/ engaged? What needs to be communicated? To whom?)
Increase the number of high quality educator applicants of color hire one TRP resident every year. Increase the number of high quality educator applicants of color hire one TRP resident every year EPS demographics are currently 28% students of color and 6% educators of color (including 13% administrators of color). Increasing by one teacher per year would add 0.4 % per year, or 2% over five years, which is our minimum target. We plan to have 17 educators of color by 9/1/25, 22 by 9/1/30. Although we hope to substantially surpass our goal, if plan goals are achieved, we will have at least three teachers of color per school. | Carolyn Yakaitis, Coordinator of Human Resources | Advertise to all certified teachers in CT with specific certifications. Annually attend UConn Education Career Fair in March, and RESC Increasing Educator Diversity Fair in April. Secure TRP applicant by 11/25/2024 for priority candidate. District intentionally hires Ellington High School graduates for non-certified education support positions. The district encourages promising non-certified staff, especially staff of color, to consider pursuing educator certification through traditional avenues and the residency program. In 2023-24, for example, one paraeducator successfully started the TRP process. | Carolyn Yakaitis (targeted recruiting for vacancies) Oliver Barton (TRP) | Secure TRP applicant by 11/25/2024 for priority candidate if possible and if not by March 31, 2025, annually by November and March. | Although we hope to substantially surpass our goal, if plan goals are achieved, we will have at least three teachers of color per school. | Participation by HR and at least one administrator. If recruitment fairs require registration fees, operating budget and grant funds will be used. Grants are provided by CSDE consistently. TRP is budgeted through our Choice program funds which are sustainable. | Possible lack of quality residents in TRP—recruit candidates from area communities for TRP. Continue to recruit for TRP among existing paraeducators and other non-certified staff of color. co-constructing event plan with teachers or administrators of color | Communicate goals and TRP opportunity to Paras and tutors Communicate to educators and possible educators of color in nearby communities. Weekly district promotional videos publicly posted will include substantial representation of students and educators of color.
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are our goals SMART and are they written in a way that makes clear what success will look like — how things will be different? Have we defined goals that are based on our district’s most current data and any projections we have about the educator workforce?
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For each goal, have we identified a single person who is responsible for monitoring progress and ensuring successful implementation?
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have we identified a coordinated and coherent set of strategies for each goal that we have set? Are our strategies and key activities research-based and/or informed by best practices?
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For each strategy, is it clear who needs to do what, what capacity or motivation they will need to make changes, and who will engage them and how?
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a specified end date for each activity and for key milestones that are part of the activity?
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have we specified how we will know that each strategy is working? How will we know if each goal is on track for success? Do we know how we will collect and monitor this information? Are we clear that we will be able to show progress toward achieving our long-term goals? Have interim benchmarks been identified?
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have we identified the personnel, financial, technological, and other resources that are required for the plan?
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have we identified the major risks that might cause the work to go off course? Do we know how we will manage them?
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are there resources for a deliberate and differentiated communications strategy aimed at building a critical mass of support for each goal and the plan as a whole? Does the team proactively onboard new leaders after transitions? Are the people with the required leadership skills — particularly system leaders and accountable leaders — involved in and/or informed of this work? Are team members accessible and available to one another in between formal meetings? Does communication flow readily and smoothly?
Increasing Educator Diversity
Plan Template

## Hiring & Selection
HIRING & SELECTION
Goal | Who Manages the Goal? | Strategies/Key Activities (How are we going to do it?) |  |  | Indicators of Progress | Resources Required | Risks and Mitigation | Communication/ Engagement Efforts
(What are we trying to do?) | (name, position) | What? | Who Owns This? | By When? | (How will we know if we are on track for success?) | (What people, time, money, and technology will be needed?) | (What could go wrong? How will we make that less likely to happen?) | (Who needs to be consulted/ engaged? What needs to be communicated? To whom?)
Increase the number of quality interviewees, finalists, and selected teachers of color | Oliver Barton, Assistant Superintendent | Engage and orient 16 administrators at Administrative Council meeting on 3/20/2025, annually thereafter in March. | Assistant Superintendent will own training and engaging administrators for hiring, selection, and retention. | Beginning in March 2025 and annually thereafter. | Increased number of interviewees, finalists, and selected teachers of color | Principal and committee time | Implicit bias may impact perspectives of panelists—book study/training on implicit bias by admins. Add CREC PD on bias and representation for teachers and administrators. | Recruitment and preparation of hiring committee members. The superintendent will communicate to all admin the priorities and strategies related to recruiting, hiring, and retaining educators of color.
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are our goals SMART and are they written in a way that makes clear what success will look like — how things will be different? Have we defined goals that are based on our district’s most current data and any projections we have about the educator workforce?
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For each goal, have we identified a single person who is responsible for monitoring progress and ensuring successful implementation?
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have we identified a coordinated and coherent set of strategies for each goal that we have set? Are our strategies and key activities research-based and/or informed by best practices?
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For each strategy, is it clear who needs to do what, what capacity or motivation they will need to make changes, and who will engage them and how?
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a specified end date for each activity and for key milestones that are part of the activity?
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have we specified how we will know that each strategy is working? How will we know if each goal is on track for success? Do we know how we will collect and monitor this information? Are we clear that we will be able to show progress toward achieving our long-term goals? Have interim benchmarks been identified?
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have we identified the personnel, financial, technological, and other resources that are required for the plan?
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have we identified the major risks that might cause the work to go off course? Do we know how we will manage them?
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are there resources for a deliberate and differentiated communications strategy aimed at building a critical mass of support for each goal and the plan as a whole? Does the team proactively onboard new leaders after transitions? Are the people with the required leadership skills — particularly system leaders and accountable leaders — involved in and/or informed of this work? Are team members accessible and available to one another in between formal meetings? Does communication flow readily and smoothly?
Increasing Educator Diversity
Plan Template

## Retention
RETENTION
Goal | Who Manages the Goal? | Strategies/Key Activities (How are we going to do it?) |  |  | Indicators of Progress | Resources Required | Risks and Mitigation | Communication/ Engagement Efforts
(What are we trying to do?) | (name, position) | What? | Who Owns This? | By When? | (How will we know if we are on track for success?) | (What people, time, money, and technology will be needed?) | (What could go wrong? How will we make that less likely to happen?) | (Who needs to be consulted/ engaged? What needs to be communicated? To whom?)
Retain TRP teachers and teachers of color at rate greater than or equal to overall retention. 2023/24 overall retention rate was 16/267 (94%). Retention of teachers of color was also 94%. Target for teacher of color retention 2045-25 school year to 2025-26 school year is 94%. | Oliver Barton, Assistant Superintendent | Quarterly 1:1 meetings with principals/superv isors on teacher engagement and performance Annual celebration/networking (affinity) meeting w TRP grads, mentors, and teachers of color by 5/31/25, annually thereafter in May. | Assistant superintendent and principals. Tracey Deptula, Carolyn Yakaitis | May of each academic year. | Meetings completed, notes on engagement and teacher connectedness to and support across the community. Notes from convening. Evaluate attendance and feedback from affinity meeting 5/31/25, and future events annually to seek ways to improve. | Administrator time. Food and favors for meeting. | Low expectations on connectedness and support—admin reflection on mindset and data. Low interest-ensure engaging event, collect feedback, assess. Add 1:1 coaching of administrators by assistant superintendent. Sharing of best practices in connecting with staff at administrative council with support of two existing administrators of color. | Administrators, teachers
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are our goals SMART and are they written in a way that makes clear what success will look like — how things will be different? Have we defined goals that are based on our district’s most current data and any projections we have about the educator workforce?
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For each goal, have we identified a single person who is responsible for monitoring progress and ensuring successful implementation?
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have we identified a coordinated and coherent set of strategies for each goal that we have set? Are our strategies and key activities research-based and/or informed by best practices?
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For each strategy, is it clear who needs to do what, what capacity or motivation they will need to make changes, and who will engage them and how?
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a specified end date for each activity and for key milestones that are part of the activity?
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have we specified how we will know that each strategy is working? How will we know if each goal is on track for success? Do we know how we will collect and monitor this information? Are we clear that we will be able to show progress toward achieving our long-term goals? Have interim benchmarks been identified?
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have we identified the personnel, financial, technological, and other resources that are required for the plan?
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have we identified the major risks that might cause the work to go off course? Do we know how we will manage them?
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are there resources for a deliberate and differentiated communications strategy aimed at building a critical mass of support for each goal and the plan as a whole? Does the team proactively onboard new leaders after transitions? Are the people with the required leadership skills — particularly system leaders and accountable leaders — involved in and/or informed of this work? Are team members accessible and available to one another in between formal meetings? Does communication flow readily and smoothly?
Increasing Educator Diversity
Plan Template