## Cover Page
Increasing Educator Diversity Plan
District:
Stonington Public Schools
Team Lead:
Bethany Wagner, Human Resources Manager
Team Members:
Lisa Babcock, Special Services Supervisor Jennifer Bausch, 6-12 Curriculum Coordinator
Kristen Morehouse, K-5 Curriculum Coordinator Whitney Ross, West Vine Street School Teacher
AnneFay Sullivan, Assistant Principal West Vine Street School
Vision:
To create a welcoming and connected environment that promotes diversity, equity, and inclusion.
Theory of Action:
If Stonington Public Schools increases educator diversity by establishing
equitable hiring practices and increasing cultural awareness
for recruiting, hiring, and selection,
Then, Stonington Public Schools will create a more diverse workforce
And, Stonington students will benefit from cultural connection and awareness.

## Recruitment
Recruitment
Goal | Who Manages the Goal? | Strategies/Key Activities | Strategies/Key Activities | Strategies/Key Activities | Indicators of Progress | Resources Required | Risks and Mitigation | Communication & Engagement Efforts
|  | What? | Who? | When?
Expand the pool of qualified applicants including diverse applicants who apply for open positions within SPS | Human Resources Manager | Develop contacts with local training and educational institutions and other community organizations, including those that traditionally have highly diverse enrollments or membership, to publicize job openings and solicit referrals of qualified diverse candidates | Design leadership training focused on promoting diversity, cultural competence and awareness, sensitivity, and recognizing bias within the application process | Adjust hiring documents before June 2024 to show district commitment to diversity and a welcoming and inclusive environment | Increased number of diverse applicants, as assessed after the hiring and selection process has been finalized | Time to train leaders | Town demo- graphics could hinder the district’s appeal to diverse candidates | Utilize career center coordinator and school counseling office
|  | Include on the district website and in position postings a diversity statement along with a non- discrimination statement to inform applicants that the district values diversity | Provide training to school leaders | By August 2024, create a marketing video that highlights diversity and inclusion within all SPS schools | Increased number of diverse student teachers in the district as assessed after the hiring and selection process has been finalized | Time to build and improve content | Garner diversity plan buy-in from town decision- makers | Gain buy-in from district and town leaders
[6 empty] | Methods to make job applications and descriptions more reflective of a community that values diversity | Support town plans to address its affordable housing crisis

## Hiring and Selection
Goal | Who Manages | Strategies/ | Strategies/ | Strategies/ | Indicators of Progress | Resources Required | Risks and Mitigation | Communication & Engagement Efforts
| the Goal? | Key Activities | Key Activities | Key Activities
|  | What? | Who? | When?
Establish equitable hiring practices that reduce or eliminate the effects of unconscious and implicit bias | Driven by District Leaders | Select diverse interview committees (parents/staff) that include individuals with a wide range of experiences and perspectives | Ensure hiring staff has tools needed to track applicant flow, consistent with legal requirements, after the hiring and selection process concludes | Train between June 2024 to August 2024 | Increased number of diverse candidates selected to interview, as assessed after the hiring and selection process concludes | Interview checklist/ scorecards | Volunteer- based committees limit willing participants | Identify the many staff members who may publicize job openings to potential candidates
| Monitored by HR Manager | Provide implicit bias and anti-bias training to all members of the hiring committee | Offer more than one round of interviews | Revisit changes and review data before the 2025 hiring season | Increased number of diverse candidates offered positions as assessed after the hiring and selection process concludes | Standard interview questions on cultural awareness | Heavy summer hiring needs limit willing participants | Ensure that these staff members understand the increased staff diversity plan, its goals, and its strategies
|  | Ask interview questions that reveal commitment to Board goals regarding cultural competency and creating a welcoming, safe, and inclusive school environment |  |  |  |  | Budget cuts decrease future hiring and chances to diversify staff
|  | Host job fairs |  |  |  |  | Offer pay or incentives to serve on committees
|  | Post openings on various search engines |  |  |  |  | Conduct as few July and August interviews as possible

## Retention
Retention
Goal | Who Manages the Goal? | Strategies/Key Activities | Strategies/Key Activities | Strategies/Key Activities | Indicators of Progress | Resources Required | Risks and Mitigation | Communication & Engagement Efforts
|  | What? | Who? | When?
Maintain an environment where everyone, including diverse employees, feels safe, welcome, and valued | Human Resources | Prioritize cultural awareness, competence, and responsiveness throughout the district | District Office Leaders | On-going | Climate data reflects that all stakeholders (including staff, students, and families) feel connected to the school community | Maintain staff funding levels | Budget cuts could prevent retention of diverse staff (most recent hires are the first to be cut) | Discuss DEI goals with Board of Education and Board of Finance liaison
| Leadership Team | Provide opportunities for staff to interact with all members of our educational community and discuss areas of interest or concern | TEAM District Facilitator | Annual data analysis | Curriculum writing and revisions include a more in-depth lens with input from a diverse pool of staff with varied perspectives, expertise, and interests | Provide time for leaders to train employees and committees | Garner diversity plan buy-in from both town and district decision- makers | Collaboration with TEAM district facilitator and building leaders to recruit mentors from the entire school community
| DEI Committee | Provide TEAM mentors with resources to provide adequate support and encouragement to mentees | Building Leaders |  | Climate data that shows job satisfaction of all staff, including diverse staff | Compensate mentors
Board of Finance
Board of Education
Classroom
Teachers