## Cover Page
|  |  | IMPORTANT NOTES: | 1. Formal approval by your local or regional board of education, or equivalent governing body for schools must be obtained prior to submitting your Increasing Educator Diversity Plan. Be prepared to provide the day, month and year that the plan was approved by the board or equivalent governing body as part of the upload of your submission. 2. In the absence of an original motion or a preexisting board or board equivalent policy expressly conferring authority on the superintendent or equivalent schools administrator to make any necessary Plan revisions, the school board or equivalent governing body will be expected to formally approve any necessary revisions to its Plan prior to resubmitting the revised Plan by May 15, 2024
COVER PAGE
District: | Vernon Public Schools
Vision: | The Vision of the Vernon Public Schools is that every graduate is a Critical Thinker, Collaborator, Communicator, Resilient Individual, and Responsible Citizen
Theory of Action | If we prioritize recruiting, hiring, supporting, and retaining a diverse educator workforce who reflect and value the racial, ethnic, cultural, and linguistic diversity of Vernon Public Schools then we will diversify our workforce, decrease opportunity gaps, and improve outcomes for all students.
Team Lead: | Robert Testa, Assistant Superintendent
Team Members: | Melissa Trantolo-Parent, Robert Nagashima-Director of Pupil Services, Alba Osorio-Teacher, Gui Estes-Social Worker, Rob DeJesus-Teacher, Alicia McEvila-Teacher, Kimberly Grant-Human Resources Specialist, Jaime Markham-Human Resources Specialist, Jennifer Bergin-Interventionist
RECRUITMENT
Goal | Who Manages the Goal? | Strategies/Key Activities (How are we going to do it?) |  |  | Indicators of Progress | Resources Required | Risks and Mitigation | Communication/ Engagement Efforts
(What are we trying to do?) | (name, position) | What? | Who Owns This? | By When? | (How will we know if we are on track for success?) | (What people, time, money, and technology will be needed?) | (What could go wrong? How will we make that less likely to happen?) | (Who needs to be consulted/ engaged? What needs to be communicated? To whom?)
Recruit a faculty and staff more representative of the experiences and backgrounds of students enrolled in Vernon Public Schools | Robert Testa, Assistant Superintendent | Partner with the University of Connecticut to establish a Teacher Residency Program for future educators | Robert Testa, Assistant Superintendent | by August 2024 | Host (3-6) Resident Teachers in Vernon Public Schools each school year, Resident teachers include candidates that are racially and ethnically diverse. Acess to resident teacher candidates for potential positions within Vernon Public Schools | Year long paid Teacher Residency Program: $130/day per resident teacher, identify staff that will serve as mentor/host teachers | Lack of Teacher Residency candidates, no students enroll in the Residency Program | Communication with UConn regarding potential Teacher Residency candidates, Communication with VPS staff regarding potential resident placements
RECRUITMENT (continued)
Partner with an educational preparation program to build a "grow your own" teacher program that attracts and prepares RHS students for a career in the field of education. | Robert Testa, Assistant Superintendent | Offer UCONN ECE course If You Love It Teach It at Rockville High School for seniors who are interested in becoming future educators | Director of Teaching & Learning, Dominique Fox Course instructor, Kristen Piscottano | by August 2024 | Course enrollment of at least 15 students per section. Course enrollment reflects the diverse experiences and backgrounds of students enrolled in Vernon Public Schools. | Year long course $150 per student, approved course instructor, text books and instuctional materials | Course instructor needs to apply to UConn-syllabus may not be approved, curriculum may not be completed | Communication needs to go out to all RHS teachers so they can recruit students to take the course who they feel have potential to be a future educator
Increase our presence at job fairs in order to recruit a diverse pool of candidates UCONN,CCSU,ECSU, USJ and make connections with Historically Black Colleges and Universities (HBCU) | Human Resources Specialists, Jaime Markham and Kimberly Grant | Reach out to colleges and universities to connect with teacher candidates, Attend job fairs and meet with potential teachers prior to graduation | Human Resources Specialists, Jaime Markham and Kimberly Grant, Increasting Educator Diversity Committeee members | by August 2025 | Target: Increase the diversity of educators from 6.6% to 8.6% (track recruitment and hiring data to measure growth) Make Contacts with at least 2 HBCUs | Human Resources Specialists, Jaime Markham and Kimberly Grant, Increasing Educator Diversity committee members. Funds for recruitment materials. | Poorly attended job fairs, failure to connect with Historically Black Colleges and Universities, Inability to attract candidates of color to apply to Vernon Public Schools | Identify and connect with potential candidates through reach out and connections with colleges and universities, Individualized follow up w/ candidates after job fairs, Offer opportunity to visit Vernon Public Schools or connect with staff members
Market Vernon Public Schools through social media and other means of marketing and advertisment. | Human Resources Specialists, Jaime Markham and Kimberly Grant | Update district website to reflect our committment to increasing eductator diversity, Include testimonials of current teachers about why they chose Vernon, Expand recruiting through the following social media platforms- Facebook, LinkedIn, Indeed, CT Reap, etc., Publish vacancy notices early in the process(March) and hire early in the process | Human Resources Specialists, Jaime Markham and Kimberly Grant, Hiring Committees | by August 2025 | Target: Increase the diversity of educators from 6.6% to 8.6 % (track recruitment and hiring data to measure growth) | Human Resources Specialists, Jaime Markham and Kimberly Grant, Resources and time to support website re-design | Failure to attract a diverse applicant pool | Potential candidates view Vernon Public Schools as a potential welcoming employer who values equity and diversity
HIRING & SELECTION
Goal | Who Manages the Goal? | Strategies/Key Activities (How are we going to do it?) |  |  | Indicators of Progress | Resources Required | Risks and Mitigation | Communication/ Engagement Efforts
(What are we trying to do?) | (name, position) | What? | Who Owns This? | By When? | (How will we know if we are on track for success?) | (What people, time, money, and technology will be needed?) | (What could go wrong? How will we make that less likely to happen?) | (Who needs to be consulted/ engaged? What needs to be communicated? To whom?)
Increase educator diversity by creating a racially, ethnically, and linguistically diverse hiring committee that oversees and monitors the hiring and selection process. | Human Resources Specialists, Jaime Markham and Kimberly Grant | Monitor the racial, ethnic, and linguistic diversity data of teachers and leaders by district and by school. Plan and facilitate professional learning sessions for hiring committee related to the benefits of diversity in the teaching workforce and cultural competency, Incorporate student involvement into hiring process at Rockville High School. | Human Resources Specialists, Jaime Markham and Kimberly Grant Hiring Committee Chair-Building Administrators | by August 2025 | Formation of a diverse hiring committee, (including at least 2 members that are racially, ethnically, culturally, and linquistically diverse) Track and analyze demographic data of staff with the goal of increasing the diversity of the teaching and admnistrative staff from 6.6% to 8.6% On-going professional learning for hiring committee members | Human Resources Specialists Jaime Markham and Kimberly Grant, Professional learning resources, time to plan and facilitate professional learning sessions | Lack of progress in recruiting, attracting, selecting, and hiring staff representative of the experiences and backgrounds of students enrolled in Vernon Public Schools | Hiring Committee and Building Administrators
Adopt procedures that ensure hiring practices prioritze candidates who have demonstrated high levels of cultural responsiveness | Robert Testa, Assistant Superintendent Increasing Educator Diversity team members (committee work) | Revamp the open ended questions in Applitrack teaching application to assess the cultural competencies of our teacher/administrator candidates. Review and revise interview questions that center on equity and cultural responsivenes | Human Resources Specialists Jaime Markham & Kimberly Grant, Hiring Committee members | by September 2024 | Revise Applitrack online application and in-person interview questions to include questions that center on equity and cultural responsiveness | Research and identify cultural responsive questions | Ineffective questions that dont prompt desired outcome | Review open ended questions for accuracy and purpose. Communicate revised application to all hiring commitees and administrators
HIRING & SELECTION (continued)
Connect candidates of color with other teachers of color within the school district prior to their decision to accept or reject the job offer. | Robert Testa Assistant Superintendent Human Resources Specialists Jaime Markham & Kimberly Grant and Hiring Committees | Identify staff that would serve as District Ambassadors. Provide District Ambassadors with training and resources to support potential new hires. | Robert Testa Assistant Superintendent, Human Resources Specialists Jaime Markham & Kimberly Grant, Hiring Committees, District Ambassadors | by February 2025 | Identify at least 3 district ambassadors. Increase the diversity of VPS teaching staff from 6.6% to 8.6% by August 2025 | Stipend for district ambassadors, training materials, professional learning sessions | Lack of support for district ambassadors. Failure to increase educational diversity of VPS teaching staff. | Promote district ambassadors program to staff. Communicate to staff and administrators the importance of this inititiave.
RETENTION
Goal | Who Manages the Goal? | Strategies/Key Activities (How are we going to do it?) |  |  | Indicators of Progress | Resources Required | Risks and Mitigation | Communication/ Engagement Efforts
(What are we trying to do?) | (name, position) | What? | Who Owns This? | By When? | (How will we know if we are on track for success?) | (What people, time, money, and technology will be needed?) | (What could go wrong? How will we make that less likely to happen?) | (Who needs to be consulted/ engaged? What needs to be communicated? To whom?)
Retain a diverse and highly qualified staff and personnel that is reflective of the Vernon Community | Robert Testa, Assistant Superintendent Human Resources Specialists Jaime Markham & Kimberly Grant, Building based administrators and staff, Professional Development and Educator Evaluation Committee | Provide professional learning opportunities for educators focused on equity and inclusion. Provide high-quality induction program, mentors for new teachers and support with district instructional coaches, consultants, and/or interventionists. | Professional Development and Educator Evaluation Committee Office of Teaching & Learning- Dominique Fox and Melissa Trantolo Human Resources Specialists Jaime Markham & Kimberly Grant | by August 2025 | Increase in favorable responses on staff and student climate survey questions, Increase in staff diversity from 6.6% to 8.6% by August 2025, District Professional Learning sessions meet the needs of staff as measured by staff responses and completion of self-reflection questions | Administrators, Professional Development Evaluation Committee members, District instructional coaches, Consultants, Inteventionists Professional learning days, Professional Learning Communities (PLCs), New Teacher Academy in August and then monthly meetings Funding needed for educational consultants | Strategies do not contribute to an increase in the diversity of candidates seeking imployment in Vernon Public Schools or result in a more diverse staff diversity | Communicate with stakeholders(teachers administrators, Board of Education members, VPS community)
RETENTION (continued)
As a menas to retain staff, continue to foster a welcoming school and district climate that promotes inclusivity and diversity. | Robert Testa, Assistant Superintendent Human Resources Specialists Jaime Markham & Kimberly Grant, Building based administrators and staff, Professional Development and Educator Evaluation Committee | Celebrate diversity by recognizing or highlighting staff and students from Vernon Public Schools. Building and district based activities that promote a sense of belonging among all staff. Explore various finacial supports or incentives aimed at retaining staff.(ex. tuition reimbursement. payment of test fees, books, supplies) | Building & central office administration and staff | by June 2025 | Increase in favorable responses on staff and student surveys, Increased staff retention, staff recommendation and recruitment of new teaching candidates | VPS administration and staff, Funding to support activities and recognitions, incentives to support retention | Strategies do not yield positive results(retention) and or increase in favorable responses on staff and student surveys | Communicate with stakeholders (administrators, teachers, Board of Education members,VPS community)
Vernon Public Schools Increasing Educator Diversity Plan

## Recruitment
RECRUITMENT
Goal | Who Manages the Goal? | Strategies/Key Activities (How are we going to do it?) |  |  | Indicators of Progress | Resources Required | Risks and Mitigation | Communication/ Engagement Efforts
(What are we trying to do?) | (name, position) | What? | Who Owns This? | By When? | (How will we know if we are on track for success?) | (What people, time, money, and technology will be needed?) | (What could go wrong? How will we make that less likely to happen?) | (Who needs to be consulted/ engaged? What needs to be communicated? To whom?)
Increasing Educator Diversity
Plan Template

## Hiring & Selection
HIRING & SELECTION
Goal | Who Manages the Goal? | Strategies/Key Activities (How are we going to do it?) |  |  | Indicators of Progress | Resources Required | Risks and Mitigation | Communication/ Engagement Efforts
(What are we trying to do?) | (name, position) | What? | Who Owns This? | By When? | (How will we know if we are on track for success?) | (What people, time, money, and technology will be needed?) | (What could go wrong? How will we make that less likely to happen?) | (Who needs to be consulted/ engaged? What needs to be communicated? To whom?)
Increasing Educator Diversity
Plan Template

## Retention
RETENTION
Goal | Who Manages the Goal? | Strategies/Key Activities (How are we going to do it?) |  |  | Indicators of Progress | Resources Required | Risks and Mitigation | Communication/ Engagement Efforts
(What are we trying to do?) | (name, position) | What? | Who Owns This? | By When? | (How will we know if we are on track for success?) | (What people, time, money, and technology will be needed?) | (What could go wrong? How will we make that less likely to happen?) | (Who needs to be consulted/ engaged? What needs to be communicated? To whom?)
Increasing Educator Diversity
Plan Template