## Governance Risk Scoring
Project Management Methodology: | Waterfall | Linear, phase gated delivery. Best for: Well defined, stable requirements; compliance heavy systems
Risk Domain | Weight (%) | Score (1-5) | Weighted Score | Scoring Criteria (lookup)
Strategic / Mission Impact | 15 | 1 | 0.15 | Department-level improvement; low visibility.
Financial Exposure | 25 | 1 | 0.25 | <$250K or discretionary; low overrun sensitivity.
Project Complexity | 12 | 1 | 0.12 | Single team; minimal dependencies; straightforward delivery.
Organizational Change Impact | 12 | 1 | 0.12 | Minimal workflow change; same roles/tools largely unchanged.
Technical Risk | 12 | 1 | 0.12 | Proven technology; no integrations; low security impact.
Regulatory / Compliance Risk | 12 | 1 | 0.12 | No regulatory, privacy, or audit implications.
Vendor / Procurement Risk | 12 | 1 | 0.12 | Existing contract/vehicle; low vendor dependency.
Total Risk Score | 100 | 7 | 1
Governance Tier: |  |  | Waterfall - Basic Governance
Recommended PM Experience: |  |  | #REF! | ==> Refer to the PM Deliverables tab for further details
Required PM Deliverables: |  |  | #REF! | ==> Refer to the PM Deliverables tab for further details

## Scoring Guidance
Domain Scoring Guidance (1–5)
Strategic/Mission Impact
Score | Criteria
1 | Department-level improvement; low visibility.
2 | Single program/branch improvement; limited leadership visibility.
3 | Multi-division impact; moderate leadership visibility.
4 | Enterprise service impact or high executive visibility.
5 | Enterprise-wide, legislative/public visibility, or mission-critical priority.
Financial Exposure
Score | Criteria
1 | <$250K or discretionary; low overrun sensitivity.
2 | $250K–$500K; limited funding complexity.
3 | $500K–$2M or mixed funding sources; moderate scrutiny.
4 | $2M–$3.75M, tight funding constraints, or high overrun sensitivity.
5 | >$3.75M, bond/federal funding, or high public scrutiny and audit attention.
Project Complexity
Score | Criteria
1 | Single team; minimal dependencies; straightforward delivery.
2 | Two functional areas; limited integrations/dependencies.
3 | 3–5 functional areas; moderate dependencies and coordination.
4 | Multiple systems/integrations; significant interdependencies; phased work.
5 | Multi-agency/enterprise; major integrations; many dependencies/critical path risk.
Organizational Change Impact
Score | Criteria
1 | Minimal workflow change; same roles/tools largely unchanged.
2 | Small process change; limited training required.
3 | Significant process/role changes; structured training and comms required.
4 | Major change to how work is done; high adoption risk.
5 | Culture shift, job redesign, labor impact, or sustained behavior change required.
Technical Risk
Score | Criteria
1 | Proven technology; no integrations; low security impact.
2 | Minor configuration; limited integrations; known patterns.
3 | Moderate integrations or data migration; some uncertainty.
4 | New platform/components; complex integration; higher security/cyber exposure.
5 | Custom development, high availability requirements, significant customization, major cyber/architecture risk.
Regulatory / Compliance Risk
Score | Criteria
1 | No regulatory, privacy, or audit implications.
2 | Low compliance sensitivity; limited records/privacy considerations.
3 | PII/data privacy or audit requirements; documented controls needed.
4 | High compliance burden; multiple policies/standards; frequent audit exposure.
5 | Statutory, regulatory or grant mandates, enforcement risk, significant audit/FOIA/public accountability.
Vendor / Procurement Risk
Score | Criteria
1 | Existing contract/vehicle; low vendor dependency.
2 | Simple quote process; low complexity contract.
3 | Competitive RFP required; moderate vendor dependency.
4 | Complex procurement; performance risk; multiple/interdependent vendors; strong contract management needed.
5 | Sole source or limited market; long-term lock-in; high vendor failure impact.

## PM Deliverables
Methodology | Definition
Waterfall | Linear, phase gated delivery. Best for: Well defined, stable requirements; compliance heavy systems
Agile | Iterative delivery using short cycles - Best for: evolving requirements, user centered systems, rapid iteration.
Hybrid | Structured planning (scope, timelines, deliverables) with iterative build cycles. Best for: Large, complex modernization efforts, or when procurement requires fixed deliverables.
Required PM Deliverables by Governance Tier*
Governance Tier | Waterfall | Agile | Hybrid | Recommended PM Experience
Tier 1 – Basic Governance | • Project Charter (scaled) • Governance Risk Scoring • High-level Process Evaluation (as‑is/to‑be) • Basic Schedule • Budget Estimate • Basic Issues and Risk Log • Lightweight plans (communication, test, training, production support, change control) • Monthly Status Report • Lightweight Change Control • Lightweight Project closeout report • Project sponsor Sign-offs | • Project Charter/definition (scaled) • Governance Risk Scoring • High-level Process Evaluation (as‑is/to‑be) • Budget Estimate • Product Vision • Product Backlog • Lightweight Release plan & Risk Log • Lightweight Sprint Artifacts (planning, backlog, review, retrospective) • Monthly Status Report (Burndown/Burnup Charts) • Project sponsor Sign-offs | • Project Charter (scaled) • Governance Risk Scoring • High-level Process Evaluation (as‑is/to‑be) • High-level schedule (milestones + sprints cycles) • High‑level Requirements + product Backlog • Lightweight Risk Log • Lightweight Sprint Artifacts (planning, backlog, review, retrospective) • Lightweight Change Control • Monthly Status Report (Burndown/Burnup Charts) • Project sponsor Sign-offs | 1 -3 Years • Fundamental PM Training • PM experience managing small projects - agency level oversight • Demonstrated success delivering 1-2 similar projects (complexity and risk)
Tier 2 – Standard Governance | • All Tier 1 Deliverables, plus: • Full Project Management Plan • Process Evaluation (as‑is → to‑be) • Detailed Schedule & Milestones • Budget Plan (describe how approved budget will be managed) • Test Plan • Risk & Issue Management Plan • Enterprise architecture, Cyber & Data Privacy assessments • Communication Plan • Change Management Plan • Training Plan • Basic Support Plan • Implementation Plan • Steering committee established and operational (Meeting cadence defined, stage gate approvals, decision escalation process, etc.) • Monthly Status Report • Key milestone reviews • Project Closeout Reports | • All Tier 1 Deliverables, plus: • Full project charter/definition • Process Evaluation (as‑is → to‑be) • Product Vision & Roadmap • Release Plan • Enterprise architecture, Cyber & Data Privacy assessments • Product Backlog with acceptance criteria • Definition of Ready (DoR) / Definition of Done (DoD) • Project Management Plan scaled to Agile (Test Plan, Risk Management Plan, Staffing, Change Management Plan, Training Plan) • Sprint Planning Notes • Sprint Backlog • Sprint Review Summary • Backlog Refinement Notes • Velocity Tracking • Monthly Status Report (Burndown/Burnup Charts) • Project closeout reports | • All Tier 1 Deliverables, plus: • Full project charter • Process Evaluation (as‑is → to‑be) • Hybrid Project schedule (milestones + Release plan) • Project Management Plan scaled to Agile (Test Plan, Risk Management Plan, Staffing, Change Management Plan, Training Plan) • Enterprise architecture, Cyber & Data Privacy assessments • Requirements Baseline + Prioritized Backlog • Product Backlog with acceptance criteria • Definition of Ready (DoR) / Definition of Done (DoD) • Sprint Planning Notes • Sprint Backlog • Sprint Review Summary • Backlog Refinement Notes • Velocity Tracking • Monthly Status Report (Burndown/Burnup Charts) • Project closeout reports | 3 - 5 Years • PM Certification preferred (CAPM, PMP, etc) • Experience managing projects up to $1M - $5M and coordinating multiple stakeholders • Demonstrated success delivering at least 2 similar projects (complexity, risk, governance requirements)
Tier 3 – Enhanced Governance | • All Tier 2 Deliverables, plus: • Quality Assurance Plan • Formal Test Plan • Staffing Plan • Procurement Plan • Formal Support Plan • Project Performance and Success Measures • Detailed reporting and risk management • Formal Stage Gates • Change Control Board • Traceability Matrix • Basic Benefits Realization Tracking • Executive steering reports / Governance Reporting Dashboard • Executive Sponsor Sign-offs | • All Tier 2 Deliverables, plus: • Program‑level Roadmap (if multiple teams) • Program increment (PI) plan • Agile Release Train / Cadence Calendar (if applicable) • Dependency & Integration Maps • Program Backlog • Increment Review Documentation (beyond sprint level) • Project performance and success measures • Traceability Matrix (epics → stories → tests → releases) • Basic Benefits Realization Tracking • Executive steering reports / Governance Dashboard (velocity, quality, financials, risks) • Executive Sponsor Sign-offs | • All Tier 2 Deliverables, plus: • Dependency & Integration Maps • Refined Product Backlog (risk-adjusted, prioritized) • Agile Release Train / Cadence Calendar (if applicable) • Dependency & Integration Maps • Program Backlog • Full Procurement Plan • Increment Review Documentation (beyond sprint level) • Project performance and success measures • Traceability Matrix (WBS ↔ Backlog ↔ Testing) • Basic Benefits Realization Tracking • Executive steering reports / Governance Dashboard (velocity, quality, financials, risks) • Executive Sponsor Sign-offs | 5 - 7 Years • PMP or equivalent certification strongly preferred •Experience managing large, complex projects with vendor management, risk management and governance reporting • Demonstrated success delivering at least 2-3 large projects (comparable complexity, risk and governance requirements)
Tier 4 – High Control Governance | • All Tier 3 Deliverables, plus: • Independent Independent Verification & Validation (if applicable) • Monthly Executive Reporting • Formal Benefits Realization Tracking • Legislative/Public Reporting (if applicable) | • All Tier 3 Deliverables, plus: • Independent Independent Verification & Validation (if applicable) • Increment Approval Gates • Monthly Executive Reporting • Formal Benefits Realization Tracking • Legislative/Public Reporting (if applicable) | • Integrated Master Schedule combining Waterfall phases + Agile increments • Enterprise‑level Roadmap • Requirements Baseline + Iterative Decomposition • Formal Hybrid Gate Reviews (milestone package + demo) • Vendor Performance Artifacts (aligned to contract) • Detailed Risk Register + Sprint-Level Risk Updates 1 • Comprehensive Hybrid Traceability Matrix (reqs → features → stories → tests → increments → milestones) | 7+ Years • PMP or equivalent certification • Experience managing large programs, enterprise projects or statewide initiatives, executive steering committees, legislative/public scrutiny, and complex vendor relationships • Demonstrated success delivering at least 1-2 enterprise-wide or mission-critical projects (comparable complexity, risk and governance requirements)
* Equivalent artifacts should be used for alternatively selected Project Management methodologies